## Summary
Overall Project Estimate Summary |  |  | Estimate Summary for Projecte Scope of Work Through 2031 |  | Comment
|  |  | Bridge Construction Only | 9194736.4286
| Original Budget | REV3 Estimate | Road Construction Only | 12872859.1429
Engineering/Project Management | 1.11 | 2.1966 | Engineering/Project Management | 2196620
Surveying |  | 1.3756 | Survey/LiDAR | 1375606
Construction Oversight |  | 1.1494 | Soil Borings | 152000
Permitting | 0.9 | 1.0801 | Construction Oversight | 1149418
Mitigation | 1.34 | 2.3827 | 6% Subcontractor M/U | 1256170.02
Road Construction | 6.64 | 12.8729 | 4% Escalation (By 1898) | 0 | To be accounted for by 1898.
Bridge Construction | 3.37 | 9.1947 | 0% Contingency | 0
Contingency (0%) | - | 0 | Tree Trimming/Fencing/Gates | 62250
Subcontractor M/U (6%) | - | 1.2562 | Permit & Mitigation | 3462792.9293
Escalation over time | - | 0 | Estimated 2021 PM/Engr/ECT/BJR | 736936
Tree Trim / Fencing |  | 0.06225 |  | 32459388.5207
Soil Borings |  | 0.152
Estimated 2021 PM/Engr/ECT/BJRock |  | 0.73694
Total | 13.36 | 32.4594
Highlighted green items were not estimated in the original budget estimate.

## Annual Cost Estimate
| Placeholder FP | WO | Work Pro WR# | Proposed Year of Construction | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | TOTAL | COUNTY
BRIDGE CONSTRUCTION | [17 empty] | Estimate is based on the following:
HAMPTON SUBSTATION | TXE - TBD4 | PRE-09816.1 | WR#2313981 | 2022 | 39000 | 857043.4009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH | 1. 1.4M planned spend for 2022.
BLOUNT RD | TXE - TBD23 | PRE-09875.1 | WR#2343385 | 2025 | 0 | 0 | 0 | 0 | 991019.309 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH | 2. Bringing the overall project in a couple years.
WEST OF FORBES RD | TXE - TBD12 | PRE-09837.1 | WR#2318656 | 2024 | 38669 | 0 | 0 | 550545.0919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH | 3. Somewhat balancing the annual spend for 2023 and beyond.
EAST OF SYDNEY WASHER RD | TXE - TBD16 | PRE-09841.1 | WR#2318671 | 2024 | 40650 | 0 | 0 | 646648.5574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH | 4. Grouping by County for permitting purposes.
TAMPA PALMS #1 | TXE - TBD14 | PRE-09839.1 | WR#2318663 | 2023 | 38650 | 0 | 542536.4697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH | 5. Proximity of projects to each other for construction/mobilization purposes.
TAMPA PALMS #2 | TXE - TBD21 | PRE-09873.1 | WR#2343382 | 2023 | 41650 | 0 | 686691.6681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
TAMPA PALMS #3 | TXE - TBD17 | PRE-09842.1 | WR#2318676 | 2023 | 41650 | 0 | 638639.9353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
TAMPA PALMS #4 | TXE - TBD25 | PRE-09877.1 | WR#2343389 | 2023 | 41650 | 0 | 702708.9123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
MORRIS BRIDGE RD | TXE - TBD6 | PRE-09818.1 | WR#2314042 | 2022 | 37650 | 518510.6033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
C.R. 542 | TXE - TBD28 | PRE-09880.1 | WR#2343398 | 2026 | 0 | 0 | 0 | 0 | 0 | 678683.046 | 0 | 0 | 0 | 0 | 0 |  | POLK
COLUMBUS DRIVE #1 | TXE - TBD13 | PRE-09838.1 | WR#2318659 | 2025 | 41650 | 0 | 0 | 0 | 630631.3132 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
COLUMBUS DRIVE #2 | TXE - TBD11 | PRE-09836.1 | WR#2318651 | 2025 | 41650 | 0 | 0 | 0 | 630631.3132 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
Proposed Bridge A | TBD | TBD | TBD | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
BAYSIDE STATION | n/a | n/a | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
19TH AV NE | TXE - TBD15 | PRE-09840.1 | WR#2318665 | n/a | 5372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
Proposed Bridge M | TXE - TBD18 | PRE-09843.1 | WR#2318681 | n/a | 7714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
Proposed Bridge P | TXE - TBD3 | PRE-09815.1 | WR#2313976 | n/a | 10405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
RACETRACK ROAD (KML_1) | TBD | TBD | TBD | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526655.8187 | 0 | 0 | 0 |  | HILLSBOROUGH
COUNTRYWAY BLVD (KML_2) | TBD | TBD | TBD | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823123.4831 | 0 | 0 | 0 |  | HILLSBOROUGH
PROGRESS BLVD (KML_5) | TBD | TBD | TBD | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
LITTLE FISHHAWK CREEK (KML_12) | TBD | TBD | TBD | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526655.8187 | 0 |  | HILLSBOROUGH
KEYSVILLE ROAD WEST (KML_14) | TBD | TBD | TBD | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622807.4936 | 0 |  | HILLSBOROUGH
HOLLOWAY ROAD (KML_15) | TBD | TBD | TBD | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638832.7728 | 0 | 0 |  | HILLSBOROUGH
KIRKLAND ROAD (KML_18) | TBD | TBD | TBD | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622807.4936 | 0 | 0 |  | HILLSBOROUGH
KEYSVILLE ROAD EAST (KML_20) | TBD | TBD | TBD | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590756.9353 | 0 | 0 |  | HILLSBOROUGH
BRIDGES TOTAL |  |  |  |  | 426360 | 1375554.0042 | 2570576.9855 | 1197193.6493 | 2252281.9354 | 678683.046 | 0 | 1349779.3017 | 1852397.2017 | 1149463.3123 |  | 12852289.436
ROAD CONSTRUCTION
230623 | TXE - TBD2 | PRE-09814.1 | WR#2313972 | 2027 | 28700 | 0 | 0 | 0 | 0 | 0 | 149087.767 | 0 | 0 | 0 | 0 |  | POLK
230612 | TXE - TBD27 | PRE-09879.1 | WR#2343395 | 2025 | 0 | 0 | 0 | 0 | 871512.3891 | 0 | 0 | 0 | 0 | 0 | 0 |  | POLK
230606 | TXE - TBD10 | PRE-09822.1 | WR#2314074 | 2025 | 23700 | 0 | 0 | 0 | 148621.4929 | 0 | 0 | 0 | 0 | 0 | 0 |  | POLK
230020 | TXE - TBD20 | PRE-09872.1 | WR#2343379 | 2024 | 43700 | 0 | 0 | 1304003.7553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
230008 | TXE - TBD1 | PRE-09813.1 | WR#2313969 | 2022 | 28000 | 166473.0866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
230007 | TXE - TBD30 | PRE-09881.1 | WR#2343399 | 2023 | 33700 | 0 | 324877.7348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
230006 | TBD | TBD | TBD | 2026 | 0 | 0 | 0 | 0 | 0 | 1260617.6035 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
66839 | TXE - TBD9 | PRE-09821.1 | WR#2314067 | 2025 | 33700 | 0 | 0 | 0 | 291612.9128 | 0 | 0 | 0 | 0 | 0 | 0 |  | POLK
66833 | TBD | TBD | TBD | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 2137983.4225 | 0 | 0 | 0 | 0 |  | POLK
66055 | TBD | TBD | TBD | 2026 | 0 | 0 | 0 | 0 | 0 | 1402807.3739 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
67051 | TBD | TBD | TBD | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
66046 | TBD | TBD | TBD | 2024 | 0 | 0 | 0 | 496313.4232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
66035 | TXE - TBD26 | PRE-09878.1 | WR#2343392 | 2025 | 28700 | 0 | 0 | 0 | 215916.4006 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
66033 | TBD | TBD | TBD | 2023 | 0 | 0 | 215685.4311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
66016 | TXE - TBD24 | PRE-09876.1 | WR#2343386 | 2025 | 28700 | 0 | 0 | 0 | 145932.6297 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
66007 | TXE - TBD7 | PRE-09819.1 | WR#2314047 | 2023 | 23700 | 0 | 166026.9798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
66001 | TBD | TBD | TBD | 2023 |  | 0 | 243632.7455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
230010 | TXE - TBD13 | PRE-09838.1 | WR#2318659 | 2025 | 23700 | 0 | 0 | 0 | 147068.447 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
230037 | TXE - TBD8 | PRE-09820.1 | WR#2314055 | n/a | 8895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
230033 | TXE - TBD5 | PRE-09817.1 | WR#2314000 | n/a | 5381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
66830 | TXE - TBD22 | PRE-09874.1 | WR#2343383 | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | POLK
230004 | TBD | TBD | TBD | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336380.3388 | 0 |  | HILLSBOROUGH
230005 | TBD | TBD | TBD | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290648.3697 | 0 |  | HILLSBOROUGH
230021 | TBD | TBD | TBD | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1931686.9575 | 0 | 0 | 0 |  | HILLS & POLK
230402 | TBD | TBD | TBD | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4424772.1816 |  | HILLSBOROUGH
230604 | TBD | TBD | TBD | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702698.0306 | 0 | 0 |  | POLK
66014 | TBD | TBD | TBD | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370332.8613 | 0 |  | HILLSBOROUGH
66025 | TBD | TBD | TBD | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 463875.5253 | 0 | 0 |  | HILLSBOROUGH
66021 | TBD | TBD | TBD | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 1087955.2248 | 0 | 0 | 0 | 0 |  | HILLSBOROUGH
ROADS TOTAL |  |  |  |  | 310576 | 166473.0866 | 950222.8911 | 1800317.1785 | 1820664.2721 | 2663424.9774 | 3375026.4142 | 1931686.9575 | 1166573.5559 | 997361.5698 | 4424772.1816 | 19607099.0847
COMBINED ROADS & BRIDGES TOTAL |  |  |  |  | 736936 | 1542027.0908 | 3520799.8765 | 2997510.8278 | 4072946.2075 | 3342108.0233 | 3375026.4142 | 3281466.2593 | 3018970.7576 | 2146824.8821 | 4424772.1816 | 32459388.5207

## Access Bridge
[8 empty] | 16' Bank Stabilization (per foot) |  |  |  |  | Access Using Temporary Matting |  | Bridge ENG, RM & CONST (per foot) |  |  |  |  | 14' Bridge Approach (per foot) |  |  |  |  | Project & Construction Management |  | 6% Subcontractor Markup |  |  | Pemit & Mitigation
|  | Placeholder FP | WO | Work Pro WR# | 1898 Year of Const. | Revised Year of Const. | Reason for Deferring | Footage | Construction (w/ Flexamat) | Escalation (By 1898) | Engineering | Survey & LiDAR | Length | Matting | Footage | Removal | Construction | Soil Borings | Escalation (By 1898) | Footage | Construction | Escalation (By 1898) | Engineering | Survey | Project Management | Construction Support | York & Road Contractor | Subtotal | Contingency | Permit (Bridge + Road) | Mitigation (Bridge & Stabilization) | Total
[5 empty] | 2022 | 2022 |  |  | 270 | 0% | 50 | 43 |  | 6 |  | 1325 | 6100 | 2000 | 0% |  | 285 | 0% | 50 | 43 | 40 | 70 | 6% |  | 0% | [$50k/bridge + $60k/mi rd] | [$175k * AC/2]
HAMPTON SUBSTATION | 230403 | TXE - TBD4 | PRE-09816.1 | WR#2313981 | 2022 | 2022 | n/a | 478 | 129060 | 0 | 23900 | 20554 | 1000 | 25714.2857 | 60 | 79500 | 366000 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 25520 | 44660 | 36183.6 | 796891.8857 | 0 | 51136.3636 | 9015.1515 | 60151.5152
BLOUNT RD | 230403 | TXE - TBD23 | PRE-09875.1 | WR#2343385 | 2025 | 2025 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 92 | 121900 | 561200 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 16800 | 29400 | 46389.6 | 929967.8857 | 0 | 51136.3636 | 9915.0597 | 61051.4233
WEST OF FORBES RD | 66413 | TXE - TBD12 | PRE-09837.1 | WR#2318656 | 2023 | 2024 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 37 | 49025 | 225700 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 14600 | 25550 | 21887.1 | 491040.3857 | 0 | 51136.3636 | 8368.3425 | 59504.7062
EAST OF SYDNEY WASHER RD | 66413 | TXE - TBD16 | PRE-09841.1 | WR#2318671 | 2023 | 2024 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 49 | 64925 | 298900 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 15080 | 26390 | 27233.1 | 586806.3857 | 0 | 51136.3636 | 8705.8081 | 59842.1717
TAMPA PALMS #1 | 230061 | TXE - TBD14 | PRE-09839.1 | WR#2318663 | 2023 | 2023 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 36 | 47700 | 219600 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 14560 | 25480 | 21441.6 | 483059.8857 | 0 | 51136.3636 | 8340.2204 | 59476.584
TAMPA PALMS #2 | 230061 | TXE - TBD21 | PRE-09873.1 | WR#2343382 | 2025 | 2023 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 54 | 71550 | 329400 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 15280 | 26740 | 29460.6 | 626708.8857 | 0 | 51136.3636 | 8846.4187 | 59982.7824
TAMPA PALMS #3 | 230061 | TXE - TBD17 | PRE-09842.1 | WR#2318676 | 2023 | 2023 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 48 | 63600 | 292800 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 15040 | 26320 | 26787.6 | 578825.8857 | 0 | 51136.3636 | 8677.686 | 59814.0496
TAMPA PALMS #4 | 230061 | TXE - TBD25 | PRE-09877.1 | WR#2343389 | 2026 | 2023 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 56 | 74200 | 341600 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 15360 | 26880 | 30351.6 | 642669.8857 | 0 | 51136.3636 | 8902.663 | 60039.0266
MORRIS BRIDGE RD | 66426 | TXE - TBD6 | PRE-09818.1 | WR#2314042 | 2022 | 2022 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 33 | 43725 | 201300 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 14440 | 25270 | 20105.1 | 459118.3857 | 0 | 51136.3636 | 8255.854 | 59392.2176
C.R. 542 | 230608 | TXE - TBD28 | PRE-09880.1 | WR#2343398 | 2027 | 2026 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 53 | 70225 | 323300 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 15240 | 26670 | 29015.1 | 618728.3857 | 0 | 51136.3636 | 8818.2966 | 59954.6602
COLUMBUS DRIVE #1 | 230001 | TXE - TBD13 | PRE-09838.1 | WR#2318659 | 2023 | 2025 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 47 | 62275 | 286700 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 15000 | 26250 | 26342.1 | 570845.3857 | 0 | 51136.3636 | 8649.5638 | 59785.9275
COLUMBUS DRIVE #2 | 230001 | TXE - TBD11 | PRE-09836.1 | WR#2318651 | 2022 | 2025 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 47 | 62275 | 286700 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 15000 | 26250 | 26342.1 | 570845.3857 | 0 | 51136.3636 | 8649.5638 | 59785.9275
BAYSIDE STATION | 66008 | n/a | n/a | n/a | 2024 |  | Overall Bayside SOW TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19TH AV NE | 230008 | TXE - TBD15 | PRE-09840.1 | WR#2318665 | 2023 |  | Developer creating access | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Bridge A | 230020 | TBD | TBD | TBD | 2029 |  | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Bridge M | 230401 | TXE - TBD18 | PRE-09843.1 | WR#2318681 | 2023 |  | Req's 2600' of new road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Bridge P | 66008 | TXE - TBD3 | PRE-09815.1 | WR#2313976 | 2022 |  | Overall Bayside SOW TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RACETRACK ROAD (KML_1) | 230011 | TBD | TBD | TBD |  | 2028 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 34 | 45050 | 207400 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 14480 | 25340 | 20550.6 | 467098.8857 | 0 | 51136.3636 | 8420.5693 | 59556.933
COUNTRYWAY BLVD (KML_2) | 230011 | TBD | TBD | TBD |  | 2028 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 71 | 94075 | 433100 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 15960 | 27930 | 37034.1 | 762377.3857 | 0 | 51136.3636 | 9609.7337 | 60746.0973
PROGRESS BLVD (KML_5) | 66007 | TBD | TBD | TBD |  | 2030 | Development being built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LITTLE FISHHAWK CREEK (KML_12) | 230005 | TBD | TBD | TBD |  | 2030 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 34 | 45050 | 207400 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 14480 | 25340 | 20550.6 | 467098.8857 | 0 | 51136.3636 | 8420.5693 | 59556.933
KEYSVILLE ROAD WEST (KML_14) | 230021 | TBD | TBD | TBD |  | 2030 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 46 | 60950 | 280600 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 14960 | 26180 | 25896.6 | 562864.8857 | 0 | 51136.3636 | 8806.2443 | 59942.6079
HOLLOWAY ROAD (KML_15) | 230403 | TBD | TBD | TBD |  | 2029 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 48 | 63600 | 292800 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 15040 | 26320 | 26787.6 | 578825.8857 | 0 | 51136.3636 | 8870.5234 | 60006.8871
KIRKLAND ROAD (KML_18) | 66024 | TBD | TBD | TBD |  | 2029 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 46 | 60950 | 280600 | 8000 | 0 | 100 | 28500 | 0 | 5000 | 4300 | 14960 | 26180 | 25896.6 | 562864.8857 | 0 | 51136.3636 | 8806.2443 | 59942.6079
KEYSVILLE ROAD EAST (KML_20) | 230021 | TBD | TBD | TBD |  | 2029 | n/a | 228 | 61560 | 0 | 11400 | 9804 | 1000 | 25714.2857 | 42 | 55650 | 256200 | 8000 |  | 100 | 28500 | 0 | 5000 | 4300 | 14800 | 25900 | 24114.6 | 530942.8857 | 0 | 51136.3636 | 8677.686 | 59814.0496
[8 empty] | 4582 | 1237140 | 0 | 229100 | 197026 |  | 488571.4286 | 933 | 1236225 | 5691300 | 152000 | 0 | 1900 | 541500 | 0 | 95000 | 81700 | 296600 | 519050 | 522369.9 | 11287582.3286 | 0 | 971590.9091 | 166756.1983 | 1138347.1074
[28 empty] | 12425929.436 | w/ Permit & Mitigation
ASSUMPTIONS: | Estimate for Mitigation $175k * (AC/2) | [8 empty] | from Nate Alcoz
Estimate for Permitting $60k per road mile
Estimate for Permitting $50k per bridge
Bridge Construction construction estimate from Polk Project (York Bridge Concepts)
Bridge ENG & CON - for budget - 25% ENG & 75% CON
Bridge Removal is based on a $52k per bridge removal cost + 6% M/U
Bridge Construction includes contractor installation of bridge approaches.

## Access Road
[9 empty] | 14' Road | [11 empty] | Real Estate | Project & Construction Management |  | 6% Subcontractor Markup |  |  | Permit & Mitigation
[9 empty] | Construction | [6 empty] | Access Using Temporary Matting |  | Escalation | Survey & LiDAR | Engineering | Boundary Survey | Project Management | Construction Support | Road Contractor |  |  | Permit | Mitigation
| Placeholder FP | WO | Work Pro WR# |  |  | 1898 Year of Const. | Revised Year of Const. | Reason for Deferring | R4 + Sub-base |  | R7 | R6 (Cabled Concrete) | Culverts | Tree Trimming | Fencing/Gates | Length | Matting | (By 1898) | [6 empty] | Subtotal | Contingency |  |  | Total
Circuit |  |  |  | Linear Feet | Acres | 2022 | 2022 |  | 110 | 30 | 155 | 430 | 25000 | 2500 | 1500 |  | 6 | 0% | 10 | 10 | 5 | 10 | 8 | 6% |  | 0% | [$60k/mi rd] | [$175k * AC/2]
230623 | TXE - TBD2 | PRE-09814.1 | WR#2313972 | 411 | 0.13209 | 2022 | 2027 | n/a | 37298.25 | 10172.25 | 9555.75 | 4418.25 | 25000 | 2500 | 1500 | 1000 | 25714.2857 | 0 | 4110 | 4110 | 0 | 4110 | 3288 | 5186.67 | 136963.4557 | 0 | 566.1157 | 11558.1956 | 12124.3113
230612 | TXE - TBD27 | PRE-09879.1 | WR#2343395 | 3608 | 1.1596 | 2025 | 2025 | n/a | 327426 | 89298 | 83886 | 38786 | 25000 | 2500 | 1500 | 1000 | 25714.2857 | 0 | 36080 | 36080 | 0 | 36080 | 28864 | 33863.76 | 765078.0457 | 0 | 4969.697 | 101464.6465 | 106434.3434
230606 | TXE - TBD10 | PRE-09822.1 | WR#2314074 | 420 | 0.13499 | 2022 | 2025 | n/a | 38115 | 10395 | 9765 | 4515 | 25000 | 0 | 1500 | 1000 | 25714.2857 | 0 | 4200 | 4200 | 0 | 4200 | 3360 | 5267.4 | 136231.6857 | 0 | 578.5124 | 11811.2948 | 12389.8072
230037 | TXE - TBD8 | PRE-09820.1 | WR#2314055 | 0 | 0 | 2022 |  | Existing access sufficient | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230033 | TXE - TBD5 | PRE-09817.1 | WR#2314000 | 0 | 0 | 2022 |  | Extensive Public Outreach | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230020 | TXE - TBD20 | PRE-09872.1 | WR#2343379 | 5533 | 1.7783 | 2024 | 2024 | n/a | 502119.75 | 136941.75 | 128642.25 | 59479.75 | 25000 | 0 | 1500 | 1000 | 25714.2857 | 0 | 55330 | 55330 | 0 | 55330 | 44264 | 51131.01 | 1140782.7957 | 0 | 7621.2121 | 155599.7475 | 163220.9596
230008 | TXE - TBD1 | PRE-09813.1 | WR#2313969 | 499 | 0.16038 | 2022 | 2022 | n/a | 45284.25 | 12350.25 | 11601.75 | 5364.25 | 25000 | 0 | 1500 | 1000 | 25714.2857 | 0 | 4990 | 4990 | 0 | 4990 | 3992 | 5976.03 | 151752.8157 | 0 | 687.3278 | 14032.9431 | 14720.2709
230007 | TXE - TBD30 | PRE-09881.1 | WR#2343399 | 1200 | 0.38567 | 2027 | 2023 | n/a | 108900 | 29700 | 27900 | 12900 | 25000 | 0 | 1500 | 1000 | 25714.2857 | 0 | 12000 | 12000 | 0 | 12000 | 9600 | 12264 | 289478.2857 | 0 | 1652.8926 | 33746.5565 | 35399.449
230006 | TBD | TBD | TBD | 5341 | 1.7166 | 2028 | 2026 | n/a | 484695.75 | 132189.75 | 124178.25 | 57415.75 | 25000 | 0 | 1500 | 1000 | 25714.2857 | 0 | 53410 | 53410 | 0 | 53410 | 42728 | 49408.77 | 1103060.5557 | 0 | 7356.7493 | 150200.2984 | 157557.0478
66839 | TXE - TBD9 | PRE-09821.1 | WR#2314067 | 1030 | 0.33104 | 2022 | 2025 | n/a | 93472.5 | 25492.5 | 23947.5 | 11072.5 | 25000 | 0 | 1500 | 1000 | 25714.2857 | 0 | 10300 | 10300 | 5150 | 10300 | 8240 | 10739.1 | 261228.3857 | 0 | 1418.7328 | 28965.7943 | 30384.5271
66833 | TBD | TBD | TBD | 9024 | 2.9003 | 2027 | 2027 | n/a | 818928 | 223344 | 209808 | 97008 | 25000 | 0 | 1500 | 1000 | 25714.2857 | 0 | 90240 | 90240 | 45120 | 90240 | 72192 | 82445.28 | 1871779.5657 | 0 | 12429.7521 | 253774.1047 | 266203.8567
66830 | TXE - TBD22 | PRE-09874.1 | WR#2343383 | 0 | 0 | 2025 |  | Veg SPP will provide access | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66055 | TBD | TBD | TBD | 5841 | 1.8773 | 2028 | 2026 | n/a | 530070.75 | 144564.75 | 135803.25 | 62790.75 | 25000 | 0 | 1500 | 1000 | 25714.2857 | 0 | 58410 | 58410 | 29205 | 58410 | 46728 | 53893.77 | 1230500.5557 | 0 | 8045.4545 | 164261.3636 | 172306.8182
67051 | TBD | TBD | TBD | 0 | 0 | 2029 |  | De-energized T-line | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66046 | TBD | TBD | TBD | 2031 | 0.65275 | 2029 | 2024 | n/a | 184313.25 | 50267.25 | 47220.75 | 21833.25 | 0 | 0 | 1500 | 1000 | 25714.2857 | 0 | 20310 | 20310 | 10155 | 20310 | 16248 | 18218.07 | 436399.8557 | 0 | 2797.5207 | 57116.0468 | 59913.5675
66035 | TXE - TBD26 | PRE-09878.1 | WR#2343392 | 817 | 0.26258 | 2025 | 2025 | n/a | 74142.75 | 20220.75 | 18995.25 | 8782.75 | 0 | 0 | 1500 | 1000 | 25714.2857 | 0 | 8170 | 8170 | 4085 | 8170 | 6536 | 7328.49 | 191815.2757 | 0 | 1125.3444 | 22975.7805 | 24101.1249
66033 | TBD | TBD | TBD | 816 | 0.26226 | 2028 | 2023 | n/a | 74052 | 20196 | 18972 | 8772 | 0 | 0 | 1500 | 1000 | 25714.2857 | 0 | 8160 | 8160 | 4080 | 8160 | 6528 | 7319.52 | 191613.8057 | 0 | 1123.9669 | 22947.6584 | 24071.6253
66016 | TXE - TBD24 | PRE-09876.1 | WR#2343386 | 514 | 0.1652 | 2026 | 2025 | n/a | 46645.5 | 12721.5 | 11950.5 | 5525.5 | 0 | 0 | 1500 | 1000 | 25714.2857 | 0 | 5140 | 5140 | 2570 | 5140 | 4112 | 4610.58 | 130769.8657 | 0 | 707.989 | 14454.775 | 15162.764
66007 | TXE - TBD7 | PRE-09819.1 | WR#2314047 | 601 | 0.19316 | 2022 | 2023 | n/a | 54540.75 | 14874.75 | 13973.25 | 6460.75 | 0 | 0 | 1500 | 1000 | 25714.2857 | 0 | 6010 | 6010 | 3005 | 6010 | 4808 | 5390.97 | 148297.7557 | 0 | 827.8237 | 16901.4004 | 17729.2241
66001 | TBD | TBD | TBD | 937 | 0.30115 | 2029 | 2023 | n/a | 85032.75 | 23190.75 | 21785.25 | 10072.75 | 0 | 0 | 1500 | 1000 | 25714.2857 | 0 | 9370 | 9370 | 4685 | 9370 | 7496 | 8404.89 | 215991.6757 | 0 | 1290.6336 | 26350.4362 | 27641.0698
230010 | TXE - TBD13 | PRE-09838.1 | WR#2318659 | 520 | 0.16713 | 2023 | 2025 | n/a | 47190 | 12870 | 12090 | 5590 | 0 | 0 | 1250 | 1000 | 25714.2857 | 0 | 5200 | 5200 | 2600 | 5200 | 4160 | 4664.4 | 131728.6857 | 0 | 716.2534 | 14623.5078 | 15339.7612
230004 | TBD | TBD | TBD | 1213 | 0.38985 |  | 2030 | n/a | 110079.75 | 30021.75 | 28202.25 | 13039.75 | 25000 | 2500 | 1500 | 1000 | 25714.2857 | 0 | 12130 | 12130 | 6065 | 12130 | 9704 | 12380.61 | 300597.3957 | 0 | 1670.7989 | 34112.1442 | 35782.9431
230005 | TBD | TBD | TBD | 1015 | 0.32622 |  | 2030 | n/a | 92111.25 | 25121.25 | 23598.75 | 10911.25 | 25000 | 2500 | 1500 | 1000 | 25714.2857 | 0 | 10150 | 10150 | 5075 | 10150 | 8120 | 10604.55 | 260706.3357 | 0 | 1398.0716 | 28543.9624 | 29942.034
230021 | TBD | TBD | TBD | 8120 | 2.6097 |  | 2028 | n/a | 736890 | 200970 | 188790 | 87290 | 25000 | 2500 | 1500 | 1000 | 25714.2857 | 0 | 81200 | 81200 | 40600 | 81200 | 64960 | 74336.4 | 1692150.6857 | 0 | 11184.573 | 228351.6988 | 239536.2718
230402 | TBD | TBD | TBD | 18914 | 6.0789 |  | 2031 | n/a | 1716445.5 | 468121.5 | 439750.5 | 203325.5 | 25000 | 2500 | 1500 | 1000 | 25714.2857 | 0 | 189140 | 189140 | 94570 | 189140 | 151312 | 171158.58 | 3866817.8657 | 0 | 26052.3416 | 531901.9743 | 557954.3159
230604 | TBD | TBD | TBD | 2799 | 0.89959 |  | 2029 | n/a | 254009.25 | 69275.25 | 65076.75 | 30089.25 | 25000 | 2500 | 1500 | 1000 | 25714.2857 | 0 | 27990 | 27990 | 13995 | 27990 | 22392 | 26607.03 | 620128.8157 | 0 | 3855.3719 | 78713.843 | 82569.2149
66014 | TBD | TBD | TBD | 1360 | 0.4371 |  | 2030 | n/a | 123420 | 33660 | 31620 | 14620 | 25000 | 2500 | 1500 | 1000 | 25714.2857 | 0 | 13600 | 13600 | 6800 | 13600 | 10880 | 13699.2 | 330213.4857 | 0 | 1873.2782 | 38246.0973 | 40119.3756
66025 | TBD | TBD | TBD | 1765 | 0.56726 |  | 2029 | n/a | 160173.75 | 43683.75 | 41036.25 | 18973.75 | 25000 | 2500 | 1500 | 1000 | 25714.2857 | 0 | 17650 | 17650 | 8825 | 17650 | 14120 | 17332.05 | 411808.8357 | 0 | 2431.1295 | 49635.5601 | 52066.6896
66021 | TBD | TBD | TBD | 4467 | 1.4357 |  | 2027 | n/a | 405380.25 | 110558.25 | 103857.75 | 48020.25 | 25000 | 2500 | 1500 | 1000 | 25714.2857 | 0 | 44670 | 44670 | 22335 | 44670 | 35736 | 41568.99 | 956180.7757 | 0 | 6152.8926 | 125621.5565 | 131774.449
|  |  |  | 78796 |  |  |  |  | 7150737 | 1950201 | 1832007 | 847057 | 450000 | 25000 | 37250 |  | 642857.1429 | 0 | 787960 | 787960 | 308920 | 787960 | 630368 | 733800.12 | 16972077.2629 | 0 | 108534.4353 | 2215911.3866 | 2324445.8219
|  |  |  | 14.9235 | miles | [19 empty] | 19296523.0847 | w/ Permit & Mitigation
[25 empty] | 215.3926 | Base Cost per Foot
|  |  | ASSUMPTIONS: | Estimate for Mitigation $175k * (AC/2) | [5 empty] | from Nate Alcoz | [14 empty] | 244.8922 | Cost / ft total w/ Permit, Mitigation
|  |  |  | Estimate for Permitting $60k per road mile | [20 empty] | 1293030.6346 | Cost / mile total
Road Construction costs [R4 - $95.60 / R7 - $144.75 / R6 - $418.40 / sub-base - $97.81] from P&J (Scotty Orr)
Sub-base is only needed under 25% of R4 road, so $25 was used.
Boundary Survey costs $3.69 from GFY
Road Type - 2.5% R6, 15% R7, 82.5% R4
The above road unit pricing were increased in this revision to account for inflation.
Supplemental Road for Columbus Bridge #1 was renamed to 230010