## 2022
Tampa Electric Company
Storm Protection Plan
Projected Period Amount
Projected Period: January through December 2022
Capital Expenditures
(in Dollars)
Additions Only
End of
|  | Placeholder | Actual |  | Placeholder | Actual |  | PMO Est. |  | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Period
Line | Program | FP | FP | FP Description | PMO | PMO | PMO Description | In-Service Date | Depr Grp | January | February | March | April | May | June | July | August | September | October | November | December | Total
B | Transmission Asset Upgrades | [8 empty] | 1414824.5 | 1095257.5 | 1496512.544 | 1552687.74 | 589100.28 | 1445105.9 | 1425937.895 | 1312579.84 | 1425215.1 | 1711052 | 1550451 | 1460273.5 | 16478997.799
| 1 | TAU-TBD14 | PRE-09752 | SPP TAU - Circuit 66407 | TAU-TBD14.1 | PRE-09752.1 | SPP TAU - Circuit 66407 | 3/15/2022 | Transmission Line - Acct 355 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
| 2 | TAU-TBD15 | PRE-09753 | SPP TAU - Circuit 66033 | TAU-TBD15.1 | PRE-09753.1 | SPP TAU - Circuit 66033 | 5/15/2022 | Transmission Line - Acct 355 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
| 3 | TAU-TBD16 | PRE-09754 | SPP TAU - Circuit 66016 | TAU-TBD16.1 | PRE-09754.1 | SPP TAU - Circuit 66016 | 6/15/2022 | Transmission Line - Acct 355 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
| 4 | TAU-TBD17 | PRE-09755 | SPP TAU - Circuit 66427 | TAU-TBD17.1 | PRE-09755.1 | SPP TAU - Circuit 66427 | 3/15/2022 | Transmission Line - Acct 355 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
| 5 | TAU-TBD18 | PRE-09756 | SPP TAU - Circuit 66415 | TAU-TBD18.1 | PRE-09756.1 | SPP TAU - Circuit 66415 | 5/15/2022 | Transmission Line - Acct 355 | 0 | 307490 | 9510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317000
| 6 | TAU-TBD20 | PRE-09758 | SPP TAU - Circuit 66022 | TAU-TBD20.1 | PRE-09758.1 | SPP TAU - Circuit 66022 | 3/15/2022 | Transmission Line - Acct 355 | 672980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 672980
| 7 | TAU-TBD21 | PRE-09759 | SPP TAU - Circuit 66060 | TAU-TBD21.1 | PRE-09759.1 | SPP TAU - Circuit 66060 | 3/15/2022 | Transmission Line - Acct 355 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
| 8 | TAU-TBD22 | PRE-09760 | SPP TAU - Circuit 66048 | TAU-TBD22.1 | PRE-09760.1 | SPP TAU - Circuit 66048 | 3/15/2022 | Transmission Line - Acct 355 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
| 9 | TAU-TBD24 | PRE-09762 | SPP TAU - Circuit 66036 | TAU-TBD24.1 | PRE-09762.1 | SPP TAU - Circuit 66036 | 5/15/2022 | Transmission Line - Acct 355 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000
| 10 | TAU-TBD25 | PRE-09763 | SPP TAU - Circuit 230402 | TAU-TBD25.1 | PRE-09763.1 | SPP TAU - Circuit 230402 | 12/15/2022 | Transmission Line - Acct 355 | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 294700 | 0 | 0 | 300100
| 11 | TAU-TBD27 | PRE-09824 | SPP TAU - Circuit 230602 | TAU-TBD27.1 | PRE-09824.1 | SPP TAU - Circuit 230602 | 3/15/2022 | Transmission Line - Acct 355 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
| 12 | TAU-TBD28 | PRE-09825 | SPP TAU - Circuit 230012 | TAU-TBD28.1 | PRE-09825.1 | SPP TAU - Circuit 230012 | 3/15/2022 | Transmission Line - Acct 355 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
| 13 | TAU-TBD29 | PRE-09826 | SPP TAU - Circuit 230606 | TAU-TBD29.1 | PRE-09826.1 | SPP TAU - Circuit 230606 | 2022-04-15 | Transmission Line - Acct 355 | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000
| 14 | TAU-TBD30 | PRE-09827 | SPP TAU - Circuit 230033 | TAU-TBD30.1 | PRE-09827.1 | SPP TAU - Circuit 230033 | 2022-04-15 | Transmission Line - Acct 355 | 0 | 0 | 294699.519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294699.519
| 15 | TAU-TBD31 | PRE-09828 | SPP TAU - Circuit 230609 | TAU-TBD31.1 | PRE-09828.1 | SPP TAU - Circuit 230609 | 2022-04-15 | Transmission Line - Acct 355 | 0 | 0 | 105250.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105250.025
| 16 | TAU-TBD32 | PRE-09829 | SPP TAU - Circuit 230013 | TAU-TBD32.1 | PRE-09829.1 | SPP TAU - Circuit 230013 | 2022-05-15 | Transmission Line - Acct 355 | 0 | 0 | 84200 | 336800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421000
| 17 | TAU-TBD33 | PRE-09830 | SPP TAU - Circuit 66030 | TAU-TBD33.1 | PRE-09830.1 | SPP TAU - Circuit 66030 | 2022-06-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 978880 | 520030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1498910
| 18 | TAU-TBD34 | PRE-09831 | SPP TAU - Circuit 66025 | TAU-TBD34.1 | PRE-09831.1 | SPP TAU - Circuit 66025 | 2022-08-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 1376550 | 948290 | 0 | 0 | 0 | 0 | 0 | 2324840
| 19 | TAU-TBD35 | PRE-09832 | SPP TAU - Circuit 66020 | TAU-TBD35.1 | PRE-09832.1 | SPP TAU - Circuit 66020 | 2022-08-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 305900.245 | 0 | 0 | 0 | 0 | 0 | 305900.245
| 20 | TAU-TBD36 | PRE-09833 | SPP TAU - Circuit 66027 | TAU-TBD36.1 | PRE-09833.1 | SPP TAU - Circuit 66027 | 2022-09-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 122360 | 428260 | 0 | 0 | 0 | 0 | 550620
| 21 | TAU-TBD37 | PRE-09834 | SPP TAU - Circuit 66008 | TAU-TBD37.1 | PRE-09834.1 | SPP TAU - Circuit 66008 | 2022-09-15 | Transmission Line - Acct 355 | 6660 | 0 | 0 | 0 | 0 | 0 | 0 | 275310 | 0 | 0 | 0 | 0 | 281970
| 22 | TAU-TBD38 | PRE-09835 | SPP TAU - Circuit 66001 | TAU-TBD38.1 | PRE-09835.1 | SPP TAU - Circuit 66001 | 2022-11-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403603 | 1376550 | 97320 | 0 | 0 | 1877473
| 23 | TAU-TBD39 | PRE-10042 | SPP TAU - Circuit 66045 | TAU-TBD39.1 | PRE-10042.1 | SPP TAU - Circuit 66045 | 2022-12-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1283850 | 256770 | 167756 | 1708376
| 24 | TAU-TBD40 | PRE-10043 | SPP TAU - Circuit 66026 | TAU-TBD40.1 | PRE-10043.1 | SPP TAU - Circuit 66026 | 2023-02-15 | Transmission Line - Acct 355 | 5184.5 | 77767.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000 | 2582952
| 25 | TAU-TBD41 | PRE-10044 | SPP TAU - Circuit 230006 | TAU-TBD41.1 | PRE-10044.1 | SPP TAU - Circuit 230006 | 2023-04-15 | Transmission Line - Acct 355 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000
| 26 | TAU-TBD42 | PRE-10045 | SPP TAU - Circuit 66021 | TAU-TBD42.1 | PRE-10045.1 | SPP TAU - Circuit 66021 | 2023-05-15 | Transmission Line - Acct 355 | 0 | 0 | 2853 | 28530 | 14265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45648
| 27 | TAU-TBD43 | PRE-10046 | SPP TAU - Circuit 66028 | TAU-TBD43.1 | PRE-10046.1 | SPP TAU - Circuit 66028 | 2023-06-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 3077.74 | 46166.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49243.84
| 28 | TAU-TBD44 | PRE-10047 | SPP TAU - Circuit 66032 | TAU-TBD44.1 | PRE-10047.1 | SPP TAU - Circuit 66032 | 2023-07-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 2536 | 38040 | 0 | 0 | 0 | 0 | 0 | 0 | 40576
| 29 | TAU-TBD45 | PRE-10048 | SPP TAU - Circuit 66017 | TAU-TBD45.1 | PRE-10048.1 | SPP TAU - Circuit 66017 | 2023-09-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 6103.18 | 30515.9 | 45773.85 | 152579.5 | 0 | 0 | 0 | 0 | 234972.43
| 30 | TAU-TBD46 | PRE-10049 | SPP TAU - Circuit 66011 | TAU-TBD46.1 | PRE-10049.1 | SPP TAU - Circuit 66011 | 2023-09-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 1394.8 | 20922 | 0 | 0 | 0 | 0 | 22316.8
| 31 | TAU-TBD47 | PRE-10050 | SPP TAU - Circuit 66047 | TAU-TBD47.1 | PRE-10050.1 | SPP TAU - Circuit 66047 | 2023-09-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 63.4 | 951 | 0 | 0 | 0 | 0 | 1014.4
| 32 | TAU-TBD48 | PRE-10051 | SPP TAU - Circuit 66436 | TAU-TBD48.1 | PRE-10051.1 | SPP TAU - Circuit 66436 | 2023-10-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 2155.6 | 26945 | 5389 | 0 | 0 | 0 | 34489.6
| 33 | TAU-TBD49 | PRE-10052 | SPP TAU - Circuit 66098 | TAU-TBD49.1 | PRE-10052.1 | SPP TAU - Circuit 66098 | 2023-10-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388.14 | 20822.1 | 0 | 0 | 0 | 22210.24
| 34 | TAU-TBD50 | PRE-10053 | SPP TAU - Circuit 230020 | TAU-TBD50.1 | PRE-10053.1 | SPP TAU - Circuit 230020 | 2023-12-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2621.2 | 19659 | 19659 | 0 | 0 | 41939.2
| 35 | TAU-TBD51 | PRE-10054 | SPP TAU - Circuit 230623 | TAU-TBD51.1 | PRE-10054.1 | SPP TAU - Circuit 230623 | 2024-01-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2795 | 13975 | 27950 | 0 | 44720
| 36 | TAU-TBD52 | PRE-10055 | SPP TAU - Circuit 230604 | TAU-TBD52.1 | PRE-10055.1 | SPP TAU - Circuit 230604 | 2024-02-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1548 | 11610 | 11610 | 24768
| 37 | TAU-TBD53 | PRE-10056 | SPP TAU - Circuit 66035 | TAU-TBD53.1 | PRE-10056.1 | SPP TAU - Circuit 66035 | 2024-03-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4121 | 30907.5 | 35028.5
C | Substation Extreme Weather Protection | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | Distribution Overhead Feeder Hardening | [8 empty] | 327573.5275 | 254486 | 2201678.625 | 4415185.9537 | 2435512.165 | 2567917.38 | 3285690.935 | 2384825.665 | 2989138.81 | 7971249.305 | 2539399.025 | 1970000 | 33342657.3912
| 1 | FH - TBD18 | PRE-09848 | SPP FH - Yukon 13101 | FH - TBD18.1 | PRE-09848.1 | SPP FH - Yukon 13101 | 3/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 2 | FH - TBD19 | PRE-09849 | SPP FH - McFarland 13104 | FH - TBD19.1 | PRE-09849.1 | SPP FH - McFarland 13104 | 3/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 3 | FH - TBD20 | PRE-09850 | SPP FH - Manhattan 13111 | FH - TBD20.1 | PRE-09850.1 | SPP FH - Manhattan 13111 | 3/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 4 | FH - TBD21 | PRE-09851 | SPP FH - East Winter Haven 13309 | FH - TBD21.1 | PRE-09851.1 | SPP FH - East Winter Haven 13309 | 5/15/22 | Distribution Line - Acct 364 | 62734 | 62734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 125468
| 5 | FH - TBD22 | FH - TBD22 | SPP FH - 13313 | FH - TBD22.1 | FH - TBD22.1 | SPP FH - East Winter Haven 13313 | 5/15/22 | Distribution Line - Acct 364 | 36518 | 36518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 73036
| 6 | FH - TBD23 | FH - TBD23 | SPP FH - 13314 | FH - TBD23.1 | FH - TBD23.1 | SPP FH - East Winter Haven 13314 | 5/15/22 | Distribution Line - Acct 364 | 14834 | 14834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 29668
| 7 | FH - TBD24 | FH - TBD24 | SPP FH - 13339 | FH - TBD24.1 | FH - TBD24.1 | SPP FH - Waters 13339 | 3/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 8 | FH - TBD25 | FH - TBD25 | SPP FH - 13433 | FH - TBD25.1 | FH - TBD25.1 | SPP FH - 12th Ave 13433 | 7/15/22 | Distribution Line - Acct 364 | 213200 | 140400 | 172400 | 162400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 688400
| 9 | FH - TBD26 | FH - TBD26 | SPP FH - 13808 | FH - TBD26.1 | FH - TBD26.1 | SPP FH - Knights Ave. 13808 | 3/15/22 | Distribution Line - Acct 364 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 10 | FH - TBD27 | FH - TBD27 | SPP FH - 13964 | FH - TBD27.1 | FH - TBD27.1 | SPP FH - Orient 13964 | 3/15/22 | Distribution Line - Acct 364 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 11 | FH - TBD9 | FH - TBD9 | SPP FH - 13148 | FH - TBD9.1 | FH - TBD9.1 | SPP FH - Hopewell 13148 | 7/15/22 | Distribution Line - Acct 364 |  |  | 491018.75 | 728073.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1219092.66
| 12 | FH - TBD10 | FH - TBD10 | SPP FH - 13048 | FH - TBD10.1 | FH - TBD10.1 | SPP FH -Fourteenth Street 13048 | 10/15/22 | Distribution Line - Acct 364 |  |  | 710859.875 | 146093.75 | 365234.375 | 438281.25 | 417187.66 | 0 | 0 | 0 | 0 | 0 | 2077656.91
| 13 | FH - TBD11 | FH - TBD11 | SPP FH - 13094 | FH - TBD11.1 | FH - TBD11.1 | SPP FH - Plymouth 13094 - OH Feeder | 12/15/22 | Distribution Line - Acct 364 |  |  |  | 706264.6775 | 144463.355 | 144463.355 | 293926.71 | 433390.065 | 211695.0325 | 0 | 0 | 0 | 1934203.195
| 13 | FH - TBD11 | FH - TBD11 | SPP FH - 13094 | FH - TBD11.2 | FH - TBD11.2 | SPP FH - Plymouth 13094 - S&E/R&C | 1/15/23 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 905000 | 905000 | 905000 | 905000 | 0 | 0 | 3620000
| 14 | FH - TBD12 | FH - TBD12 | SPP FH - 13770 | FH - TBD12.1 | FH - TBD12.1 | SPP FH - Lake Juliana 13770 - OH Feeder | 12/15/22 | Distribution Line - Acct 364 |  |  |  | 605221.0587 | 587442.96 | 202380.385 | 389760.77 | 389760.77 | 483450.9625 | 0 | 0 | 0 | 2658016.9062
| 14 | FH - TBD12 | FH - TBD12 | SPP FH - 13770 | FH - TBD12.2 | FH - TBD12.2 | SPP FH - Lake Juliana 13770 - S&E/R&C | 3/15/23 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810000 | 810000 | 810000 | 810000 | 3240000
| 15 | FH - TBD13 | FH - TBD13 | SPP FH - 13118 | FH - TBD13.1 | FH - TBD13.1 | SPP FH - Lake Alfred 13118 -OH Feeder | 9/15/22 | Distribution Line - Acct 364 | 0 | 0 | 827400 | 269400 | 330500 | 330500 | 0 | 0 | 0 | 0 | 0 | 0 | 1757800
| 15 | FH - TBD13 | FH - TBD13 | SPP FH - 13118 | FH - TBD13.2 | FH - TBD13.2 | SPP FH - Lake Alfred 13118 - S&E/R&C | 3/15/23 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 540000 | 540000 | 1620000
| 16 | FH - TBD14 | FH - TBD14 | SPP FH - 13296 | FH - TBD14.1 | FH - TBD14.1 | SPP FH - Jan Phyl 13296 - OH Feeder | 10/15/22 | Distribution Line - Acct 364 | 0 | 0 |  | 1432280.16 | 451346.71 | 555433.3875 | 555433.3875 | 0 | 0 | 0 | 0 | 0 | 2994493.645
| 16 | FH - TBD14 | FH - TBD14 | SPP FH - 13296 | FH - TBD14.2 | FH - TBD14.2 | SPP FH - Jan Phyl 13296 - S&E/R&C | 3/15/23 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 1500000
| 17 | FH - TBD15 | FH - TBD15 | SPP FH - 13989 | FH - TBD15.1 | FH - TBD15.1 | SPP FH - Trout Creek 13989 | 10/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 319502.305 | 67873.855 | 222558.4925 | 222558.4925 |  | 0 | 0 | 0 | 0 | 832493.145
| 18 | FH - TBD16 | FH - TBD16 | SPP FH - 13984 | FH - TBD16.1 | FH - TBD16.1 | SPP FH - Coronet 13984 | 12/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 475126.555 | 132198.4075 | 172931.21 | 218664.0125 | 172931.21 | 0 | 0 | 0 | 1171851.395
| 19 | FH - TBD17 | FH - TBD17 | SPP FH - 14123 | FH - TBD17.1 | FH - TBD17.1 | SPP FH - Fishhawk 14123 | 12/15/22 | Distribution Line - Acct 364 |  | 0 | 0 | 41947.1975 | 0 | 532580.6425 | 224735.9875 | 271683.185 | 177788.79 | 0 | 0 | 0 | 1248735.8025
| 20 | FH - TBD28 | FH - TBD28 | SPP FH - 14094 | FH - TBD28.1 | FH - TBD28.1 | SPP FH - Pebble Creek 14094 | 1/15/23 | Distribution Line - Acct 364 | 287.5275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3096 | 5175.495 | 0 | 0 | 8559.0225
| 21 | FH - TBD29 | FH - TBD29 | SPP FH - 13651 | FH - TBD29.1 | FH - TBD29.1 | SPP FH - Rhodine 13651 | 2/15/23 | Distribution Line - Acct 364 |  |  | 0 | 1537.6075 | 1537.6075 | 0 | 12096.4575 | 12763.2525 | 12763.2525 | 9688.0375 | 0 | 0 | 50386.215
| 22 | FH - TBD30 | FH - TBD30 | SPP FH - 13346 | FH - TBD30.1 | FH - TBD30.1 | SPP FH - East Bay 13346 | 2/15/23 | Distribution Line - Acct 364 |  |  | 0 | 2465.2875 | 2465.2875 | 0 | 0 | 0 | 39806.2625 | 19257.0125 | 16791.725 | 0 | 80785.575
| 23 | FH - TBD31 | FH - TBD31 | SPP FH - 13312 | FH - TBD31.1 | FH - TBD31.1 | SPP FH - East Winter Haven13312 | 2/15/23 | Distribution Line - Acct 364 | 0 |  |  | 0 | 9521.46 | 9521.46 | 92060.26 | 33564.38 | 52607.3 | 62128.76 | 52607.3 | 0 | 312010.92
| 24 | FH - TBD32 | FH - TBD32 | SPP FH - 13008 | FH - TBD32.1 | FH - TBD32.1 | SPP FH - 13008 | 9/15/23 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 25 | FH - TBD33 | FH - TBD33 | SPP FH - 13028 | FH - TBD33.1 | FH - TBD33.1 | SPP FH - 13028 | 9/15/23 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 26 | FH - TBD34 | FH - TBD34 | SPP FH - 13039 | FH - TBD34.1 | FH - TBD34.1 | SPP FH - 13039 | 12/15/23 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 27 | FH - TBD35 | FH - TBD35 | SPP FH - 13077 | FH - TBD35.1 | FH - TBD35.1 | SPP FH - 13077 | 12/15/23 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 28 | FH - TBD36 | FH - TBD36 | SPP FH - 13187 | FH - TBD36.1 | FH - TBD36.1 | SPP FH - 13187 | 2/15/24 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 29 | FH - TBD37 | FH - TBD37 | SPP FH - 13227 | FH - TBD37.1 | FH - TBD37.1 | SPP FH - 13227 | 12/15/23 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 30 | FH - TBD38 | FH - TBD38 | SPP FH - 13230 | FH - TBD38.1 | FH - TBD38.1 | SPP FH - 13230 | 2/15/24 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 31 | FH - TBD39 | FH - TBD39 | SPP FH - 13292 | FH - TBD39.1 | FH - TBD39.1 | SPP FH - 13292 | 6/15/23 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 32 | FH - TBD40 | FH - TBD40 | SPP FH - 13299 | FH - TBD40.1 | FH - TBD40.1 | SPP FH - 13299 | 2/15/24 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 33 | FH - TBD41 | FH - TBD41 | SPP FH - 13308 | FH - TBD41.1 | FH - TBD41.1 | SPP FH - 13308 | 9/15/23 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 34 | FH - TBD42 | FH - TBD42 | SPP FH - 13687 | FH - TBD42.1 | FH - TBD42.1 | SPP FH - 13687 | 12/15/23 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 35 | FH - TBD43 | FH - TBD43 | SPP FH - 13040 | FH - TBD43.1 | FH - TBD43.1 | SPP FH - 13040 | 2/15/24 | Distribution Line - Acct 364 | [7 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 50000
| 36 | TBD | TBD | RIVA License Purchase | TBD | TBD | RIVA License Purchase | 10/15/22 | ? | [9 empty] | 5000000 |  |  | 5000000
| 37 | TBD | TBD | FLISR Server Installation | TBD | TBD | FLISR Server Installation | 5/15/23 | ? | [10 empty] | 500000 |  | 500000
E | Transmission Access Enhancements | [8 empty] | 316758.9 | 313258.9 | 119123.45 | 116347.5833 | 222647.2653 | 222647.2653 | 257864.26 | 280864.26 | 183231.2447 | 245002.9113 | 70438.3333 | 61771.6667 | 2409956.04
| 1 | TXE - TBD1 | PRE-09813 | SPP TXE - 230008 | TXE - TBD1.1 | PRE-09813.1 | SPP TXE - 230008 | 1/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46438.3333 | 46438.3333 | 46438.3333 | 139315
| 2 | TXE - TBD2 | PRE-09814 | SPP TXE - 230623 | TXE - TBD2.1 | PRE-09814.1 | SPP TXE - 230623 | 11/15/2027 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | TXE - TBD3 | PRE-09815 | SPP TXE - P - Bridge | TXE - TBD3.1 | PRE-09815.1 | SPP TXE - P - Bridge | 12/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | TXE - TBD4 | PRE-09816 | SPP TXE - Hampton Sub - Bridge | TXE - TBD4.1 | PRE-09816.1 | SPP TXE - Hampton Sub - Bridge | 11/15/2022 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 151564.578 | 151564.578 | 151564.578 | 151564.578 | 0 | 0 | 606258.312
| 5 | TXE - TBD5 | PRE-09817 | SPP TXE - 230033 | TXE - TBD5.1 | PRE-09817.1 | SPP TXE - 230033 | 5/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | TXE - TBD6 | PRE-09818 | SPP TXE - Morris Bridge - Bridge | TXE - TBD6.1 | PRE-09818.1 | SPP TXE - Morris Bridge - Bridge | 9/15/2022 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 106299.682 | 106299.682 | 106299.682 | 106299.682 | 0 | 0 | 0 | 0 | 425198.728
| 7 | TXE - TBD7 | PRE-09819 | SPP TXE - 66007 | TXE - TBD7.1 | PRE-09819.1 | SPP TXE - 66007 | 11/15/2023 | Transmission Line - Acct 359 | 12364.5 | 8864.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21229
| 8 | TXE - TBD8 | PRE-09820 | SPP TXE - 230037 | TXE - TBD8.1 | PRE-09820.1 | SPP TXE - 230037 | 8/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | TXE - TBD9 | PRE-09821 | SPP TXE - 66839 | TXE - TBD9.1 | PRE-09821.1 | SPP TXE - 66839 | 11/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8666.6667 | 8666.6667 | 8666.6667 | 26000
| 10 | TXE - TBD10 | PRE-09822 | SPP TXE - 230606 | TXE - TBD10.1 | PRE-09822.1 | SPP TXE - 230606 | 11/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 20000
| 11 | TXE - TBD11 | PRE-09836 | SPP TXE - Columbus Dr #2 - Bridge | TXE - TBD11.1 | PRE-09836.1 | SPP TXE - Columbus Dr #2 - Bridge | 12/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7333.3333 | 7333.3333 | 7333.3333 | 0 | 0 | 22000
| 12 | TXE - TBD12 | PRE-09837 | SPP TXE - W. of Forbes Rd - Bridge | TXE - TBD12.1 | PRE-09837.1 | SPP TXE - W. of Forbes Rd - Bridge | 6/15/2024 | Transmission Line - Acct 359 | 30809.7333 | 30809.7333 | 30809.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92429.2
| 13 | TXE - TBD13 | PRE-09838 | SPP TXE - Columbus Dr #1 - Bridge | TXE - TBD13.1 | PRE-09838.1 | SPP TXE - Columbus Dr #1 - Bridge | 12/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000 | 0 | 0 | 27000
| 14 | TXE - TBD14 | PRE-09839 | SPP TXE - Tampa Palms #1 - Bridge | TXE - TBD14.1 | PRE-09839.1 | SPP TXE - Tampa Palms #1 - Bridge | 4/15/2023 | Transmission Line - Acct 359 | 47377.3 | 47377.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94754.6
| 15 | TXE - TBD16 | PRE-09841 | SPP TXE - E.Sydney Washer Rd-Bridge | TXE - TBD16.1 | PRE-09841.1 | SPP TXE - E.Sydney Washer Rd-Bridge | 6/15/2024 | Transmission Line - Acct 359 | 33508.4667 | 33508.4667 | 33508.4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100525.4
| 16 | TXE - TBD17 | PRE-09842 | SPP TXE - Tampa Palms #3 - Bridge | TXE - TBD17.1 | PRE-09842.1 | SPP TXE - Tampa Palms #3 - Bridge | 7/15/2023 | Transmission Line - Acct 359 | 51425.4 | 51425.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102850.8
| 17 | TXE - TBD20 | PRE-09872 | SPP TXE - 230020 - 4 road locations | TXE - TBD20.1 | PRE-09872.1 | SPP TXE - 230020 - 4 road locations | 12/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 54805.25 | 54805.25 | 54805.25 | 54805.25 | 0 | 0 | 0 | 0 | 0 | 0 | 219221
| 18 | TXE - TBD21 | PRE-09873 | SPP TXE - Tampa Palms #2 - Bridge | TXE - TBD21.1 | PRE-09873.1 | SPP TXE - Tampa Palms #2 - Bridge | 6/15/2023 | Transmission Line - Acct 359 | 53449.7 | 53449.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106899.4
| 19 | TXE - TBD24 | PRE-09876 | SPP TXE - 66016 | TXE - TBD24.1 | PRE-09876.1 | SPP TXE - 66016 | 12/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 20000
| 20 | TXE - TBD25 | PRE-09877 | SPP TXE - Tampa Palms #4 - Bridge | TXE - TBD25.1 | PRE-09877.1 | SPP TXE - Tampa Palms #4 - Bridge | 9/15/2023 | Transmission Line - Acct 359 | 54124.3 | 54124.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108248.6
| 21 | TXE - TBD26 | PRE-09878 | SPP TXE - 66035 - 2 road locations | TXE - TBD26.1 | PRE-09878.1 | SPP TXE - 66035 - 2 road locations | 12/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8666.6667 | 8666.6667 | 8666.6667 | 0 | 26000
| 22 | TXE - TBD30 | PRE-09881 | SPP TXE - 230007 | TXE - TBD30.1 | PRE-09881.1 | SPP TXE - 230007 | 10/15/2023 | Transmission Line - Acct 359 | 33699.5 | 33699.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67399
| 23 | TXE - TBD32 | TXE - TBD32 | SPP TXE - 66033 | TXE - TBD32.1 | TXE - TBD32.1 | SPP TXE - 66033 | 1/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 15024 | 15024 | 15024 | 0 | 0 | 0 | 0 | 0 | 0 | 45072
| 24 | TXE - TBD34 | TXE - TBD34 | SPP TXE - 66046 | TXE - TBD34.1 | TXE - TBD34.1 | SPP TXE - 66046 | 1/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 30304.6667 | 30304.6667 | 30304.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 90914
| 25 | TXE - TBD36 | TXE - TBD36 | SPP TXE - 66001 - 3 road locations | TXE - TBD36.1 | TXE - TBD36.1 | SPP TXE - 66001 - 3 road locations | 1/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 16213.6667 | 16213.6667 | 16213.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 48641
|  |  |  | Total of Capital Programs | [5 empty] | 2059156.9275 | 1663002.4 | 3817314.619 | 6084221.2771 | 3247259.7103 | 4235670.5453 | 4969493.09 | 3978269.765 | 4597585.1547 | 9927304.2163 | 4160288.3583 | 3492045.1667 | 52231611.2302

## 2023
Tampa Electric Company
Storm Protection Plan
Projected Period Amount
Projected Period: January through December 2023
Capital Expenditures
(in Dollars)
Additions Only
End of
|  | Placeholder | Actual |  | Placeholder | Actual |  | PMO Est. |  | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Period
Line | Program | FP | FP | FP Description | PMO | PMO | PMO Description | In-Service Date | Depr Grp | January | February | March | April | May | June | July | August | September | October | November | December | Total
B | Transmission Asset Upgrades | [8 empty] | 1392937.3 | 1591413.4 | 1293302.6 | 1656018.6 | 1588061.4 | 1533177.9 | 1445318.4 | 1251344.4 | 1498077.6 | 1591531.2 | 1694428.4 | 928176 | 17463787.2
| 1 | TAU-TBD42 | PRE-10045 | SPP TAU - Circuit 66021 | TAU-TBD42.1 | PRE-10045.1 | SPP TAU - Circuit 66021 | 2023-05-15 | Transmission Line - Acct 355 | 1283850 | 99855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1383705
| 2 | TAU-TBD43 | PRE-10046 | SPP TAU - Circuit 66028 | TAU-TBD43.1 | PRE-10046.1 | SPP TAU - Circuit 66028 | 2023-06-15 | Transmission Line - Acct 355 | 76943.5 | 1384983 | 30777.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1492703.9
| 3 | TAU-TBD44 | PRE-10047 | SPP TAU - Circuit 66032 | TAU-TBD44.1 | PRE-10047.1 | SPP TAU - Circuit 66032 | 2023-07-15 | Transmission Line - Acct 355 | 0 | 63400 | 1141200 | 25360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1229960
| 4 | TAU-TBD45 | PRE-10048 | SPP TAU - Circuit 66017 | TAU-TBD45.1 | PRE-10048.1 | SPP TAU - Circuit 66017 | 2023-09-15 | Transmission Line - Acct 355 | 0 | 0 | 61031.8 | 1525795 | 1159604.2 | 61031.8 | 0 | 0 | 0 | 0 | 0 | 0 | 2807462.8
| 5 | TAU-TBD46 | PRE-10049 | SPP TAU - Circuit 66011 | TAU-TBD46.1 | PRE-10049.1 | SPP TAU - Circuit 66011 | 2023-09-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 34870 | 313830 | 313830 | 13948 | 0 | 0 | 0 | 0 | 0 | 676478
| 6 | TAU-TBD47 | PRE-10050 | SPP TAU - Circuit 66047 | TAU-TBD47.1 | PRE-10050.1 | SPP TAU - Circuit 66047 | 2023-09-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 1585 | 28530 | 634 | 0 | 0 | 0 | 0 | 0 | 30749
| 7 | TAU-TBD48 | PRE-10051 | SPP TAU - Circuit 66436 | TAU-TBD48.1 | PRE-10051.1 | SPP TAU - Circuit 66436 | 2023-10-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 53890 | 970020 | 21556 | 0 | 0 | 0 | 0 | 0 | 1045466
| 8 | TAU-TBD49 | PRE-10052 | SPP TAU - Circuit 66098 | TAU-TBD49.1 | PRE-10052.1 | SPP TAU - Circuit 66098 | 2023-10-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 34703.5 | 624663 | 13881.4 | 0 | 0 | 0 | 0 | 673247.9
| 9 | TAU-TBD50 | PRE-10053 | SPP TAU - Circuit 230020 | TAU-TBD50.1 | PRE-10053.1 | SPP TAU - Circuit 230020 | 2023-12-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 65530 | 655300 | 524240 | 26212 | 0 | 0 | 0 | 1271282
| 10 | TAU-TBD51 | PRE-10054 | SPP TAU - Circuit 230623 | TAU-TBD51.1 | PRE-10054.1 | SPP TAU - Circuit 230623 | 2024-01-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 69875 | 628875 | 628875 | 27950 | 0 | 0 | 1355575
| 11 | TAU-TBD52 | PRE-10055 | SPP TAU - Circuit 230604 | TAU-TBD52.1 | PRE-10055.1 | SPP TAU - Circuit 230604 | 2024-02-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38700 | 696600 | 15480 | 0 | 0 | 750780
| 12 | TAU-TBD53 | PRE-10056 | SPP TAU - Circuit 66035 | TAU-TBD53.1 | PRE-10056.1 | SPP TAU - Circuit 66035 | 2024-03-15 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103025 | 1442350 | 412100 | 61815 | 2019290
| 13 | TAU-TBD54 | TAU-TBD54 | SPP TAU - Circuit 66067 | TAU-TBD54.1 | TAU-TBD54.1 | SPP TAU - Circuit 66067 | 3/15/2024 | Transmission Line - Acct 355 | 25867.2 | 12933.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64668 | 1164024 | 25867.2 | 1293360
| 14 | TAU-TBD55 | TAU-TBD55 | SPP TAU - Circuit 66042 | TAU-TBD55.1 | TAU-TBD55.1 | SPP TAU - Circuit 66042 | 4/15/2024 | Transmission Line - Acct 355 | 6276.6 | 18829.8 | 12553.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62766 | 753192 | 853617.6
| 15 | TAU-TBD56 | TAU-TBD56 | SPP TAU - Circuit 66652 | TAU-TBD56.1 | TAU-TBD56.1 | SPP TAU - Circuit 66652 | 5/15/2024 | Transmission Line - Acct 355 | 0 | 11412 | 34236 | 22824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68472
| 16 | TAU-TBD57 | TAU-TBD57 | SPP TAU - Circuit 66034 | TAU-TBD57.1 | TAU-TBD57.1 | SPP TAU - Circuit 66034 | 6/15/2024 | Transmission Line - Acct 355 | 0 | 0 | 13504.2 | 40512.6 | 27008.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81025.2
| 17 | TAU-TBD58 | TAU-TBD58 | SPP TAU - Circuit 66838 | TAU-TBD58.1 | TAU-TBD58.1 | SPP TAU - Circuit 66838 | 7/15/2024 | Transmission Line - Acct 355 | 0 | 0 | 0 | 6657 | 19971 | 13314 | 0 | 0 | 0 | 0 | 0 | 0 | 39942
| 18 | TAU-TBD59 | TAU-TBD59 | SPP TAU - Circuit 66040 | TAU-TBD59.1 | TAU-TBD59.1 | SPP TAU - Circuit 66040 | 8/15/2024 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 12172.8 | 36518.4 | 24345.6 | 0 | 0 | 0 | 0 | 0 | 73036.8
| 19 | TAU-TBD60 | TAU-TBD60 | SPP TAU - Circuit 66656 | TAU-TBD60.1 | TAU-TBD60.1 | SPP TAU - Circuit 66656 | 9/15/2024 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 9700.2 | 29100.6 | 19400.4 | 0 | 0 | 0 | 0 | 58201.2
| 20 | TAU-TBD61 | TAU-TBD61 | SPP TAU - Circuit 66412 | TAU-TBD61.1 | TAU-TBD61.1 | SPP TAU - Circuit 66412 | 10/15/2024 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 5896.2 | 17688.6 | 11792.4 | 0 | 0 | 0 | 35377.2
| 21 | TAU-TBD62 | TAU-TBD62 | SPP TAU - Circuit 66830 | TAU-TBD62.1 | TAU-TBD62.1 | SPP TAU - Circuit 66830 | 1/15/2025 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2662.8 | 7988.4 | 5325.6 | 0 | 0 | 15976.8
| 22 | TAU-TBD63 | TAU-TBD63 | SPP TAU - Circuit 66650 | TAU-TBD63.1 | TAU-TBD63.1 | SPP TAU - Circuit 66650 | 1/15/2025 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5896.2 | 17688.6 | 11792.4 | 0 | 0 | 35377.2
| 23 | TAU-TBD64 | TAU-TBD64 | SPP TAU - Circuit 66657 | TAU-TBD64.1 | TAU-TBD64.1 | SPP TAU - Circuit 66657 | 3/15/2025 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5896.2 | 17688.6 | 11792.4 | 0 | 35377.2
| 24 | TAU-TBD65 | TAU-TBD65 | SPP TAU - Circuit 66043 | TAU-TBD65.1 | TAU-TBD65.1 | SPP TAU - Circuit 66043 | 4/15/2025 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6276.6 | 18829.8 | 12553.2 | 37659.6
| 25 | TAU-TBD66 | TAU-TBD66 | SPP TAU - Circuit 66837 | TAU-TBD66.1 | TAU-TBD66.1 | SPP TAU - Circuit 66837 | 4/15/2025 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3043.2 | 9129.6 | 12172.8
| 26 | TAU-TBD67 | TAU-TBD67 | SPP TAU - Circuit 66603 | TAU-TBD67.1 | TAU-TBD67.1 | SPP TAU - Circuit 66603 | 5/15/2025 | Transmission Line - Acct 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21873 | 65619 | 87492
C | Substation Extreme Weather Protection | [8 empty] | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 300000 | 0 | 700000
| 1 | SEW-TBD1 | SEW-TBD1 | SPP SEW - MacDill AFB | SEW-TBD1.1 | SEW-TBD1.1 | SPP SEW - MacDill AFB | 2024-01-15 |  | 50000 | 50000 | [7 empty] | 300000 | 300000 |  | 700000
D | Distribution Overhead Feeder Hardening | [8 empty] | 1430000 | 2340000 | 2480000 | 2900000 | 2900000 | 2823479 | 2578792 | 2832333 | 2772190 | 2732832 | 2645097 | 1430460 | 29865183
| 1 | FH - TBD32 | FH - TBD32 | SPP FH - 13008 | FH - TBD32.1 | FH - TBD32.1 | SPP FH - 13008 | 9/15/23 | Distribution Line - Acct 364 | 30000 | 200000 | 200000 | 300000 | 200000 | 95084 | [6 empty] | 1025084
| 2 | FH - TBD33 | FH - TBD33 | SPP FH - 13028 | FH - TBD33.1 | FH - TBD33.1 | SPP FH - 13028 | 9/15/23 | Distribution Line - Acct 364 | 20000 | 180000 | 250000 | 250000 | 250000 | 28395 | [6 empty] | 978395
| 3 | FH - TBD34 | FH - TBD34 | SPP FH - 13039 | FH - TBD34.1 | FH - TBD34.1 | SPP FH - 13039 | 12/15/23 | Distribution Line - Acct 364 | 20000 | 80000 | 100000 | 150000 | 200000 | 200000 | 200000 | 36716 |  |  |  |  | 986716
| 4 | FH - TBD35 | FH - TBD35 | SPP FH - 13077 | FH - TBD35.1 | FH - TBD35.1 | SPP FH - 13077 | 12/15/23 | Distribution Line - Acct 364 | 25000 | 100000 | 100000 | 100000 | 100000 | 200000 | 200000 | 200000 | 80582 |  |  |  | 1105582
| 5 | FH - TBD36 | FH - TBD36 | SPP FH - 13187 | FH - TBD36.1 | FH - TBD36.1 | SPP FH - 13187 | 2/15/24 | Distribution Line - Acct 364 | 30000 | 100000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 200000 | 300000 | 300000 | 1715 | 1831715
| 6 | FH - TBD37 | FH - TBD37 | SPP FH - 13227 | FH - TBD37.1 | FH - TBD37.1 | SPP FH - 13227 | 12/15/23 | Distribution Line - Acct 364 | 25000 | 30000 | 100000 | 100000 | 200000 | 200000 | 300000 | 45617 |  |  |  |  | 1000617
| 7 | FH - TBD38 | FH - TBD38 | SPP FH - 13230 | FH - TBD38.1 | FH - TBD38.1 | SPP FH - 13230 | 2/15/24 | Distribution Line - Acct 364 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 100000 | 350000 | 250000 | 200000 | 134546 |  | 1484546
| 8 | FH - TBD39 | FH - TBD39 | SPP FH - 13292 | FH - TBD39.1 | FH - TBD39.1 | SPP FH - 13292 | 6/15/23 | Distribution Line - Acct 364 | 90000 | 30000 | [10 empty] | 120000
| 9 | FH - TBD40 | FH - TBD40 | SPP FH - 13299 | FH - TBD40.1 | FH - TBD40.1 | SPP FH - 13299 | 2/15/24 | Distribution Line - Acct 364 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 300000 | 350000 | 250000 | 80000 | 33199 |  | 2213199
| 10 | FH - TBD41 | FH - TBD41 | SPP FH - 13308 | FH - TBD41.1 | FH - TBD41.1 | SPP FH - 13308 | 9/15/23 | Distribution Line - Acct 364 | 200000 | 200000 | 200000 | 200000 | 200000 | 250000 | 53706 | [5 empty] | 1303706
| 11 | FH - TBD42 | FH - TBD42 | SPP FH - 13311 | FH - TBD42.1 | FH - TBD42.1 | SPP FH - 13311 | 2/15/24 | Distribution Line - Acct 364 | 20000 | 20000 | 10000 |  |  |  | 50000 | 200000 | 200000 | 200000 | 300000 | 150070 | 1150070
| 12 | FH - TBD43 | FH - TBD43 | SPP FH - 13343 | FH - TBD43.1 | FH - TBD43.1 | SPP FH - 13343 | 2/15/24 | Distribution Line - Acct 364 | [11 empty] | 49314 | 49314
| 13 | FH - TBD44 | FH - TBD44 | SPP FH - 13364 | FH - TBD44.1 | FH - TBD44.1 | SPP FH - 13364 | 2/15/24 | Distribution Line - Acct 364 | [11 empty] | 53082 | 53082
| 14 | FH - TBD45 | FH - TBD45 | SPP FH - 13414 | FH - TBD45.1 | FH - TBD45.1 | SPP FH - 13414 | 2/15/24 | Distribution Line - Acct 364 | 50000 | 20000 | [5 empty] | 50000 | 150000 | 250000 | 300000 | 148360 | 968360
| 15 | FH - TBD46 | FH - TBD46 | SPP FH - 13417 | FH - TBD46.1 | FH - TBD46.1 | SPP FH - 13417 | 2/15/24 | Distribution Line - Acct 364 | 50000 | [5 empty] | 50000 | 200000 | 200000 | 250000 | 300000 | 142739 | 1192739
| 16 | FH - TBD47 | FH - TBD47 | SPP FH - 13438 | FH - TBD47.1 | FH - TBD47.1 | SPP FH - 13438 | 2/15/24 | Distribution Line - Acct 364 | [11 empty] | 45745 | 45745
| 17 | FH - TBD48 | FH - TBD48 | SPP FH - 13457 | FH - TBD48.1 | FH - TBD48.1 | SPP FH - 13457 | 9/15/23 | Distribution Line - Acct 364 | 50000 | 200000 | 200000 | 200000 | 150000 | 100000 | 61008 | [5 empty] | 961008
| 18 | FH - TBD49 | FH - TBD49 | SPP FH - 13633 | FH - TBD49.1 | FH - TBD49.1 | SPP FH - 13633 | 2/15/24 | Distribution Line - Acct 364 | 50000 | [5 empty] | 100000 | 200000 | 200000 | 300000 | 350000 | 167614 | 1367614
| 19 | FH - TBD50 | FH - TBD50 | SPP FH - 13687 | FH - TBD50.1 | FH - TBD50.1 | SPP FH - 13687 | 12/15/23 | Distribution Line - Acct 364 | 200000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 268365 |  |  |  | 2218365
| 20 | FH - TBD51 | FH - TBD51 | SPP FH - 13695 | FH - TBD51.1 | FH - TBD51.1 | SPP FH - 13695 | 2/15/24 | Distribution Line - Acct 364 | 30000 | 20000 | [5 empty] | 50000 | 60000 | 350000 | 350000 | 157582 | 1017582
| 21 | FH - TBD52 | FH - TBD52 | SPP FH - 13737 | FH - TBD52.1 | FH - TBD52.1 | SPP FH - 13737 | 2/15/24 | Distribution Line - Acct 364 | 30000 | 20000 |  |  |  |  | 100000 | 100000 | 100000 | 200000 | 200000 | 210134 | 960134
| 22 | FH - TBD53 | FH - TBD53 | SPP FH - 13753 | FH - TBD53.1 | FH - TBD53.1 | SPP FH - 13753 | 9/15/23 | Distribution Line - Acct 364 | 30000 | 20000 | 250000 | 300000 | 300000 | 300000 | 14078 | [5 empty] | 1214078
| 23 | FH - TBD54 | FH - TBD54 | SPP FH - 13772 | FH - TBD54.1 | FH - TBD54.1 | SPP FH - 13772 | 2/15/24 | Distribution Line - Acct 364 | [10 empty] | 30000 | 90000 | 120000
| 24 | FH - TBD55 | FH - TBD55 | SPP FH - 13807 | FH - TBD55.1 | FH - TBD55.1 | SPP FH - 13807 | 2/15/24 | Distribution Line - Acct 364 | 50000 | 50000 | 100000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 100000 | 47352 |  | 1547352
| 25 | FH - TBD56 | FH - TBD56 | SPP FH - 13892 | FH - TBD56.1 | FH - TBD56.1 | SPP FH - 13892 | 12/15/23 | Distribution Line - Acct 364 | 30000 | 120000 | 120000 | 150000 | 150000 | 150000 | 150000 | 150000 | 63243 |  |  |  | 1083243
| 26 | FH - TBD57 | FH - TBD57 | SPP FH - 13944 | FH - TBD57.1 | FH - TBD57.1 | SPP FH - 13944 | 2/15/24 | Distribution Line - Acct 364 | [11 empty] | 8847 | 8847
| 27 | FH - TBD58 | FH - TBD58 | SPP FH - 13014 | FH - TBD58.1 | FH - TBD58.1 | SPP FH - 13014 | 2/15/24 | Distribution Line - Acct 364 | [11 empty] | 79623 | 79623
| 28 | FH - TBD59 | FH - TBD59 | SPP FH - 13040 | FH - TBD59.1 | FH - TBD59.1 | SPP FH - 13040 | 2/15/24 | Distribution Line - Acct 364 | 150000 | 200000 | 200000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 202832 |  |  | 2252832
| 29 | FH - TBD60 | FH - TBD60 | SPP FH - 13042 | FH - TBD60.1 | FH - TBD60.1 | SPP FH - 13042 | 2/15/24 | Distribution Line - Acct 364 |  |  |  | 50000 | 50000 | 50000 | 50000 | 50000 | 300000 | 300000 | 300000 | 46012 | 1196012
| 30 | FH - TBD61 | FH - TBD61 | SPP FH - 13083 | FH - TBD61.1 | FH - TBD61.1 | SPP FH - 13083 | 2/15/24 | Distribution Line - Acct 364 | [11 empty] | 79623 | 79623
| 31 | TBD | TBD | FLISR Server Installation | TBD | TBD | FLISR Server Installation | 5/15/23 | ? |  | 250000 | [10 empty] | 250000
E | Transmission Access Enhancements | [8 empty] | 205557.76 | 342955.66 | 368667.3 | 509692.4 | 404939.3 | 267541.4 | 230028.7133 | 137524.9467 | 137524.9467 | 176685.3733 | 128164.04 | 128164.04 | 3037445.88
| 1 | TXE - TBD1 | PRE-09813 | SPP TXE - 230008 | TXE - TBD1.1 | PRE-09813.1 | SPP TXE - 230008 | 1/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | TXE - TBD2 | PRE-09814 | SPP TXE - 230623 | TXE - TBD2.1 | PRE-09814.1 | SPP TXE - 230623 | 11/15/2027 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | TXE - TBD3 | PRE-09815 | SPP TXE - P - Bridge | TXE - TBD3.1 | PRE-09815.1 | SPP TXE - P - Bridge | 12/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | TXE - TBD4 | PRE-09816 | SPP TXE - Hampton Sub - Bridge | TXE - TBD4.1 | PRE-09816.1 | SPP TXE - Hampton Sub - Bridge | 11/15/2022 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | TXE - TBD5 | PRE-09817 | SPP TXE - 230033 | TXE - TBD5.1 | PRE-09817.1 | SPP TXE - 230033 | 5/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | TXE - TBD6 | PRE-09818 | SPP TXE - Morris Bridge - Bridge | TXE - TBD6.1 | PRE-09818.1 | SPP TXE - Morris Bridge - Bridge | 9/15/2022 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | TXE - TBD7 | PRE-09819 | SPP TXE - 66007 | TXE - TBD7.1 | PRE-09819.1 | SPP TXE - 66007 | 11/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48521.3333 | 48521.3333 | 48521.3333 | 0 | 0 | 145564
| 8 | TXE - TBD8 | PRE-09820 | SPP TXE - 230037 | TXE - TBD8.1 | PRE-09820.1 | SPP TXE - 230037 | 8/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | TXE - TBD9 | PRE-09821 | SPP TXE - 66839 | TXE - TBD9.1 | PRE-09821.1 | SPP TXE - 66839 | 11/15/2025 | Transmission Line - Acct 359 | 15192.265 | 15192.265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30384.53
| 10 | TXE - TBD10 | PRE-09822 | SPP TXE - 230606 | TXE - TBD10.1 | PRE-09822.1 | SPP TXE - 230606 | 11/15/2025 | Transmission Line - Acct 359 | 6194.905 | 6194.905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12389.81
| 11 | TXE - TBD11 | PRE-09836 | SPP TXE - Columbus Dr #2 - Bridge | TXE - TBD11.1 | PRE-09836.1 | SPP TXE - Columbus Dr #2 - Bridge | 12/15/2025 | Transmission Line - Acct 359 | 29892.965 | 29892.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59785.93
| 12 | TXE - TBD12 | PRE-09837 | SPP TXE - W. of Forbes Rd - Bridge | TXE - TBD12.1 | PRE-09837.1 | SPP TXE - W. of Forbes Rd - Bridge | 6/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13 | TXE - TBD13 | PRE-09838 | SPP TXE - Columbus Dr #1 - Bridge | TXE - TBD13.1 | PRE-09838.1 | SPP TXE - Columbus Dr #1 - Bridge | 12/15/2025 | Transmission Line - Acct 359 | 29892.965 | 29892.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59785.93
| 14 | TXE - TBD14 | PRE-09839 | SPP TXE - Tampa Palms #1 - Bridge | TXE - TBD14.1 | PRE-09839.1 | SPP TXE - Tampa Palms #1 - Bridge | 4/15/2023 | Transmission Line - Acct 359 | 104753.1 | 104753.1 | 104753.1 | 104753.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419012.4
| 15 | TXE - TBD16 | PRE-09841 | SPP TXE - E.Sydney Washer Rd-Bridge | TXE - TBD16.1 | PRE-09841.1 | SPP TXE - E.Sydney Washer Rd-Bridge | 6/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16 | TXE - TBD17 | PRE-09842 | SPP TXE - Tampa Palms #3 - Bridge | TXE - TBD17.1 | PRE-09842.1 | SPP TXE - Tampa Palms #3 - Bridge | 7/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 126516.3 | 126516.3 | 126516.3 | 126516.3 | 0 | 0 | 0 | 0 | 0 | 0 | 506065.2
| 17 | TXE - TBD20 | PRE-09872 | SPP TXE - 230020 - 4 road locations | TXE - TBD20.1 | PRE-09872.1 | SPP TXE - 230020 - 4 road locations | 12/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 | TXE - TBD21 | PRE-09873 | SPP TXE - Tampa Palms #2 - Bridge | TXE - TBD21.1 | PRE-09873.1 | SPP TXE - Tampa Palms #2 - Bridge | 6/15/2023 | Transmission Line - Acct 359 | 0 | 137397.9 | 137397.9 | 137397.9 | 137397.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549591.6
| 19 | TXE - TBD24 | PRE-09876 | SPP TXE - 66016 | TXE - TBD24.1 | PRE-09876.1 | SPP TXE - 66016 | 12/15/2025 | Transmission Line - Acct 359 | 7581 | 7581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15162
| 20 | TXE - TBD25 | PRE-09877 | SPP TXE - Tampa Palms #4 - Bridge | TXE - TBD25.1 | PRE-09877.1 | SPP TXE - Tampa Palms #4 - Bridge | 9/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 0 | 141025.1 | 141025.1 | 141025.1 | 141025.1 | 0 | 0 | 0 | 0 | 0 | 564100.4
| 21 | TXE - TBD26 | PRE-09878 | SPP TXE - 66035 - 2 road locations | TXE - TBD26.1 | PRE-09878.1 | SPP TXE - 66035 - 2 road locations | 12/15/2025 | Transmission Line - Acct 359 | 12050.56 | 12050.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24101.12
| 22 | TXE - TBD30 | PRE-09881 | SPP TXE - 230007 | TXE - TBD30.1 | PRE-09881.1 | SPP TXE - 230007 | 10/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 89003.6133 | 89003.6133 | 89003.6133 | 0 | 0 | 0 | 267010.84
| 23 | TXE - TBD32 | TXE - TBD32 | SPP TXE - 66033 | TXE - TBD32.1 | TXE - TBD32.1 | SPP TXE - 66033 | 1/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60552.7867 | 60552.7867 | 60552.7867 | 181658.36
| 24 | TXE - TBD34 | TXE - TBD34 | SPP TXE - 66046 | TXE - TBD34.1 | TXE - TBD34.1 | SPP TXE - 66046 | 1/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 25 | TXE - TBD36 | TXE - TBD36 | SPP TXE - 66001 - 3 road locations | TXE - TBD36.1 | TXE - TBD36.1 | SPP TXE - 66001 - 3 road locations | 1/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67611.2533 | 67611.2533 | 67611.2533 | 202833.76
|  |  |  | Total of Capital Programs | [5 empty] | 3078495.06 | 4324369.06 | 4141969.9 | 5065711 | 4893000.7 | 4624198.3 | 4254139.1133 | 4221202.3467 | 4407792.5467 | 4801048.5733 | 4767689.44 | 2486800.04 | 51066416.08