## DPL-12 Trans Asset Appendix
Tampa Electric's Transmission Asset Upgrades - Year 2022 Details
Project ID | Circuit No. | Pole Count | Project Start Month | Construction |  | Project Cost in 2020
|  |  |  | Start Month | End Month
Transmission Upgrades-138/230 kV-230006 | 230006 | 101 | 2022-09-21 | 2022-11-21 | 2022-04-22 | 1500000
Transmission Upgrades-138/230 kV-230402 | 230402 | 14 | 2022-03-22 | 2022-08-22 | 2022-12-22 | 300100
Transmission Upgrades-69 kV-66048 | 66048 | 5 | 2022-12-20 | 2022-04-21 | 2022-04-22 | 50000
Transmission Upgrades-138/230 kV-230606 | 230606 | 28 | 2022-07-21 | 2022-10-21 | 2022-03-22 | 210000
Transmission Upgrades-138/230 kV-230012 | 230012 | 16 | 2022-07-21 | 2022-10-21 | 2022-03-22 | 50000
Transmission Upgrades-138/230 kV-230020 | 230020 | 61 | 2022-08-22 | 2022-01-23 | 2022-06-23 | 41939.2
Transmission Upgrades-69 kV-66022 | 66022 | 50 | 2022-12-20 | 2022-08-21 | 2022-08-22 | 672980
Transmission Upgrades-69 kV-66001 | 66001 | 70 | 2022-03-21 | 2022-10-21 | 2022-06-22 | 1877473
Transmission Upgrades-69 kV-66016 | 66016 | 40 | 2022-11-20 | 2022-06-21 | 2022-06-22 | 400000
Transmission Upgrades-69 kV-66032 | 66032 | 40 | 2022-02-22 | 2022-01-23 | 2022-08-23 | 40576
Transmission Upgrades-69 kV-66020 | 66020 | 10 | 2022-07-21 | 2022-03-22 | 2022-08-22 | 305900.245
Transmission Upgrades-69 kV-66035 | 66035 | 65 | 2022-08-22 | 2022-01-23 | 2022-08-23 | 35028.5
Transmission Upgrades-138/230 kV-230602 | 230602 | 112 | 2022-05-21 | 2022-08-21 | 2022-03-22 | 50000
Transmission Upgrades-69 kV-66008 | 66008 | 9 | 2022-10-21 | 2022-07-21 | 2022-12-21 | 281970
Transmission Upgrades-69 kV-66030 | 66030 | 50 | 2022-07-21 | 2022-04-22 | 2022-09-22 | 1498910
Transmission Upgrades-69 kV-66045 | 66045 | 52 | 2022-09-21 | 2022-05-22 | 2022-12-22 | 1708376
Transmission Upgrades-138/230 kV-230033 | 230033 | 14 | 2022-06-21 | 2022-03-22 | 2022-06-22 | 294699.519
Transmission Upgrades-69 kV-66025 | 66025 | 105 | 2022-03-21 | 2022-08-21 | 2022-08-22 | 2324840
Transmission Upgrades-138/230 kV-230623 | 230623 | 65 | 2022-10-22 | 2022-01-23 | 2022-07-23 | 44720
Transmission Upgrades-69 kV-66021 | 66021 | 45 | 2022-02-22 | 2022-06-22 | 2022-03-23 | 45648
Transmission Upgrades-69 kV-66017 | 66017 | 97 | 2022-02-22 | 2022-07-22 | 2022-06-23 | 234972.43
Transmission Upgrades-138/230 kV-230609 | 230609 | 5 | 2022-12-21 | 2022-12-21 | 2022-03-22 | 105250.025
Transmission Upgrades-69 kV-66033 | 66033 | 26 | 2022-11-20 | 2022-11-21 | 2022-05-22 | 50000
Transmission Upgrades-69 kV-66036 | 66036 | 31 | 2022-11-20 | 2022-06-21 | 2022-05-22 | 300000
Transmission Upgrades-69 kV-66027 | 66027 | 17 | 2022-07-21 | 2022-02-22 | 2022-06-22 | 550620
Transmission Upgrades-69 kV-66060 | 66060 | 6 | 2022-11-20 | 2022-07-21 | 2022-04-22 | 10000
Transmission Upgrades-138/230 kV-230604 | 230604 | 36 | 2022-10-22 | 2022-02-23 | 2022-07-23 | 24768
Transmission Upgrades-69 kV-66407 | 66407 | 29 | 2022-12-20 | 2022-05-21 | 2022-05-22 | 10000
Transmission Upgrades-138/230 kV-230013 | 230013 | 20 | 2022-07-21 | 2022-03-22 | 2022-06-22 | 421000
Transmission Upgrades-69 kV-66427 | 66427 | 7 | 2022-11-20 | 2022-06-21 | 2022-06-22 | 10000
Transmission Upgrades-69 kV-66026 | 66026 | 83 | 2022-10-21 | 2022-04-22 | 2022-10-22 | 2582952
Transmission Upgrades-69 kV-66098 | 66098 | 22 | 2022-09-22 | 2022-01-23 | 2022-06-23 | 22210.24
Transmission Upgrades-69 kV-66011 | 66011 | 24 | 2022-09-21 | 2022-05-22 | 2022-12-22 | 22316.8
Transmission Upgrades-69 kV-66028 | 66028 | 49 | 2022-09-22 | 2022-01-23 | 2022-06-23 | 49243.84
Transmission Upgrades-69 kV-66047 | 66047 | 1 | 2022-02-21 | 2022-04-22 | 2022-06-22 | 1014.4
Transmission Upgrades-69 kV-66415 | 66415 | 10 | 2022-12-20 | 2022-03-22 | 2022-08-22 | 317000
Transmission Upgrades-69 kV-66436 | 66436 | 36 | 2022-08-22 | 2022-02-23 | 2022-08-23 | 34489.6
The North American Electric Reliability Corporation ("NERC") defines the transmission system as lines operated at relatively high voltages varying from 69kV up to 765kV and capable of delivery large quantities of electricity. Tampa Electric's transmission system is made up of 69kV, 138kV and 230kV voltages and is designed to transmit power to the end-user 13.2kV distribution substations. As such, Tampa Electric does not attribute customer counts directly to individual transmission lines. It should be noted, that without Tampa Electric's transmission network in place, power could not be delivered to the distribution network which would result in automatic load loss.