## SPPCRC 2022 Projection Capital
Tampa Electric Company
Storm Protection Plan Cost Recovery Clause
Projected Period Amount
Projected Period: January through December 2022
Capital Expenditures
(in Dollars)
Additions Only
[22 empty] | End of |  | Original 2022
|  | Placeholder | Actual |  | Placeholder | Actual |  | PMO Est. |  | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Period |  | Program Est
Line | Program | FP | FP | FP Description | PMO | PMO | PMO Description | In-Service Date | Depr Grp | January | February | March | April | May | June | July | August | September | October | November | December | Total |  | Total | Variance
D | Distribution Overhead Feeder Hardening | [8 empty] | 327573.5275 | 254486 | 2201678.625 | 4415185.9538 | 2435512.165 | 2567917.38 | 3285690.935 | 2384825.665 | 2989138.81 | 7971249.305 | 2039399.025 | 1970000 | 32842657.3912 |  | 29581441.3912 | -3261216
| 1 | FH - TBD18 | PRE-09848 | SPP FH - Yukon 13101 | FH - TBD18.1 | PRE-09848.1 | SPP FH - Yukon 13101 | 3/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | in svc 03/15/22
| 2 | FH - TBD19 | PRE-09849 | SPP FH - McFarland 13104 | FH - TBD19.1 | PRE-09849.1 | SPP FH - McFarland 13104 | 3/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | in svc 3/15/22
| 3 | FH - TBD20 | PRE-09850 | SPP FH - Manhattan 13111 | FH - TBD20.1 | PRE-09850.1 | SPP FH - Manhattan 13111 | 3/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | in svc 03/15/22
| 4 | FH - TBD21 | PRE-09851 | SPP FH - East Winter Haven 13309 | FH - TBD21.1 | PRE-09851.1 | SPP FH - East Winter Haven 13309 | 5/15/22 | Distribution Line - Acct 364 | 62734 | 62734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 125468 | in svc 05/15/22
| 5 | FH - TBD22 | FH - TBD22 | SPP FH - 13313 | FH - TBD22.1 | FH - TBD22.1 | SPP FH - East Winter Haven 13313 | 5/15/22 | Distribution Line - Acct 364 | 36518 | 36518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 73036 | in svc 05/15/22
| 6 | FH - TBD23 | FH - TBD23 | SPP FH - 13314 | FH - TBD23.1 | FH - TBD23.1 | SPP FH - East Winter Haven 13314 | 5/15/22 | Distribution Line - Acct 364 | 14834 | 14834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 29668 | in svc 05/15/22
| 7 | FH - TBD24 | FH - TBD24 | SPP FH - 13339 | FH - TBD24.1 | FH - TBD24.1 | SPP FH - Waters 13339 | 3/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | in svc 03/15/22
| 8 | FH - TBD25 | FH - TBD25 | SPP FH - 13433 | FH - TBD25.1 | FH - TBD25.1 | SPP FH - 12th Ave 13433 | 7/15/22 | Distribution Line - Acct 364 | 213200 | 140400 | 172400 | 162400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 688400 | in svc 07/15/22
| 9 | FH - TBD26 | FH - TBD26 | SPP FH - 13808 | FH - TBD26.1 | FH - TBD26.1 | SPP FH - Knights Ave. 13808 | 3/15/22 | Distribution Line - Acct 364 | April: 0; May: 0; June: 0; July: 0; August: 0; September: 0; December: 0 | 0 | in svc 03/15/22
| 10 | FH - TBD27 | FH - TBD27 | SPP FH - 13964 | FH - TBD27.1 | FH - TBD27.1 | SPP FH - Orient 13964 | 3/15/22 | Distribution Line - Acct 364 | April: 0; May: 0; June: 0; July: 0; August: 0; September: 0; December: 0 | 0 | in svc 03/15/22
| 11 | FH - TBD9 | FH - TBD9 | SPP FH - 13148 | FH - TBD9.1 | FH - TBD9.1 | SPP FH - Hopewell 13148 | 7/15/22 | Distribution Line - Acct 364 |  |  | 491018.75 | 728073.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1219092.66 | in svc 07/15/22
| 12 | FH - TBD10 | FH - TBD10 | SPP FH - 13048 | FH - TBD10.1 | FH - TBD10.1 | SPP FH -Fourteenth Street 13048 | 10/15/22 | Distribution Line - Acct 364 |  |  | 710859.875 | 146093.75 | 365234.375 | 438281.25 | 417187.66 | 0 | 0 | 0 | 0 | 0 | 2077656.91 | in svc 010/15/22
| 13 | FH - TBD11 | FH - TBD11 | SPP FH - 13094 | FH - TBD11.1 | FH - TBD11.1 | SPP FH - Plymouth 13094 - OH Feeder | 12/15/22 | Distribution Line - Acct 364 |  |  |  | 706264.6775 | 144463.355 | 144463.355 | 293926.71 | 433390.065 | 211695.0325 | 0 | 0 | 0 | 1934203.195 | in svc 12/15/22
| 13 | FH - TBD11 | FH - TBD11 | SPP FH - 13094 | FH - TBD11.2 | FH - TBD11.2 | SPP FH - Plymouth 13094 - S&E/R&C | 1/15/23 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 905000 | 905000 | 905000 | 905000 | 0 | 0 | 3620000 | in svc 01/15/23
| 14 | FH - TBD12 | FH - TBD12 | SPP FH - 13770 | FH - TBD12.1 | FH - TBD12.1 | SPP FH - Lake Juliana 13770 - OH Feeder | 12/15/22 | Distribution Line - Acct 364 |  |  |  | 605221.0587 | 587442.96 | 202380.385 | 389760.77 | 389760.77 | 483450.9625 | 0 | 0 | 0 | 2658016.9062 | in svc 12/15/22
| 14 | FH - TBD12 | FH - TBD12 | SPP FH - 13770 | FH - TBD12.2 | FH - TBD12.2 | SPP FH - Lake Juliana 13770 - S&E/R&C | 3/15/23 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810000 | 810000 | 810000 | 810000 | 3240000 | in svc 03/15/23
| 15 | FH - TBD13 | FH - TBD13 | SPP FH - 13118 | FH - TBD13.1 | FH - TBD13.1 | SPP FH - Lake Alfred 13118 -OH Feeder | 9/15/22 | Distribution Line - Acct 364 | 0 | 0 | 827400 | 269400 | 330500 | 330500 | 0 | 0 | 0 | 0 | 0 | 0 | 1757800 | in svc 09/15/22
| 15 | FH - TBD13 | FH - TBD13 | SPP FH - 13118 | FH - TBD13.2 | FH - TBD13.2 | SPP FH - Lake Alfred 13118 - S&E/R&C | 3/15/23 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 540000 | 540000 | 1620000 | in svc 03/15/23
| 16 | FH - TBD14 | FH - TBD14 | SPP FH - 13296 | FH - TBD14.1 | FH - TBD14.1 | SPP FH - Jan Phyl 13296 - OH Feeder | 10/15/22 | Distribution Line - Acct 364 | 0 | 0 |  | 1432280.16 | 451346.71 | 555433.3875 | 555433.3875 | 0 | 0 | 0 | 0 | 0 | 2994493.645 | in svc 10/15/22
| 16 | FH - TBD14 | FH - TBD14 | SPP FH - 13296 | FH - TBD14.2 | FH - TBD14.2 | SPP FH - Jan Phyl 13296 - S&E/R&C | 3/15/23 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 1500000 | in svc 03/15/23
| 17 | FH - TBD15 | FH - TBD15 | SPP FH - 13989 | FH - TBD15.1 | FH - TBD15.1 | SPP FH - Trout Creek 13989 | 10/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 319502.305 | 67873.855 | 222558.4925 | 222558.4925 |  | 0 | 0 | 0 | 0 | 832493.145 | in svc 10/15/22
| 18 | FH - TBD16 | FH - TBD16 | SPP FH - 13984 | FH - TBD16.1 | FH - TBD16.1 | SPP FH - Coronet 13984 | 12/15/22 | Distribution Line - Acct 364 | 0 | 0 | 0 | 0 | 475126.555 | 132198.4075 | 172931.21 | 218664.0125 | 172931.21 | 0 | 0 | 0 | 1171851.395 | in svc 12/15/22
| 19 | FH - TBD17 | FH - TBD17 | SPP FH - 14123 | FH - TBD17.1 | FH - TBD17.1 | SPP FH - Fishhawk 14123 | 12/15/22 | Distribution Line - Acct 364 |  | 0 | 0 | 41947.1975 | 0 | 532580.6425 | 224735.9875 | 271683.185 | 177788.79 | 0 | 0 | 0 | 1248735.8025 | in svc 12/15/22
| 20 | FH - TBD28 | FH - TBD28 | SPP FH - 14094 | FH - TBD28.1 | FH - TBD28.1 | SPP FH - Pebble Creek 14094 | 1/15/23 | Distribution Line - Acct 364 | 287.5275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3096 | 5175.495 | 0 | 0 | 8559.0225 | in svc 01/15/23
| 21 | FH - TBD29 | FH - TBD29 | SPP FH - 13651 | FH - TBD29.1 | FH - TBD29.1 | SPP FH - Rhodine 13651 | 2/15/23 | Distribution Line - Acct 364 |  |  | 0 | 1537.6075 | 1537.6075 | 0 | 12096.4575 | 12763.2525 | 12763.2525 | 9688.0375 | 0 | 0 | 50386.215 | in svc 01/15/23
| 22 | FH - TBD30 | FH - TBD30 | SPP FH - 13346 | FH - TBD30.1 | FH - TBD30.1 | SPP FH - East Bay 13346 | 2/15/23 | Distribution Line - Acct 364 |  |  | 0 | 2465.2875 | 2465.2875 | 0 | 0 | 0 | 39806.2625 | 19257.0125 | 16791.725 | 0 | 80785.575 | in svc 02/15/23
| 23 | FH - TBD31 | FH - TBD31 | SPP FH - 13312 | FH - TBD31.1 | FH - TBD31.1 | SPP FH - East Winter Haven13312 | 2/15/23 | Distribution Line - Acct 364 | 0 |  |  | 0 | 9521.46 | 9521.46 | 92060.26 | 33564.38 | 52607.3 | 62128.76 | 52607.3 | 0 | 312010.92 | in svc 02/15/23
| 24 |  |  | RIVA License purchase |  |  | RIVA Licensing for Storm Apps | 10/15/22 | Distribution Line - Acct 364 | October: 5000000 | 5000000
| 25 |  |  | SPP FH - 13008 |  |  | SPP FH - 13008 | 9/15/23 | Distribution Line - Acct 364 | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000
| 26 |  |  | SPP FH - 13028 |  |  | SPP FH - 13028 | 9/15/23 | Distribution Line - Acct 364 | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000
| 27 |  |  | SPP FH - 13039 |  |  | SPP FH - 13039 | 12/15/23 | Distribution Line - Acct 364 | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000
| 28 |  |  | SPP FH - 13077 |  |  | SPP FH - 13077 | 12/15/23 | Distribution Line - Acct 364 | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000
| 29 |  |  | SPP FH - 13187 |  |  | SPP FH - 13187 | 2/15/24 | Distribution Line - Acct 364 | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000
| 30 |  |  | SPP FH - 13227 |  |  | SPP FH - 13227 | 12/15/23 | Distribution Line - Acct 364 | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000
| 31 |  |  | SPP FH - 13230 |  |  | SPP FH - 13230 | 2/15/24 | Distribution Line - Acct 364 | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000
| 32 |  |  | SPP FH - 13292 |  |  | SPP FH - 13292 | 6/15/23 | Distribution Line - Acct 364 | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000
| 33 |  |  | SPP FH - 13299 |  |  | SPP FH - 13299 | 2/15/24 | Distribution Line - Acct 364 | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000
| 34 |  |  | SPP FH - 13308 |  |  | SPP FH - 13308 | 9/15/23 | Distribution Line - Acct 364 | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000
| 35 |  |  | SPP FH - 13687 |  |  | SPP FH - 13687 | 12/15/23 |  | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000
| 36 |  |  | SPP FH - 13040 |  |  | SPP FH - 13040 | 2/15/24 |  | August: 10000; September: 10000; October: 10000; November: 10000; December: 10000 | 50000

## SPPCRC 2023 Projection Capi
Tampa Electric Company
Storm Protection Plan Cost Recovery Clause
Projected Period Amount
Projected Period: January through December 2022
Capital Expenditures
(in Dollars)
Additions Only
[22 empty] | End of |  | Original 2022
|  | Placeholder | Actual |  | Placeholder | Actual |  | PMO Est. |  | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Period |  | Program Est
Line | Program | FP | FP | FP Description | PMO | PMO | PMO Description | In-Service Date | Depr Grp | January | February | March | April | May | June | July | August | September | October | November | December | Total |  | Total | Variance
D | Distribution Overhead Feeder Hardening | [8 empty] | 1430000 | 2090000 | 2480000 | 2900000 | 2900000 | 2823479 | 2578792 | 2832333 | 2772190 | 2732832 | 2645097 | 1430460 | 29615183 |  | 29581441.3912 | -33741.6088
1075084 | 1 |  |  | SPP FH - 13008 |  |  | SPP FH - 13008 | 9/15/23 | Distribution Line - Acct 364 | January: 30000; February: 200000; March: 200000; April: 300000; May: 200000; June: 95084 | 1025084 | -50000
1028395 | 2 |  |  | SPP FH - 13028 |  |  | SPP FH - 13028 | 9/15/23 | Distribution Line - Acct 364 | January: 20000; February: 180000; March: 250000; April: 250000; May: 250000; June: 28395 | 978395 | -50000
1036716 | 3 |  |  | SPP FH - 13039 |  |  | SPP FH - 13039 | 12/15/23 | Distribution Line - Acct 364 | 20000 | 80000 | 100000 | 150000 | 200000 | 200000 | 200000 | 36716 |  |  |  |  | 986716 | -50000
1155581.877 | 4 |  |  | SPP FH - 13077 |  |  | SPP FH - 13077 | 12/15/23 | Distribution Line - Acct 364 | 25000 | 100000 | 100000 | 100000 | 100000 | 200000 | 200000 | 200000 | 80582 |  |  |  | 1105582 | -49999.877
1881714.5036 | 5 |  |  | SPP FH - 13187 |  |  | SPP FH - 13187 | 2/15/24 | Distribution Line - Acct 364 | 30000 | 100000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 200000 | 300000 | 300000 | 1715 | 1831715 | -49999.5036
1050617 | 6 |  |  | SPP FH - 13227 |  |  | SPP FH - 13227 | 12/15/23 | Distribution Line - Acct 364 | 25000 | 30000 | 100000 | 100000 | 200000 | 200000 | 300000 | 45617 |  |  |  |  | 1000617 | -50000
1534545.554 | 7 |  |  | SPP FH - 13230 |  |  | SPP FH - 13230 | 2/15/24 | Distribution Line - Acct 364 | 50000 | 50000 | 50000 | 50000 | 50000 | 200000 | 100000 | 350000 | 250000 | 200000 | 134546 |  | 1484546 | -49999.554
120000 | 8 |  |  | SPP FH - 13292 |  |  | SPP FH - 13292 | 6/15/23 | Distribution Line - Acct 364 | January: 90000; February: 30000 | 120000 | 0
2263199.2333 | 9 |  |  | SPP FH - 13299 |  |  | SPP FH - 13299 | 2/15/24 | Distribution Line - Acct 364 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 300000 | 350000 | 250000 | 80000 | 33199 |  | 2213199 | -50000.2333
1303706 | 10 |  |  | SPP FH - 13308 |  |  | SPP FH - 13308 | 9/15/23 | Distribution Line - Acct 364 | January: 200000; February: 200000; March: 200000; April: 200000; May: 200000; June: 250000; July: 53706 | 1303706 | 0
1150070 | 11 |  |  | SPP FH - 13311 |  |  | SPP FH - 13311 | 2/15/24 | Distribution Line - Acct 364 | 20000 | 20000 | 10000 |  |  |  | 50000 | 200000 | 200000 | 200000 | 300000 | 150070 | 1150070 | 0
49314 | 12 |  |  | SPP FH - 13343 |  |  | SPP FH - 13343 | 2/15/24 | Distribution Line - Acct 364 | December: 49314 | 49314 | 0
53082 | 13 |  |  | SPP FH - 13364 |  |  | SPP FH - 13364 | 2/15/24 | Distribution Line - Acct 364 | December: 53082 | 53082 | 0
968360 | 13 |  |  | SPP FH - 13414 |  |  | SPP FH - 13414 | 2/15/24 | Distribution Line - Acct 364 | January: 50000; February: 20000; August: 50000; September: 150000; October: 250000; November: 300000; December: 148360 | 968360 | 0
1192739 | 14 |  |  | SPP FH - 13417 |  |  | SPP FH - 13417 | 2/15/24 | Distribution Line - Acct 364 | January: 50000; July: 50000; August: 200000; September: 200000; October: 250000; November: 300000; December: 142739 | 1192739 | 0
45745 | 14 |  |  | SPP FH - 13438 |  |  | SPP FH - 13438 | 2/15/24 | Distribution Line - Acct 364 | December: 45745 | 45745 | 0
961008 | 15 |  |  | SPP FH - 13457 |  |  | SPP FH - 13457 | 9/15/23 | Distribution Line - Acct 364 | January: 50000; February: 200000; March: 200000; April: 200000; May: 150000; June: 100000; July: 61008 | 961008 | 0
1367614 | 15 |  |  | SPP FH - 13633 |  |  | SPP FH - 13633 | 2/15/24 | Distribution Line - Acct 364 | January: 50000; July: 100000; August: 200000; September: 200000; October: 300000; November: 350000; December: 167614 | 1367614 | 0
2268364.9856 | 16 |  |  | SPP FH - 13687 |  |  | SPP FH - 13687 | 12/15/23 | Distribution Line - Acct 364 | 200000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 268365 |  |  |  | 2218365 | -49999.9856
1017582 | 16 |  |  | SPP FH - 13695 |  |  | SPP FH - 13695 | 2/15/24 | Distribution Line - Acct 364 | January: 30000; February: 20000; August: 50000; September: 60000; October: 350000; November: 350000; December: 157582 | 1017582 | 0
960134 | 17 |  |  | SPP FH - 13737 |  |  | SPP FH - 13737 | 2/15/24 | Distribution Line - Acct 364 | 30000 | 20000 |  |  |  |  | 100000 | 100000 | 100000 | 200000 | 200000 | 210134 | 960134 | 0
1214078.263 | 18 |  |  | SPP FH - 13753 |  |  | SPP FH - 13753 | 9/15/23 | Distribution Line - Acct 364 | January: 30000; February: 20000; March: 250000; April: 300000; May: 300000; June: 300000; July: 14078 | 1214078 | -0.263
120000 | 19 |  |  | SPP FH - 13772 |  |  | SPP FH - 13772 | 2/15/24 | Distribution Line - Acct 364 | November: 30000; December: 90000 | 120000 | 0
1547352 | 20 |  |  | SPP FH - 13807 |  |  | SPP FH - 13807 | 2/15/24 | Distribution Line - Acct 364 | 50000 | 50000 | 100000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 100000 | 47352 |  | 1547352 | 0
1083242.9856 | 21 |  |  | SPP FH - 13892 |  |  | SPP FH - 13892 | 12/15/23 | Distribution Line - Acct 364 | 30000 | 120000 | 120000 | 150000 | 150000 | 150000 | 150000 | 150000 | 63243 |  |  |  | 1083243 | 0.0144
8847 | 22 |  |  | SPP FH - 13944 |  |  | SPP FH - 13944 | 2/15/24 | Distribution Line - Acct 364 | December: 8847 | 8847 | 0
79623 | 23 |  |  | SPP FH - 13014 |  |  | SPP FH - 13014 | 2/15/24 | Distribution Line - Acct 364 | December: 79623 | 79623 | 0
2252831.9856 | 24 |  |  | SPP FH - 13040 |  |  | SPP FH - 13040 | 2/15/24 | Distribution Line - Acct 364 | 150000 | 200000 | 200000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 202832 |  |  | 2252832 | 0.0144
1196012 | 25 |  |  | SPP FH - 13042 |  |  | SPP FH - 13042 | 2/15/24 | Distribution Line - Acct 364 |  |  |  | 50000 | 50000 | 50000 | 50000 | 50000 | 300000 | 300000 | 300000 | 46012 | 1196012 | 0
79623 | 26 |  |  | SPP FH - 13083 |  |  | SPP FH - 13083 | 2/15/24 | Distribution Line - Acct 364 | December: 79623 | 79623 | 0
| 27 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0 | 0
| 28 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0 | 0
| 29 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0 | 0
| 30 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 31 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 32 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 33 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 34 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 35 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 36 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 37 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 38 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 39 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 40 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 41 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 42 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 43 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 44 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 45 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 46 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 47 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 48 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 49 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 50 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 51 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 52 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0
| 53 | [7 empty] | Distribution Line - Acct 364 | [12 empty] | 0

## Sheet4
Circuit Number | ProjectID | Sum of Project_Costs
13008 |  | 1075084
| Distribution Feeder Hardening-Breaker-60013388 | 545483
| Distribution Feeder Hardening-Recloser-92477860 | 529601
13028 |  | 1028395
| Distribution Feeder Hardening-Breaker-60055353 | 420395
| FLISR-13028 | 608000
13039 |  | 1036716
| Distribution Feeder Hardening-Breaker-60078488 | 504716
| FLISR-13039 | 532000
13077 |  | 1155581.877
| Distribution Feeder Hardening-Breaker-92300431 | 699528
| FLISR-13077 | 456053.877
13187 |  | 1881714.5036
| Distribution Feeder Hardening-Breaker-60075458 | 744923
| FLISR-13187 | 1136791.5036
13227 |  | 1050617
| Distribution Feeder Hardening-Breaker-60063798 | 636617
| FLISR-13227 | 414000
13230 |  | 1534545.554
| Distribution Feeder Hardening-Breaker-60049915 | 520573
| FLISR-13230 | 1013972.554
13292 |  | 120000
| Lake Silver N-13292-Protection Upgrade | 120000
13299 |  | 2263199.2333
| Distribution Feeder Hardening-Breaker-60320300 | 540104
| Distribution Feeder Hardening-Recloser-93280362 | 513126
| FLISR-13299 | 1209969.2333
13308 |  | 1303706
| Distribution Feeder Hardening-Breaker-60067752 | 1027706
| FLISR-13308 | 276000
13311 |  | 1150070
| Distribution Feeder Hardening-Breaker-60067708 | 770070
| FLISR-13311 | 380000
13343 |  | 49314
| Distribution Feeder Hardening-Breaker-76251434 | 49314
13364 |  | 53082
| Distribution Feeder Hardening-Breaker-60068434 | 53082
13414 |  | 968360
| Distribution Feeder Hardening-Breaker-60089566 | 455346
| Distribution Feeder Hardening-Recloser-92204970 | 513014
13417 |  | 1192739
| Distribution Feeder Hardening-Breaker-60055127 | 812739
| FLISR-13417 | 380000
13438 |  | 45745
| Distribution Feeder Hardening-Breaker-60070711 | 45745
13457 |  | 961008
| Distribution Feeder Hardening-Breaker-60083955 | 581008
| FLISR-13457 | 380000
13633 |  | 1367614
| Distribution Feeder Hardening-Breaker-60075477 | 1017614
| FLISR-13633 | 350000
13687 |  | 2268364.9856
| Distribution Feeder Hardening-Breaker-60083992 | 614592
| Distribution Feeder Hardening-Recloser-92018434 | 556112
| FLISR-13687 | 977660.9856
| Pearson S-13687-Protection Upgrade | 120000
13695 |  | 1017582
| Distribution Feeder Hardening-Breaker-60066896 | 485582
| FLISR-13695 | 532000
13737 |  | 960134
| Distribution Feeder Hardening-Breaker-60068564 | 580134
| FLISR-13737 | 380000
13753 |  | 1214078.263
| Distribution Feeder Hardening-Breaker-60075196 | 736076
| FLISR-13753 | 478002.263
13772 |  | 120000
| Lake Juliana-13772-Protection Upgrade | 120000
13807 |  | 1547352
| Distribution Feeder Hardening-Breaker-60095496 | 787267
| Distribution Feeder Hardening-Recloser-92203202 | 438085
| FLISR-13807 | 322000
13892 |  | 1083242.9856
| Distribution Feeder Hardening-Breaker-60071612 | 181582
| FLISR-13892 | 901660.9856
13944 |  | 8847
| Distribution Feeder Hardening-Breaker-60066663 | 8847
14014 |  | 79623
| Distribution Feeder Hardening-Breaker-90939808 | 79623
14040 |  | 2252831.9856
| Distribution Feeder Hardening-Breaker-60084101 | 404267
| Distribution Feeder Hardening-Recloser-91847101 | 794904
| FLISR-14040 | 1053660.9856
14042 |  | 1196012
| Distribution Feeder Hardening-Breaker-60084114 | 355183
| Distribution Feeder Hardening-Recloser-92357154 | 840829
14083 |  | 79623
| Distribution Feeder Hardening-Breaker-72901595 | 79623
Total Result |  | 30065182.3877

## FH and FLISR 2023
Circuit Number | ProjectID | Project_Costs | 13008 | SPP FH - 13008 | 1075084
13008 | Distribution Feeder Hardening-Breaker-60013388 | 545483 | 13028 | SPP FH - 13028 | 1028395
13008 | Distribution Feeder Hardening-Recloser-92477860 | 529601 | 13039 | SPP FH - 13039 | 1036716
13028 | Distribution Feeder Hardening-Breaker-60055353 | 420395 | 13077 | SPP FH - 13077 | 1155581.877
13028 | FLISR-13028 | 608000 | 13187 | SPP FH - 13187 | 1881714.5036
13039 | Distribution Feeder Hardening-Breaker-60078488 | 504716 | 13227 | SPP FH - 13227 | 1050617
13039 | FLISR-13039 | 532000 | 13230 | SPP FH - 13230 | 1534545.554
13077 | Distribution Feeder Hardening-Breaker-92300431 | 699528 | 13292 | SPP FH - 13292 | 120000
13077 | FLISR-13077 | 456053.877 | 13299 | SPP FH - 13299 | 2263199.2333
13187 | Distribution Feeder Hardening-Breaker-60075458 | 744923 | 13308 | SPP FH - 13308 | 1303706
13187 | FLISR-13187 | 1136791.5036 | 13311 | SPP FH - 13311 | 1150070
13227 | Distribution Feeder Hardening-Breaker-60063798 | 636617 | 13343 | SPP FH - 13343 | 49314
13227 | FLISR-13227 | 414000 | 13364 | SPP FH - 13364 | 53082
13230 | Distribution Feeder Hardening-Breaker-60049915 | 520573 | 13414 | SPP FH - 13414 | 968360
13230 | FLISR-13230 | 1013972.554 | 13417 | SPP FH - 13417 | 1192739
13292 | Lake Silver N-13292-Protection Upgrade | 120000 | 13438 | SPP FH - 13438 | 45745
13299 | Distribution Feeder Hardening-Breaker-60320300 | 540104 | 13457 | SPP FH - 13457 | 961008
13299 | Distribution Feeder Hardening-Recloser-93280362 | 513126 | 13633 | SPP FH - 13633 | 1367614
13299 | FLISR-13299 | 1209969.2333 | 13687 | SPP FH - 13687 | 2268364.9856
13308 | Distribution Feeder Hardening-Breaker-60067752 | 1027706 | 13695 | SPP FH - 13695 | 1017582
13308 | FLISR-13308 | 276000 | 13737 | SPP FH - 13737 | 960134
13311 | Distribution Feeder Hardening-Breaker-60067708 | 770070 | 13753 | SPP FH - 13753 | 1214078.263
13311 | FLISR-13311 | 380000 | 13772 | SPP FH - 13772 | 120000
13343 | Distribution Feeder Hardening-Breaker-76251434 | 49314 | 13807 | SPP FH - 13807 | 1547352
13364 | Distribution Feeder Hardening-Breaker-60068434 | 53082 | 13892 | SPP FH - 13892 | 1083242.9856
13414 | Distribution Feeder Hardening-Breaker-60089566 | 455346 | 13944 | SPP FH - 13944 | 8847
13414 | Distribution Feeder Hardening-Recloser-92204970 | 513014 | 14014 | SPP FH - 13014 | 79623
13417 | Distribution Feeder Hardening-Breaker-60055127 | 812739 | 14040 | SPP FH - 13040 | 2252831.9856
13417 | FLISR-13417 | 380000 | 14042 | SPP FH - 13042 | 1196012
13438 | Distribution Feeder Hardening-Breaker-60070711 | 45745 | 14083 | SPP FH - 13083 | 79623
13457 | Distribution Feeder Hardening-Breaker-60083955 | 581008
13457 | FLISR-13457 | 380000
13633 | Distribution Feeder Hardening-Breaker-60075477 | 1017614
13633 | FLISR-13633 | 350000
13687 | Distribution Feeder Hardening-Recloser-92018434 | 556112
13687 | Distribution Feeder Hardening-Breaker-60083992 | 614592
13687 | FLISR-13687 | 977660.9856
13687 | Pearson S-13687-Protection Upgrade | 120000
13695 | Distribution Feeder Hardening-Breaker-60066896 | 485582
13695 | FLISR-13695 | 532000
13737 | Distribution Feeder Hardening-Breaker-60068564 | 580134
13737 | FLISR-13737 | 380000
13753 | Distribution Feeder Hardening-Breaker-60075196 | 736076
13753 | FLISR-13753 | 478002.263
13772 | Lake Juliana-13772-Protection Upgrade | 120000
13807 | Distribution Feeder Hardening-Breaker-60095496 | 787267
13807 | Distribution Feeder Hardening-Recloser-92203202 | 438085
13807 | FLISR-13807 | 322000
13892 | Distribution Feeder Hardening-Breaker-60071612 | 181582
13892 | FLISR-13892 | 901660.9856
13944 | Distribution Feeder Hardening-Breaker-60066663 | 8847
14014 | Distribution Feeder Hardening-Breaker-90939808 | 79623
14040 | Distribution Feeder Hardening-Breaker-60084101 | 404267
14040 | Distribution Feeder Hardening-Recloser-91847101 | 794904
14040 | FLISR-14040 | 1053660.9856
14042 | Distribution Feeder Hardening-Breaker-60084114 | 355183
14042 | Distribution Feeder Hardening-Recloser-92357154 | 840829
14083 | Distribution Feeder Hardening-Breaker-72901595 | 79623