## 2022
Tampa Electric Company
Storm Protection Plan
Projected Period Amount
Projected Period: January through December 2022
Capital Expenditures
(in Dollars)
Additions Only
End of
|  | Placeholder | Actual |  | Placeholder | Actual |  | PMO Est. |  | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Period
Line | Program | FP | FP | FP Description | PMO | PMO | PMO Description | In-Service Date | Depr Grp | January | February | March | April | May | June | July | August | September | October | November | December | Total
E | Transmission Access Enhancements | [8 empty] | 316758.9 | 313258.9 | 119123.45 | 116347.5833 | 222647.2653 | 222647.2653 | 257864.26 | 280864.26 | 183231.2447 | 245002.9113 | 70438.3333 | 61771.6667 | 2409956.04
| 1 | TXE - TBD1 | PRE-09813 | SPP TXE - 230008 | TXE - TBD1.1 | PRE-09813.1 | SPP TXE - 230008 | 1/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46438.3333 | 46438.3333 | 46438.3333 | 139315
| 2 | TXE - TBD2 | PRE-09814 | SPP TXE - 230623 | TXE - TBD2.1 | PRE-09814.1 | SPP TXE - 230623 | 11/15/2027 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | TXE - TBD3 | PRE-09815 | SPP TXE - P - Bridge | TXE - TBD3.1 | PRE-09815.1 | SPP TXE - P - Bridge | 12/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | TXE - TBD4 | PRE-09816 | SPP TXE - Hampton Sub - Bridge | TXE - TBD4.1 | PRE-09816.1 | SPP TXE - Hampton Sub - Bridge | 11/15/2022 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 151564.578 | 151564.578 | 151564.578 | 151564.578 | 0 | 0 | 606258.312
| 5 | TXE - TBD5 | PRE-09817 | SPP TXE - 230033 | TXE - TBD5.1 | PRE-09817.1 | SPP TXE - 230033 | 5/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | TXE - TBD6 | PRE-09818 | SPP TXE - Morris Bridge - Bridge | TXE - TBD6.1 | PRE-09818.1 | SPP TXE - Morris Bridge - Bridge | 9/15/2022 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 106299.682 | 106299.682 | 106299.682 | 106299.682 | 0 | 0 | 0 | 0 | 425198.728
| 7 | TXE - TBD7 | PRE-09819 | SPP TXE - 66007 | TXE - TBD7.1 | PRE-09819.1 | SPP TXE - 66007 | 11/15/2023 | Transmission Line - Acct 359 | 12364.5 | 8864.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21229
| 8 | TXE - TBD8 | PRE-09820 | SPP TXE - 230037 | TXE - TBD8.1 | PRE-09820.1 | SPP TXE - 230037 | 8/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | TXE - TBD9 | PRE-09821 | SPP TXE - 66839 | TXE - TBD9.1 | PRE-09821.1 | SPP TXE - 66839 | 11/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8666.6667 | 8666.6667 | 8666.6667 | 26000
| 10 | TXE - TBD10 | PRE-09822 | SPP TXE - 230606 | TXE - TBD10.1 | PRE-09822.1 | SPP TXE - 230606 | 11/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 20000
| 11 | TXE - TBD11 | PRE-09836 | SPP TXE - Columbus Dr #2 - Bridge | TXE - TBD11.1 | PRE-09836.1 | SPP TXE - Columbus Dr #2 - Bridge | 12/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7333.3333 | 7333.3333 | 7333.3333 | 0 | 0 | 22000 | 723791 | 1686165.04
| 12 | TXE - TBD12 | PRE-09837 | SPP TXE - W. of Forbes Rd - Bridge | TXE - TBD12.1 | PRE-09837.1 | SPP TXE - W. of Forbes Rd - Bridge | 6/15/2024 | Transmission Line - Acct 359 | 30809.7333 | 30809.7333 | 30809.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92429.2
| 13 | TXE - TBD13 | PRE-09838 | SPP TXE - Columbus Dr #1 - Bridge | TXE - TBD13.1 | PRE-09838.1 | SPP TXE - Columbus Dr #1 - Bridge | 12/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000 | 0 | 0 | 27000
| 14 | TXE - TBD14 | PRE-09839 | SPP TXE - Tampa Palms #1 - Bridge | TXE - TBD14.1 | PRE-09839.1 | SPP TXE - Tampa Palms #1 - Bridge | 4/15/2023 | Transmission Line - Acct 359 | 47377.3 | 47377.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94754.6
| 15 | TXE - TBD16 | PRE-09841 | SPP TXE - E.Sydney Washer Rd-Bridge | TXE - TBD16.1 | PRE-09841.1 | SPP TXE - E.Sydney Washer Rd-Bridge | 6/15/2024 | Transmission Line - Acct 359 | 33508.4667 | 33508.4667 | 33508.4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100525.4
| 16 | TXE - TBD17 | PRE-09842 | SPP TXE - Tampa Palms #3 - Bridge | TXE - TBD17.1 | PRE-09842.1 | SPP TXE - Tampa Palms #3 - Bridge | 7/15/2023 | Transmission Line - Acct 359 | 51425.4 | 51425.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102850.8
| 17 | TXE - TBD20 | PRE-09872 | SPP TXE - 230020 - 4 road locations | TXE - TBD20.1 | PRE-09872.1 | SPP TXE - 230020 - 4 road locations | 12/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 54805.25 | 54805.25 | 54805.25 | 54805.25 | 0 | 0 | 0 | 0 | 0 | 0 | 219221
| 18 | TXE - TBD21 | PRE-09873 | SPP TXE - Tampa Palms #2 - Bridge | TXE - TBD21.1 | PRE-09873.1 | SPP TXE - Tampa Palms #2 - Bridge | 6/15/2023 | Transmission Line - Acct 359 | 53449.7 | 53449.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106899.4
| 19 | TXE - TBD24 | PRE-09876 | SPP TXE - 66016 | TXE - TBD24.1 | PRE-09876.1 | SPP TXE - 66016 | 12/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 20000
| 20 | TXE - TBD25 | PRE-09877 | SPP TXE - Tampa Palms #4 - Bridge | TXE - TBD25.1 | PRE-09877.1 | SPP TXE - Tampa Palms #4 - Bridge | 9/15/2023 | Transmission Line - Acct 359 | 54124.3 | 54124.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108248.6
| 21 | TXE - TBD26 | PRE-09878 | SPP TXE - 66035 - 2 road locations | TXE - TBD26.1 | PRE-09878.1 | SPP TXE - 66035 - 2 road locations | 12/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8666.6667 | 8666.6667 | 8666.6667 | 0 | 26000
| 22 | TXE - TBD30 | PRE-09881 | SPP TXE - 230007 | TXE - TBD30.1 | PRE-09881.1 | SPP TXE - 230007 | 10/15/2023 | Transmission Line - Acct 359 | 33699.5 | 33699.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67399
| 23 | TXE - TBD32 | TXE - TBD32 | SPP TXE - 66033 | TXE - TBD32.1 | TXE - TBD32.1 | SPP TXE - 66033 | 1/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 15024 | 15024 | 15024 | 0 | 0 | 0 | 0 | 0 | 0 | 45072
| 24 | TXE - TBD34 | TXE - TBD34 | SPP TXE - 66046 | TXE - TBD34.1 | TXE - TBD34.1 | SPP TXE - 66046 | 1/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 30304.6667 | 30304.6667 | 30304.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 90914
| 25 | TXE - TBD36 | TXE - TBD36 | SPP TXE - 66001 - 3 road locations | TXE - TBD36.1 | TXE - TBD36.1 | SPP TXE - 66001 - 3 road locations | 1/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 16213.6667 | 16213.6667 | 16213.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 48641

## 2023
Tampa Electric Company
Storm Protection Plan
Projected Period Amount
Projected Period: January through December 2023
Capital Expenditures
(in Dollars)
Additions Only
End of
|  | Placeholder | Actual |  | Placeholder | Actual |  | PMO Est. |  | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Period
Line | Program | FP | FP | FP Description | PMO | PMO | PMO Description | In-Service Date | Depr Grp | January | February | March | April | May | June | July | August | September | October | November | December | Total
E | Transmission Access Enhancements | [8 empty] | 205557.76 | 342955.66 | 368667.3 | 509692.4 | 404939.3 | 267541.4 | 230028.7133 | 137524.9467 | 137524.9467 | 176685.3733 | 128164.04 | 128164.04 | 3037445.88
| 1 | TXE - TBD1 | PRE-09813 | SPP TXE - 230008 | TXE - TBD1.1 | PRE-09813.1 | SPP TXE - 230008 | 1/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | TXE - TBD2 | PRE-09814 | SPP TXE - 230623 | TXE - TBD2.1 | PRE-09814.1 | SPP TXE - 230623 | 11/15/2027 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | TXE - TBD3 | PRE-09815 | SPP TXE - P - Bridge | TXE - TBD3.1 | PRE-09815.1 | SPP TXE - P - Bridge | 12/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | TXE - TBD4 | PRE-09816 | SPP TXE - Hampton Sub - Bridge | TXE - TBD4.1 | PRE-09816.1 | SPP TXE - Hampton Sub - Bridge | 11/15/2022 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | TXE - TBD5 | PRE-09817 | SPP TXE - 230033 | TXE - TBD5.1 | PRE-09817.1 | SPP TXE - 230033 | 5/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | TXE - TBD6 | PRE-09818 | SPP TXE - Morris Bridge - Bridge | TXE - TBD6.1 | PRE-09818.1 | SPP TXE - Morris Bridge - Bridge | 9/15/2022 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | TXE - TBD7 | PRE-09819 | SPP TXE - 66007 | TXE - TBD7.1 | PRE-09819.1 | SPP TXE - 66007 | 11/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48521.3333 | 48521.3333 | 48521.3333 | 0 | 0 | 145564
| 8 | TXE - TBD8 | PRE-09820 | SPP TXE - 230037 | TXE - TBD8.1 | PRE-09820.1 | SPP TXE - 230037 | 8/15/2029 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | TXE - TBD9 | PRE-09821 | SPP TXE - 66839 | TXE - TBD9.1 | PRE-09821.1 | SPP TXE - 66839 | 11/15/2025 | Transmission Line - Acct 359 | 15192.265 | 15192.265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30384.53
| 10 | TXE - TBD10 | PRE-09822 | SPP TXE - 230606 | TXE - TBD10.1 | PRE-09822.1 | SPP TXE - 230606 | 11/15/2025 | Transmission Line - Acct 359 | 6194.905 | 6194.905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12389.81
| 11 | TXE - TBD11 | PRE-09836 | SPP TXE - Columbus Dr #2 - Bridge | TXE - TBD11.1 | PRE-09836.1 | SPP TXE - Columbus Dr #2 - Bridge | 12/15/2025 | Transmission Line - Acct 359 | 29892.965 | 29892.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59785.93
| 12 | TXE - TBD12 | PRE-09837 | SPP TXE - W. of Forbes Rd - Bridge | TXE - TBD12.1 | PRE-09837.1 | SPP TXE - W. of Forbes Rd - Bridge | 6/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13 | TXE - TBD13 | PRE-09838 | SPP TXE - Columbus Dr #1 - Bridge | TXE - TBD13.1 | PRE-09838.1 | SPP TXE - Columbus Dr #1 - Bridge | 12/15/2025 | Transmission Line - Acct 359 | 29892.965 | 29892.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59785.93
| 14 | TXE - TBD14 | PRE-09839 | SPP TXE - Tampa Palms #1 - Bridge | TXE - TBD14.1 | PRE-09839.1 | SPP TXE - Tampa Palms #1 - Bridge | 4/15/2023 | Transmission Line - Acct 359 | 104753.1 | 104753.1 | 104753.1 | 104753.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419012.4
| 15 | TXE - TBD16 | PRE-09841 | SPP TXE - E.Sydney Washer Rd-Bridge | TXE - TBD16.1 | PRE-09841.1 | SPP TXE - E.Sydney Washer Rd-Bridge | 6/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16 | TXE - TBD17 | PRE-09842 | SPP TXE - Tampa Palms #3 - Bridge | TXE - TBD17.1 | PRE-09842.1 | SPP TXE - Tampa Palms #3 - Bridge | 7/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 126516.3 | 126516.3 | 126516.3 | 126516.3 | 0 | 0 | 0 | 0 | 0 | 0 | 506065.2
| 17 | TXE - TBD20 | PRE-09872 | SPP TXE - 230020 - 4 road locations | TXE - TBD20.1 | PRE-09872.1 | SPP TXE - 230020 - 4 road locations | 12/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18 | TXE - TBD21 | PRE-09873 | SPP TXE - Tampa Palms #2 - Bridge | TXE - TBD21.1 | PRE-09873.1 | SPP TXE - Tampa Palms #2 - Bridge | 6/15/2023 | Transmission Line - Acct 359 | 0 | 137397.9 | 137397.9 | 137397.9 | 137397.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549591.6
| 19 | TXE - TBD24 | PRE-09876 | SPP TXE - 66016 | TXE - TBD24.1 | PRE-09876.1 | SPP TXE - 66016 | 12/15/2025 | Transmission Line - Acct 359 | 7581 | 7581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15162
| 20 | TXE - TBD25 | PRE-09877 | SPP TXE - Tampa Palms #4 - Bridge | TXE - TBD25.1 | PRE-09877.1 | SPP TXE - Tampa Palms #4 - Bridge | 9/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 0 | 141025.1 | 141025.1 | 141025.1 | 141025.1 | 0 | 0 | 0 | 0 | 0 | 564100.4
| 21 | TXE - TBD26 | PRE-09878 | SPP TXE - 66035 - 2 road locations | TXE - TBD26.1 | PRE-09878.1 | SPP TXE - 66035 - 2 road locations | 12/15/2025 | Transmission Line - Acct 359 | 12050.56 | 12050.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24101.12
| 22 | TXE - TBD30 | PRE-09881 | SPP TXE - 230007 | TXE - TBD30.1 | PRE-09881.1 | SPP TXE - 230007 | 10/15/2023 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 89003.6133 | 89003.6133 | 89003.6133 | 0 | 0 | 0 | 267010.84
| 23 | TXE - TBD32 | TXE - TBD32 | SPP TXE - 66033 | TXE - TBD32.1 | TXE - TBD32.1 | SPP TXE - 66033 | 1/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60552.7867 | 60552.7867 | 60552.7867 | 181658.36
| 24 | TXE - TBD34 | TXE - TBD34 | SPP TXE - 66046 | TXE - TBD34.1 | TXE - TBD34.1 | SPP TXE - 66046 | 1/15/2025 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 25 | TXE - TBD36 | TXE - TBD36 | SPP TXE - 66001 - 3 road locations | TXE - TBD36.1 | TXE - TBD36.1 | SPP TXE - 66001 - 3 road locations | 1/15/2024 | Transmission Line - Acct 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67611.2533 | 67611.2533 | 67611.2533 | 202833.76

## 2024+
ProjectID | Project_Costs | Project Type | Install Year
Site Access-230004 | 336380 | Road | 2030
Site Access-230005 | 290648 | Road | 2030
Site Access-230006 | 1260618 | Road | 2026
Site Access-230020 | 1347704 | Road | 2024
Site Access-230021 | 1931687 | Road | 2028
Site Access-230402 | 4424772 | Road | 2031
Site Access-230604 | 702698 | Road | 2029
Site Access-230606 | 172321 | Road | 2025
Site Access-230612 | 871512 | Road | 2025
Site Access-230623 | 177788 | Road | 2027
Site Access-66014 | 370333 | Road | 2030
Site Access-66016 | 174633 | Road | 2026
Site Access-66021 | 1087955 | Road | 2027
Site Access-66025 | 463876 | Road | 2029
Site Access-66035 | 244616 | Road | 2025
Site Access-66046 | 496313 | Road | 2024
Site Access-66055 | 1402807 | Road | 2026
Site Access-66833 | 2137983 | Road | 2027
Site Access-66839 | 325313 | Road | 2025
Site Access-BLOUNT RD | 869119 | Bridge | 2025
Site Access-C.R. 542 | 608458 | Bridge | 2026
Site Access-COLUMBUS DRIVE #1 | 610006 | Bridge | 2025
Site Access-COLUMBUS DRIVE #2 | 610006 | Bridge | 2025
Site Access-COUNTRYWAY BLVD | 729048 | Bridge | 2028
Site Access-EAST OF SYDNEY WASHER RD | 622374 | Bridge | 2024
Site Access-HOLLOWAY RD | 575233 | Bridge | 2029
Site Access-KEYSVILLE RD EAST | 535107 | Bridge | 2029
Site Access-KEYSVILLE RD WEST | 561857 | Bridge | 2030
Site Access-KIRKLAND RD | 561857 | Bridge | 2029
Site Access-LITTLE FISHHAWK CREEK | 481606 | Bridge | 2030
Site Access-RACE TRACK RD | 481606 | Bridge | 2028
Site Access-WEST OF FORBES RD | 540189 | Bridge | 2024