1

1                             BEFORE THE

FLORIDA PUBLIC SERVICE COMMISSION

2

3                                          DOCKET NO. 110009-EI

4       In the Matter of:

5       NUCLEAR COST RECOVERY CLAUSE.

______________________________/

6

7       PROCEEDINGS:        SPECIAL AGENDA

8       COMMISSIONERS

PARTICIPATING:      CHAIRMAN ART GRAHAM

9                           COMMISSIONER LISA POLAK EDGAR

COMMISSIONER RONALD A. BRISÉ

10                           COMMISSIONER EDUARDO E. BALBIS

COMMISSIONER JULIE I. BROWN

11

DATE:               Monday, October 24, 2011

12

TIME:               Commenced at 9:30 a.m.

13                           Concluded at 12:19 p.m.

14       PLACE:              Betty Easley Conference Center

Room 148

15                           4075 Esplanade Way

Tallahassee, Florida

16

REPORTED BY:        LINDA BOLES, RPR, CRR

17                           Official FPSC Reporter

(850) 413-6734

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

2

1                        P R O C E E D I N G S

2                 CHAIRMAN GRAHAM:  Good morning, everyone.  Let

3       the record show it is November 24th -- I'm sorry --

4       October 24th.  We have a Special Agenda today.  It's

5       Docket Number 110009, the Nuclear Cost Recovery Clause.

6                 I'm glad you're all here, all here safely.  I

7       think we're going to have a fantastic day today.  So

8       we'll get started.  If you'd like to join me for the

9       invocation and pledge, please stand.

10                 (Invocation and pledge.)

11                 All right.  My understanding, this is going to

12       be quick and simple.

13                 So, Mark, I believe that you have the helm,

14       and you're going to take us through this.

15                 Commissioners, I believe we're going to go

16       through this one issue at a time.  We may get to the

17       point where we can skip a couple, but that's probably

18       the easiest way to go, unless somebody else has got any

19       other suggestions.

20                 Mark.

21                 MR. LAUX:  Thank you, Mr. Chairman.

22                 Good morning, Commissioners.

23                 I'll start again.  Thank you, Mr. Chairman.

24                 Good morning, Commissioners.  My name is Mark

25       Laux with Commission Staff.

FLORIDA PUBLIC SERVICE COMMISSION

3

1                 Today Staff is presenting its recommendation

2       in Docket Number 110009, the Nuclear Cost Recovery

3       proceeding.  This docket consists of the petitions filed

4       by Florida Power & Light and Progress Energy.

5                 FPL's petition included cost recovery requests

6       related to the uprates at existing nuclear plants at the

7       Turkey Point and St. Lucie site, as well as proposed new

8       generation at the Turkey Point site.  These requests are

9       addressed in Issues 1 through 19.

10                 Progress Energy's petition included cost

11       recovery related to their -- operate at the Crystal

12       River site, as well as proposed new generation at the

13       Levy site.  These requests are addressed in Issues 20

14       through 37.

15                 Staff notes that concerns on the Crystal River

16       uprate project became the subject of certain motions and

17       a stipulation.  The Commission addressed these motions

18       and stipulation at hearing.  Given these actions, only

19       issues concerning the Levy site remain to be resolved

20       today.

21                 A number of Staff are here today to aid you in

22       your discussions.  Mr. Young will deal with legal

23       concerns found in Issues 2, 15B and C; Mr. Garl and

24       Ellis on feasibility Issues 3, 10, 20, and related

25       Issues 3A, 4, 5, 21, and 22; Mr. Dowds on Issue 15A;

FLORIDA PUBLIC SERVICE COMMISSION

4

1       Mr. Breman and myself, we get all the remaining issues.

2                 On Friday, October 21st, each of your offices

3       should have received a memo from Staff that identified

4       certain typographical errors that are found in Staff's

5       recommendation.  At your pleasure, Staff can address

6       this errata now or as each one of the issues are

7       presented.

8                 Staff would further note that this is a

9       posthearing decision and is limited to participation --

10       participation is limited by Commissioners and the Staff.

11       We're prepared to go issue by issue or in any other

12       manner in which you choose.

13                 CHAIRMAN GRAHAM:  Let's go ahead and make

14       those modifications, those changes that you had that I

15       believe -- I don't know if most Commissioners got that

16       e-mail.  Let's go ahead and do those and put those on

17       the record, and then go back to the beginning.

18                 MR. LAUX:  Yes, sir.

19                 Commissioners, the first change is found on

20       page 17 in Issue 3.  If you look at the last paragraph

21       on that page, the third sentence down that starts with

22       $0.1 billion, you'll find the numbers 12.9 billion and

23       18.8 billion.  Those numbers should be changed to -- the

24       12.9 should be changed to 12.8; the 18.8 should be

25       changed to 18.7.

FLORIDA PUBLIC SERVICE COMMISSION

5

1                 If you turn to page 21, the last paragraph,

2       the third sentence that starts with "estimated 2011," in

3       front of the dollar amount 8,112,681, insert the word

4       "negative."  Did I go on the wrong page?  I'm sorry.

5                 On page 21 -- I flipped the wrong page on my

6       thing here.  In the first full paragraph on that page,

7       the very last sentence, the same 12.9 billion and

8       8.8 billion should be changed to 12.8 billion and

9       18.7 billion.

10                 Also on the chart up there, Figure 3.3, to the

11       very far end you will find the numbers 8,678 and 4,910.

12       Those numbers should be changed to 8,679 and 4,907.

13                 On page 28 in the recommendation section, the

14       second line of that, you will see the numbers

15       8.8 billion -- well, on the first line you will see the

16       number 12.9 billion, and on the second line you will see

17       8.8 billion.  The same changes to those.  The 12.9

18       should be 12.8.  The 18.8 should become 18.7.

19                 And as I was trying to hurry us along on page

20       41 again, last paragraph, third sentence, insert the

21       word "negative" in front of the number 812,681.

22                 On page 76, recommendation section, second

23       paragraph, third sentence, you will see a jurisdictional

24       number of 7,061,419.  That number should be changed to

25       7,176,395.  Oh, I'm sorry.  I did read the -- I read to

FLORIDA PUBLIC SERVICE COMMISSION

6

1       you the system number.  The jurisdictional number should

2       be changed from 7,061,419 to 7,067,402.

3                 On page 80, under the conclusions section, the

4       second paragraph, the same change should be made.  Once

5       again, the jurisdictional number goes from 7,061,419 to

6       7,067,402.

7                 And finally, on page 83, first full paragraph,

8       or first paragraph, fourth line, you'll find the number

9       12,701,007.  That should be changed to 12,706,916.

10                 Thank you.

11                 CHAIRMAN GRAHAM:  Who's got Number 1?

12                 MR. BREMAN:  Commissioners, Issue 1 is should

13       FPL be disallowed recovery of any of its rate case type

14       expenses.  The Staff recommendation is no.

15                 CHAIRMAN GRAHAM:  Actually, Commissioners,

16       Issues 1 through 5, are there any questions of those

17       first five issues?

18                 Yes?  Which issue?

19                 COMMISSIONER BROWN:  2.

20                 CHAIRMAN GRAHAM:  Issue 2.  Let's go with

21       Issue 2.

22                 MR. YOUNG:  Good morning, Commissioners.

23       Keino Young, legal Staff.

24                 Issue 2 is do the FPL activities through 2010

25       related to the Turkey Point Units 6 and 7 qualify as the

FLORIDA PUBLIC SERVICE COMMISSION

7

1       siting, design, licensing, and construction of the

2       nuclear power plant as contemplated by Section 366.93,

3       Florida Statutes?

4                 Staff recommends that the Commission find that

5       FPL's activities related to the Turkey Point 6 and

6       7 qualify as siting, design, licensing, and construction

7       of the nuclear power plant as contemplated by Section

8       366.93, Florida Statutes, because these activities

9       satisfy the statutory definition of preconstruction

10       costs.

11                 CHAIRMAN GRAHAM:  Commissioner Brown?

12                 COMMISSIONER BROWN:  Thank you, Mr. Chairman.

13                 Mr. Young, we discussed this in our briefing

14       regarding whether the statute or the rule or PSC-11

15       order -- sorry -- Order PSC-11-0095, whether it

16       specifically calls for intent.  Can you elaborate on

17       that?

18                 MR. YOUNG:  Yes, ma'am.  The statute -- the

19       order which interprets the statute and the rule stated

20       that the company -- as long as the utility is, as long

21       as the utility demonstrates the intent to build the

22       nuclear power plant, then they are -- they should --

23       they satisfied -- they could -- and actually be --

24       excuse me -- and engaging in, as stated in the statute,

25       the siting, licensing, designing, construction -- or

FLORIDA PUBLIC SERVICE COMMISSION

8

1       construction, they meet the intent requirement of the

2       order, which interpret -- the final order, which

3       interprets the statute and the rule.  Excuse me.

4                 COMMISSIONER BROWN:  So then is it necessary

5       under the statute or rule that a final decision to

6       actually construct a nuclear plant be made prior to

7       allowing recovery?

8                 MR. YOUNG:  No.

9                 COMMISSIONER BROWN:  Thank you.

10                 MR. YOUNG:  But I would, I would note that per

11       the final order, which -- per your final order, which

12       you interpreted -- which interprets the statute and the

13       rule, calls for intent.  But, as stated, if the company

14       is engaging in one of the activities, engaging in the

15       siting, licensing, construction, or designing of the

16       nuclear power plant, they meet the requirement, the

17       intent requirement of your order.

18                 COMMISSIONER BROWN:  Does any other Staff

19       member have additional comments on that?

20                 CHAIRMAN GRAHAM:  Commissioner Brisé.

21                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

22                 I think part of the two questions that I had

23       were posed.  Obviously one of the biggest issues here is

24       the whole question of intent as raised by some of the

25       Intervenors.  And I'm going to read the statute and sort

FLORIDA PUBLIC SERVICE COMMISSION

9

1       of see if my understanding is accurate of what I think

2       it says.

3                 366.93(6), "If the utility elects not to

4       complete or is precluded from completing construction of

5       the nuclear power plant, including new, expanded, or

6       relocated electrical transmission lines or facilities

7       necessary thereto, or of the integrated gasification

8       combined cycle power plant, the utility shall" -- it

9       doesn't say may; right?

10                 MR. YOUNG:  Yes, sir.

11                 COMMISSIONER BRISÉ:  "Shall be allowed to

12       recover all prudent preconstruction and construction

13       costs incurred following the Commission's issuance of a

14       final order granting a determination of need for that

15       power plant."  I want to make sure that we, for the

16       record, issued a determination of need on this one.

17                 MR. YOUNG:  Yes, we did issue a determination

18       of need.

19                 COMMISSIONER BRISÉ:  Okay.

20                 MR. YOUNG:  For both utilities.

21                 COMMISSIONER BRISÉ:  For both utilities.

22                 "Determination of need for the nuclear power

23       plant and electrical transmission lines and facilities

24       necessary thereto, or for the integrated gasification

25       combined cycle power plant, the utility shall recover

FLORIDA PUBLIC SERVICE COMMISSION

10

1       such costs through the capacity cost recovery clause

2       over a period equal to the period during which the costs

3       were incurred, or five years, whichever is greater.  The

4       unrecovered balance during that period will accrue

5       interest at the utility's weighted average cost of

6       capital as reported in the Commission's earnings

7       surveillance reporting requirement for that year."

8                 So if I understand that properly, the statute

9       provides a very broad latitude as to what is defined

10       as -- what needs to be done in order for the

11       construction of the ultimate plant.

12                 MR. YOUNG:  Yes, sir.

13                 COMMISSIONER BRISÉ:  So therefore any activity

14       that is incurred that is forward progress towards the

15       end of building a plant would be considered prudent,

16       providing that the numbers reflect prudency?

17                 MR. YOUNG:  Yes, sir.  And that's the way

18       Staff has interpreted it in terms of any activity going

19       towards ultimate -- going towards construction of the

20       plant, they meet the intent requirement of the statute

21       as interpreted by the rule and as you stated in your

22       order.

23                 COMMISSIONER BRISÉ:  All right.  And

24       considering Order 11-00095-FOF-EI, many of the

25       Intervenors looked at the language intent as part of

FLORIDA PUBLIC SERVICE COMMISSION

11

1       that order and have based the questions about intent on,

2       on that order.  My understanding of that language is

3       that as long as the utility continues to engage in

4       activities that fall under siting, design, licensing,

5       and construction, then the utility is demonstrating the

6       necessary intent to meet the requirements under that

7       statute.

8                 Is that, for lack of a better term, the intent

9       of Staff when it looked at the statute and then made its

10       own interpretation with the order?

11                 MR. YOUNG:  Yes, sir.  Absolutely.  That was

12       the intent.

13                 COMMISSIONER BRISÉ:  Thank you very much.

14                 CHAIRMAN GRAHAM:  Commissioner Balbis.

15                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

16       And thank you, Commissioner Brisé and Brown.  I agree

17       with all of your statements.

18                 And I just -- I want to, for the record, kind

19       of state where I'm coming from on this and what my

20       thought process is associated with this, this issue and

21       other issues.

22                 Most of the parties repeated an assertion that

23       FPL and Progress are merely, quote, pursuing an option

24       to construct the nuclear facilities, and I agree with

25       that assertion.  In fact, numerous witnesses, including

FLORIDA PUBLIC SERVICE COMMISSION

12

1       Florida Power & Light's CEO and president, Mr. Olivera,

2       indicated that is exactly what they are doing.  The

3       requirement of Section 366.93 of the Florida Statutes

4       provides again, as Commissioner Brisé indicated, the

5       cost recovery for these utilities engaged in the siting,

6       design, et cetera.

7                 Additionally, the statute required that we

8       develop a rule establishing a recovery mechanism, and

9       that the utility shall report to the Commission actual

10       and budgeted costs for the facilities.  And we developed

11       that rule and required that they also file a detailed

12       analysis for the long-term feasibility of completing the

13       project, and that we shall consider that in determining

14       the reasonableness and prudency of these costs and

15       approving the cost recovery factor.

16                 So, using my logic, if at any time the

17       completion of the project is infeasible, the Commission

18       can determine that the costs related to continuing with

19       the project after the finding of infeasibility could be

20       imprudent.  So I'm not uncomfortable with the term

21       pursuing an option of constructing the facility.  I

22       would expect that the utility and this Commission would

23       continue to monitor whether or not this project is

24       infeasible from a long-term standpoint.  And I think

25       that the making of an irrevocable decision at this time

FLORIDA PUBLIC SERVICE COMMISSION

13

1       on a project of this magnitude may not be reasonable,

2       considering the regulatory, technical, and other factors

3       that are, that are changing.

4                 So, again, I'm comfortable with pursuing an

5       option.  I think that follows the intent.  I think the

6       fact that we require long-term feasibility analysis

7       annually determine that we are monitoring this and that

8       the utilities are monitoring this.  However, given that

9       the project continues to be cost-effective and feasible,

10       the utilities should continue to move forward with these

11       projects and obtaining the COL for these projects.

12                 So I just wanted to get that in for the record

13       and -- because that assertion is repeated throughout

14       numerous issues that they're pursuing an option.  And I

15       agree with the parties; however, I feel that the

16       long-term feasibility analyses that are done indicate

17       that we are monitoring this, the utilities are

18       monitoring this, and making sure that an irrevocable,

19       irrevocable decision is not made at this time.

20                 So thank you.

21                 CHAIRMAN GRAHAM:  Commissioner Edgar.

22                 COMMISSIONER EDGAR:  Thank you.

23                 A question for Mr. Young.  In your response to

24       Commissioner Brisé a few moments ago, you said that

25       Progress -- the position of Staff is that Progress met

FLORIDA PUBLIC SERVICE COMMISSION

14

1       the intent requirement of the statute.  Where in the

2       statute are you referring to as the intent requirement

3       of the statute?

4                 MR. YOUNG:  If I said that, I misspoke.  I

5       said -- I meant to say that FPL is meeting the intent

6       requirement of the order, which -- your final order,

7       which interprets the statute and the rule, your rule,

8       your rule and the Florida Statutes.

9                 COMMISSIONER EDGAR:  I appreciate that, that

10       clarification.

11                 MR. YOUNG:  Yes.

12                 COMMISSIONER EDGAR:  That's more in keeping

13       with my understanding of the statute, the order --

14                 MR. YOUNG:  Yes.  I'm sorry.

15                 COMMISSIONER EDGAR:  -- and the discussions

16       that we've had previously though.  So thank you for

17       that.

18                 And, Mr. Chairman, when we come to the point,

19       I do have a question on Issue 1.  I was a little slow on

20       the -- but at whatever point is best.

21                 (Laughter.)

22                 CHAIRMAN GRAHAM:  Sure.

23                 Commissioner Brown.

24                 COMMISSIONER BROWN:  To close up this issue, I

25       just would like to add a few comments.  I believe -- and

FLORIDA PUBLIC SERVICE COMMISSION

15

1       to address that option creation approach, I believe

2       Florida Power & Light has actively pursued and obtained

3       the licenses and approvals necessary to construct and

4       operate Turkey Point 6 and 7.  I also believe it's

5       pursued other preconstruction activities that show an

6       intent, so to speak, to pursue the development of these

7       plants.  I believe it has shown a risk mitigate -- risk

8       mitigating approach that allows for progress of the

9       project, while not necessarily committing additional

10       sums of money that are not essential at this stage, and

11       I would support the Staff recommendation on Issue 2.

12                 CHAIRMAN GRAHAM:  Commissioner Brisé.

13                 COMMISSIONER BRISÉ:  Thank you.  Thank you,

14       Mr. Chairman.

15                 I have one question.  Would there actually be

16       a cost difference to ratepayers if the utility had

17       conducted more of these preconstruction activities

18       simultaneously?

19                 MR. BREMAN:  I think Issue 2 -- I'm Jim

20       Breman.  I think Issue 2 actually goes to the new build

21       project.  FPL is not pursuing simultaneous activities

22       because it is in the permitting phase.  So whenever you

23       do things simultaneously, it's possible to incur more

24       costs during that shorter time frame than you otherwise

25       would incur, but the question is unresolved whether on a

FLORIDA PUBLIC SERVICE COMMISSION

16

1       total basis you would have incurred a total of more

2       costs.  That analysis that you're asking about with

3       respect to Turkey Point 6 and 7 is not in the record.

4                 COMMISSIONER BRISÉ:  Okay.  Thank you.  And

5       I'll make my comments with respect to where I am on this

6       issue.

7                 I find that the, that the utility has done

8       what the statute has asked for.  And on the whole notion

9       of the option, I think that the statute, the way it's

10       written, contemplates the option.  And I think, as

11       Commissioner Balbis expressed, that we wouldn't

12       necessarily want a utility to be locked in and

13       ultimately be in a position where it's not favorable to

14       the consumer to go through with the project if in the

15       long run it just doesn't make sense.

16                 So, with that, I am very comfortable with the

17       Staff recommendation.  I actually commend Staff for, for

18       providing such a good recommendation.  And I'm also

19       thinking about the impact of going opposite the Staff

20       recommendation on this issue, because then it sort of

21       flips the regulatory compact from my perspective on its

22       head.  If, if the statute says that this is allowed and

23       then we then turn around and say that this is not

24       allowed, then from, from those who are thinking about

25       investing here in our state with respect to, to our

FLORIDA PUBLIC SERVICE COMMISSION

17

1       utilities, then it damages, from my perspective, the

2       regulatory environment, which ultimately will end up

3       costing the consumer a whole lot more than we are --

4       than following what, what the statute lays out.  And so

5       that's, that's my take on, on this issue.

6                 CHAIRMAN GRAHAM:  Okay.  Let's go back to

7       Issue Number 1.

8                 Commissioner Edgar.

9                 COMMISSIONER EDGAR:  Thank you.

10                 I realize that in Issue 1 we, from a pure

11       dollar perspective we are dealing with numbers

12       significantly smaller than in many of the other issues.

13       But yet I can't help but recognize that in many, many,

14       many dockets on other issues over the years we spent a

15       great deal of time parsing, as we should, parsing

16       through rate case expense and comparisons and comparable

17       treatments.  And so I'm wondering if the Staff could

18       walk me through a little bit the thought process for the

19       recommendation on rate case expense for recovery in this

20       issue and how this treatment compares with the way we

21       have addressed rate case expense in other dockets.

22                 MR. BREMAN:  Commissioner, when I looked at

23       this issue, I looked at the statute.  The definition in

24       the statute for cost is a nonexclusive listing.  They

25       give an example of cost.  So the definition of cost is a

FLORIDA PUBLIC SERVICE COMMISSION

18

1       little bit wide open.  It's kind of undefined.

2                 So then we looked at -- then I looked at

3       whether or not this cost was appropriate.  And this cost

4       is not, based on my analysis, for personnel appearing

5       before you that are under employment with FPL on a

6       full-time basis.  Those, those would be a base rate

7       event.  Instead, I found or have the opinion that these

8       costs are for expert witnesses that come before you.

9       And to the extent that those expert witnesses and

10       independents of those expert witnesses can be presented

11       to you, I think that's a benefit to the ratepayers.

12                 So that's the way I look at it, is there's no

13       prohibition from recovering the costs.  These are the

14       same type of costs that you would probably consider in a

15       base rate proceeding where there's expert witnesses

16       coming before you, and those rate case type expenses

17       would then be considered and addressed, whether or not

18       they're fully recovered.

19                 Rate cases, my understanding, and it's been a

20       few years since I've played in one, is that those rate

21       case expenses are large, and especially on a smaller

22       utility it can dominate what the outcome is.  And, as

23       you said, these dollars aren't significant.  And to the

24       extent that these are separate expenses from base rate

25       expenses, I feel fairly comfortable that the right

FLORIDA PUBLIC SERVICE COMMISSION

19

1       regulatory policy is being implemented.

2                 COMMISSIONER EDGAR:  Clarification.  I did not

3       say that these totals are not significant.  I said that

4       they are --

5                 MR. BREMAN:  Understood.

6                 COMMISSIONER EDGAR:  -- small numbers in

7       comparison to the other items that we are dealing with

8       in this case.  Clearly anything --

9                 MR. BREMAN:  My response was whether or not

10       the amount would change the factor.

11                 COMMISSIONER EDGAR:  Is the treatment that the

12       Staff has used in this recommendation for rate case

13       expense -- witness -- witnesses and witness support

14       costs primarily comparable to the treatment that we have

15       used in the past for other cost recovery clause

16       processing?

17                 MR. BREMAN:  I think other clauses are

18       different, Commissioner.  I think like, for example,

19       you're going to have the fuel clause in November, and

20       those witnesses are primarily full-time employees of the

21       company.  And so that's the difference.

22                 COMMISSIONER EDGAR:  Such that those costs

23       would be in rate base.

24                 MR. BREMAN:  Those would be rate base.  That's

25       the significant difference in my mind.

FLORIDA PUBLIC SERVICE COMMISSION

20

1                 COMMISSIONER EDGAR:  Have we had -- to your

2       knowledge, have we had expert witnesses testify in other

3       clause recovery proceedings in the past?  I think

4       probably, but --

5                 MR. BREMAN:  Probably they have.

6                 COMMISSIONER EDGAR:  And have those costs been

7       flowed through as rate case expense?

8                 MR. BREMAN:  I do not know.

9                 COMMISSIONER EDGAR:  Nor do I.

10                 Does anybody know?  We don't know.

11                 Have we in past, realizing that this is still

12       a relatively new statute and rule that we are

13       implementing here, have we flowed through, approved for

14       cost recovery the cost of expert witnesses in this

15       clause in the past?

16                 MR. BREMAN:  Yes.

17                 COMMISSIONER EDGAR:  All right.  Thank you.

18                 CHAIRMAN GRAHAM:  Anyone else on Issue 1?

19                 Okay.  How about Issue 3, 4, 5?

20                 Commissioner Brown.

21                 COMMISSIONER BROWN:  Thank you.  And this is

22       for Issue 3.  I have a few questions on that.

23                 CHAIRMAN GRAHAM:  Who wants to take us into

24       Issue 3?

25                 COMMISSIONER BROWN:  Issue 3.  Staff,

FLORIDA PUBLIC SERVICE COMMISSION

21

1       regarding sunk costs, have we ever added sunk costs to

2       the cost-effective analysis?

3                 MR. GARL:  No, Commissioner.  Ever since the

4       need determination and each one of the successive

5       nuclear cost recovery clause proceedings, sunk cost is

6       hindsight, it's what's already been spent, where the

7       feasibility analysis looks at from this point forward is

8       it feasible to continue with the project.

9                 COMMISSIONER BROWN:  Can you go through the --

10       for purposes of our interest, can you go through the

11       economic principle behind this?

12                 MR. GARL:  Yes.  Well, it's just as I said,

13       if -- when you're proceeding from point A to point B,

14       anything that happened prior to point A, it's illogical

15       to consider that when you're looking at where we are

16       today and is it feasible to continue on to completion.

17                 I think one of the FPL witnesses added that in

18       addition to a well -- well-recognized principle in not

19       including sunk costs in a feasibility analysis, it also

20       mentions it in the rule and the Commission order that

21       we're looking forward to completion rather than what

22       happened in the past.  Not to say that sunk costs should

23       be totally ignored.  The Commission order specifically

24       says that sunk costs should be recognized, and they have

25       indeed done that.

FLORIDA PUBLIC SERVICE COMMISSION

22

1                 COMMISSIONER BROWN:  Okay.  Regarding the

2       Westinghouse AP1000 design, is FPL committed to that

3       design?

4                 MR. GARL:  Yes.

5                 COMMISSIONER BROWN:  Okay.  And it was stated

6       in their application, in the application?

7                 MR. GARL:  Yes, their application to the

8       Nuclear Regulatory Commission.

9                 COMMISSIONER BROWN:  In the staff

10       recommendation it suggests the design change rulemaking

11       would be -- implement -- finalized in September.  Has

12       that occurred?

13                 MR. GARL:  Yes.  At -- later on in the hearing

14       one of the Commissioners asked if that has happened, and

15       the answer was yes.

16                 COMMISSIONER BROWN:  Okay.

17                 MR. GARL:  It's in the process and expected to

18       be finalized early next year.

19                 COMMISSIONER BROWN:  Okay.  Just another

20       question, if you don't --

21                 CHAIRMAN GRAHAM:  Sure.

22                 COMMISSIONER BROWN:  I know the Intervenors

23       expressed doubts regarding the new nuclear units as a

24       result of the events that occurred at Fukushima nuclear

25       plant.  However, I believe it was FPL Witness Diaz that

FLORIDA PUBLIC SERVICE COMMISSION

23

1       provided some convincing testimony at the hearing

2       surrounding these concerns.

3                 I wanted to take this opportunity, Staff, to

4       ask you all to address how the Commission monitors

5       nuclear project controls within the confines of the

6       record.

7                 MR. GARL:  You're referring to his testimony?

8                 COMMISSIONER BROWN:  Uh-huh.

9                 MR. GARL:  Yes.  On page 23 we've quoted that,

10       Witness Diaz saying, "The current generation of nuclear

11       power plant designs that are the subject of COLAs, such

12       as the Westinghouse AP1000 design that is referenced in

13       the Turkey Point Units 6 and 7 COLA, are more robust

14       than the existing plants in the areas shown to be

15       compromised by the earthquake/tsunami combination in

16       Japan."

17                 COMMISSIONER BROWN:  I guess my question,

18       Mr. Garl, is how does the Commission monitor nuclear

19       project controls, cost activities as it relates to

20       Turkey Point 6 and 7?

21                 MR. GARL:  By this, this very process here,

22       the annual nuclear cost recovery proceeding, where the

23       utilities are required to provide information on updated

24       costs, cost-effectiveness, an overall feasibility

25       analysis, which presents to the Commission on an annual

FLORIDA PUBLIC SERVICE COMMISSION

24

1       basis what the project looks like.

2                 COMMISSIONER BROWN:  And I just wanted --

3                 MR. BREMAN:  Excuse me, Commissioner.  You

4       might be actually asking a question with respect to

5       Issue 6 or subsequent issues having to do with project

6       management, oversight controls.

7                 COMMISSIONER BROWN:  Uh-huh.

8                 MR. BREMAN:  To the extent that the utility is

9       engaged in monitoring things at the NRC and is

10       responsive to the NRC, how much time they take to look

11       at the NRC, we have a management audit team that goes in

12       and monitors the utility's activities and then reports

13       to you and provides testimony on their findings, and

14       that's how we do that.

15                 COMMISSIONER BROWN:  And Mr. Breman

16       answered -- really, that was exactly what I was trying

17       to get at.  I think the role that the Commission plays

18       is important as it monitors cost activities at the new

19       nuclear sites and existing sites, and I would like to

20       reemphasize this point for purposes of this issue, so.

21                 CHAIRMAN GRAHAM:  Commissioner Balbis.

22                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

23                 I'd like to focus on two small points

24       concerning this issue.  One is the updated fuel forecast

25       for Florida Power & Light, and that none of the parties

FLORIDA PUBLIC SERVICE COMMISSION

25

1       really contested their forecast, but just pointed out

2       the fact that there's been a reduction in the benefits

3       of this project.  And I just want Staff to confirm that

4       with the updated fuel forecast and the lower, especially

5       natural gas fuel prices, that the Florida Power & Light

6       projects are still cost-effective.

7                 MR. GARL:  Yes, Commissioner.  The analysis,

8       the cost-effectiveness analysis that Florida Power &

9       Light did shows the results of those lower gas prices as

10       compared to last year.  The -- not only the

11       cost-effectiveness has dropped slightly, but also the

12       amount of the savings over the life of the project has

13       been reduced.  So they did consider that cost reduction

14       of natural gas in their analysis.

15                 COMMISSIONER BALBIS:  And even with those

16       reductions in benefits and natural gas prices, again,

17       the projects are still cost-effective.

18                 MR. GARL:  Yes, sir.

19                 COMMISSIONER BALBIS:  And my personal

20       knowledge and information contained within the record

21       indicates there are several ongoing issues with natural

22       gas that could provide upward price pressure to make the

23       project even more cost-effective.

24                 The other point I wanted to make is associated

25       with the sunk costs.  There was a lot of discussion

FLORIDA PUBLIC SERVICE COMMISSION

26

1       during the hearing on sunk costs, and I believe it was

2       FPL Witness Sims that -- or Sim -- that after providing

3       several caveats that he may be violating traditional

4       economic analysis, that even including sunk costs in

5       this project, that it was still cost-effective.  Is that

6       correct?

7                 MR. GARL:  That is correct.  Yes, sir.

8                 COMMISSIONER BALBIS:  Thank you.  I have no

9       further comments.

10                 CHAIRMAN GRAHAM:  Commissioner Brisé.

11                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

12                 I want to go back to regulatory feasibility.

13       What impact or -- yeah, what impact will the Vogtle

14       plant in Georgia have as an indicator with respect to

15       the AP1000 moving forward?

16                 MR. GARL:  The decision the Nuclear Regulatory

17       Commission will issue in the case of Plant Vogtle is the

18       dam letting go.  And once they approve the latest design

19       of the AP1000, followed by approval of the Plant Vogtle

20       project, that's what Florida Power & Light states that

21       they are looking for as the, the litmus test of what the

22       NRC is doing.  So that'll be a big, a big move once they

23       approve the Plant Vogtle project.

24                 COMMISSIONER BRISÉ:  Okay.  And from, from

25       what you -- or from -- I'm sure you all as Staff are

FLORIDA PUBLIC SERVICE COMMISSION

27

1       also monitoring that.  Are things relatively on track

2       there?

3                 MR. GARL:  Yes.  They -- as we say, sometime

4       next year, from all we've seen, that project should

5       receive approval as well.

6                 COMMISSIONER BRISÉ:  Okay.  All right.  I

7       thought they wanted maybe to add something.

8                 MR. BREMAN:  Commissioner, I just want to

9       point out something.  We monitor things that aren't

10       necessarily entered into the record because it's common

11       knowledge.

12                 COMMISSIONER BRISÉ:  Understood.

13                 MR. BREMAN:  The information that we're

14       referring to is basically reading information we get

15       directly from the NRC through e-mail subscription and

16       the press.  So there might be some discussion on the

17       Vogtle site about what we know is going on there that is

18       not squarely within the four corners of the record.

19                 COMMISSIONER BRISÉ:  Thank you.

20                 CHAIRMAN GRAHAM:  Any other questions of Issue

21       3, or Issue 4 or 5?  3A?  Seeing none, I guess someone

22       makes -- Commissioner Brown.

23                 COMMISSIONER BROWN:  I did have a brief

24       comment on 3A.  I was waiting.  If any of the

25       Commissioners had a question, I'll defer to you all.

FLORIDA PUBLIC SERVICE COMMISSION

28

1                 CHAIRMAN GRAHAM:  No.

2                 COMMISSIONER BROWN:  Okay.  I'll just go ahead

3       with my comment.

4                 I believe that there's value in obtaining the

5       COL for Turkey Point 6 and 7.  It's projected to save

6       customers billions of dollars in fuel and environmental

7       costs under a wide range of compliance cost scenarios

8       that were addressed in the Staff recommendation, in

9       addition to reducing our reliance on fossil fuels,

10       providing fuel diversity, and reducing emissions.  And I

11       think Florida Power & Light's decision to continue

12       pursuing the COL is, in my opinion, well reasoned, and I

13       would support Staff recommendation.

14                 CHAIRMAN GRAHAM:  Okay.  We need a motion to

15       approve Staff recommendation on Issues 1 through 5.

16                 Commissioner Edgar.

17                 COMMISSIONER EDGAR:  Mr. Chairman, I move

18       approval of the Staff recommendation on Issues 1, 2, 3,

19       3A, 4, and 5, 3 as amended by the oral modification, and

20       in recognition that Issues 4 and 5 are basically

21       subsumed within the discussion that we've had on 3.

22                 COMMISSIONER BALBIS:  Second.

23                 CHAIRMAN GRAHAM:  It's been moved and

24       seconded, all that stuff that she just said.  Any

25       further discussion?

FLORIDA PUBLIC SERVICE COMMISSION

29

1                 Seeing none, all in favor, say aye.

2                 (Affirmative response.)

3                 Any opposed?

4                 (No response.)

5                 By your action you've approved 1 through 5.

6                 Okay.  6 through 10.  Start with the small

7       ones and go up.  Questions on 6 or 7?

8                 We talked a little bit about 6.  Did you have

9       anything else to add to that?  Because it overlapped

10       with the questions that Commissioner Brown had on 3.

11                 MR. BREMAN:  No, sir.  That was all I wanted

12       to do was clarify the one question.

13                 CHAIRMAN GRAHAM:  All right.  Can I get a

14       motion to approve Staff's recommendations on Issues

15       6 through 10?

16                 Commissioner Edgar.

17                 COMMISSIONER EDGAR:  Move Staff recommendation

18       on Items 6, 7, 8, 9, 10, including the oral modification

19       on Issue 8.

20                 COMMISSIONER BRISÉ:  Second.

21                 CHAIRMAN GRAHAM:  It's been moved and

22       seconded, Staff recommendation on Issues 6 through 10,

23       including the oral modification on Issue 8.

24                 Any further discussion?

25                 Seeing -- Commissioner Brisé.

FLORIDA PUBLIC SERVICE COMMISSION

30

1                 COMMISSIONER BRISÉ:  No.  I failed to ask a

2       question on Issue 10.

3                 CHAIRMAN GRAHAM:  That's all right.  Go ahead.

4                 COMMISSIONER BRISÉ:  So if we can sort of take

5       a step backwards.  If we can have a discussion on the

6       breakeven analysis versus the CPVRR approach and what

7       the benefits would be of a breakeven analysis and how it

8       may or may not be the best tool in this instance.

9                 MR. ELLIS:  A CPVRR approach uses two

10       competing resource plans -- in this instance, one with

11       the EPU project and one without -- and then compares the

12       total cost.  So it provides a total savings number that

13       you can therefore say with those assumptions of fuel and

14       environmental costs, it will have this amount of

15       savings.

16                 A breakeven analysis eliminates from the

17       equation the capital or construction costs associated

18       with the EPU project, and then takes that total sum and

19       divides it by the capacity it provides to provide a

20       number that represents the total cost at which the

21       projects for construction can go, above which it would

22       become not cost-effective.  So Staff is recommending in

23       this case the use of a CPVRR.  It's traditionally been

24       what we have used in most projects.

25                 And the breakeven analysis in this instance,

FLORIDA PUBLIC SERVICE COMMISSION

31

1       given that we are close to implementation, a partial

2       uprate has already been conducted on one unit, St. Lucie

3       2.  It's more, it's typically more useful to do a CPVRR

4       on those variety of costs.

5                 COMMISSIONER BRISÉ:  I'm going to -- sort of

6       forgive my ignorance, all right, for, for a quick

7       minute.

8                 The average person who runs a business, they

9       look at a breakeven analysis to determine whether

10       something is viable or not.  Can you describe to me or

11       explain to me why the breakeven analysis doesn't make

12       sense in a way that, you know, if I'm the guy who has

13       the, you know, I'm just trying to sell sodas or

14       something, understands that concept as to what are the

15       moving parts that prohibits the traditional breakeven

16       analysis not to work in this particular situation?

17                 MR. BREMAN:  Sure.  I looked at Phillip

18       Ellis's analysis, and I'd like to turn you to page 49,

19       Figure 10-1.  Sometimes when you get caught up in system

20       planning you focus on a methodology, and you have an

21       inherent understanding and it's kind of hard to explain

22       things.

23                 What you're asking is a simple question.

24       Breakeven in Figure 10-1 would be zero all the way

25       across.  The CPVRR tells you how much customer savings

FLORIDA PUBLIC SERVICE COMMISSION

32

1       occur, which is our charge here.  That's the difference.

2                 COMMISSIONER BRISÉ:  Thank you.

3                 CHAIRMAN GRAHAM:  Commissioner Balbis.

4                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

5                 And I just want to add another point and have

6       a small discussion on the, the need for separate

7       economic analysis on, on the two FPL sites.  And that's

8       one of the requests that the several Intervenors have

9       made is to look at the different plants and do an

10       economic analysis on each one.

11                 My question for Staff, has any new information

12       come to light that would warrant the separation and

13       warrant a separate economic analysis on the two plant

14       sites since the need determination process?

15                 MR. ELLIS:  No.  In this instance one of the

16       main items cited is the number of unit years that the

17       St. Lucie plant will run more so than the Turkey plant

18       site.  That was information that was known at the need

19       determination in each NCRC hearing.

20                 COMMISSIONER BALBIS:  Okay.  So during the

21       need determination process the two or the four separate

22       licensure expiration dates were known.  Those have not

23       changed.  So nothing has changed that would warrant the

24       separation; is that correct?

25                 MR. ELLIS:  That would be correct.  Yes.

FLORIDA PUBLIC SERVICE COMMISSION

33

1                 COMMISSIONER BALBIS:  Okay.  Thank you.  I

2       have no further questions.

3                 CHAIRMAN GRAHAM:  All right.  We have a motion

4       on the floor.  It has been moved and seconded, the

5       Staff recommended -- to approve Staff recommendations on

6       Issues 6 through 10, including the oral modification on

7       Issue 8.  If there's no other discussion, all in favor,

8       say aye.

9                 (Affirmative response.)

10                 Any opposed?

11                 (No response.)

12                 By your action, you've approved those issues.

13                 Let's look at Issues 11 through 14.

14                 Commissioner Brown.

15                 COMMISSIONER BROWN:  Thank you, Mr. Chairman.

16                 And there was a lot of discussion during the

17       hearing regarding the fast tracking, the expedited.  I

18       know that we -- in the recommendation it talks about

19       those terms can be used interchangeably.  The question

20       for Staff, was the concept of fast tracking presented to

21       the Commission during the need determination, or

22       discussed?

23                 MR. BREMAN:  The definition of fast track was

24       not presented to the Commission in the need

25       determination, based on my reading of the order.  The

FLORIDA PUBLIC SERVICE COMMISSION

34

1       transcript of the proceeding and the discovery of the

2       need proceeding was not made part of this record.  So

3       the only thing I had to rely on was the

4       characterizations that the various witnesses had and the

5       order itself.

6                 What I found was there was a need in 2012/2013

7       time frame, and that was clearly expressed in the order.

8       And FPL has adhered to putting or achieving that target

9       in-service date with their approach to the EPU project.

10                 FPL uses a different term rather than fast

11       track.  They use the word expedited.  It's a difference

12       without a distinction in this case, because whatever

13       management policy FPL implemented has consistently tried

14       to achieve the 2013 -- 2012/2013 in-service dates.

15                 COMMISSIONER BROWN:  So without Florida Power

16       & Light's efforts to expedite, would they be able to

17       achieve that 2012/2013 in-service date?

18                 MR. BREMAN:  No, ma'am.  There's no dispute

19       that had a sequential approach been implemented, the

20       in-service date would not have made the 2012/2013 date.

21       It would have lasted at least four years longer, and

22       customer savings would have declined somewhere in the

23       neighborhood of $800 million.

24                 COMMISSIONER BROWN:  That's the second

25       question.  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

35

1                 I have one more small question regarding FPL's

2       efforts for recovering work stoppage costs.  We

3       discussed this.  I just wanted to make sure that the

4       Commission Staff is monitoring and will continue to

5       monitor recovery of work stoppage costs, including the

6       Seimens claim from third parties.

7                 MR. BREMAN:  We will.

8                 COMMISSIONER BROWN:  Okay.  Thank you.

9                 CHAIRMAN GRAHAM:  Commissioner Balbis.

10                 COMMISSIONER BALBIS:  Thank you, Mr. Chair.

11                 I just have a quick comment and a question for

12       Staff.  One of the risks associated with fast tracking a

13       project is sometimes equipment procurement.  Long lead

14       time items are purchased prior to design being completed

15       to a phase where you're more certain.  The fast tracking

16       or expediting of this project, did it result in Florida

17       Power & Light procuring equipment or other, or other --

18       or incurring other costs that have been stranded or will

19       not be recovered?

20                 MR. BREMAN:  No.

21                 COMMISSIONER BALBIS:  Thank you.  I have no

22       other questions.

23                 CHAIRMAN GRAHAM:  Commissioner Brisé.

24                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

25                 On page 63, and this is from Witness Jacobs,

FLORIDA PUBLIC SERVICE COMMISSION

36

1       he asserted that FPL failed to perform a breakeven

2       analysis and did not have a good handle on the ultimate

3       costs and was slow to recognize and take into account

4       early indications that its initial estimates were

5       inadequate.  He believed that these deficiencies

6       constitutes imprudence.  He generally ascribed the

7       imprudence to FPL employing a fast track approach.  Can

8       you explain or describe why that position is not

9       correct?  From your perspective obviously.

10                 MR. BREMAN:  Yes.  Some of the discussion

11       about fast track has already occurred, is you could not

12       have achieved the in-service date, so that it was

13       prudent or reasonable for the utility to try to do

14       something out of the ordinary.  So the question of fast

15       track is sort of taken off the table.

16                 I think the question you're going to is

17       whether or not FPL understood the full scope of the cost

18       estimate that it presented in the need case.  There is

19       no record evidence -- to answer that question, there was

20       no record evidence presented that FPL could have or

21       should have known the information that became

22       self-evident after they did their analysis in 2009 and

23       2010.  There was no demonstration or no, no

24       representation that FPL should have known that

25       information at the time of the original need

FLORIDA PUBLIC SERVICE COMMISSION

37

1       determination.  Essentially the best information they

2       had at the time was presented to you.  There's always

3       hindsight, Commissioners, and we always know more today

4       than we knew yesterday.

5                 COMMISSIONER BRISÉ:  That goes to a broader

6       question with respect to regulating in hindsight.  And

7       what is your thought process on that?  After we receive

8       information, after things have occurred based upon going

9       through the normal course and then to, and then take a

10       look back and want to address things that have already

11       been determined and agreed upon, what impact does that

12       have from your perspective on the regulation process?

13                 MR. BREMAN:  I think the regulation of this

14       clause is substantially a variance event, because we're

15       looking at the variance between the original forecast

16       and the one we have today.  So we're monitoring why the

17       prices changed, the prices of the project changed, and

18       we have better information.  And with that new

19       information, is continuing the project feasible?  And as

20       addressed in Issue 10, it was found feasible.

21                 COMMISSIONER BRISÉ:  Okay.  One last question.

22       As part of the last line of the recommendation, it says,

23       "Additionally, Staff recommends the Commission not adopt

24       OPC Witnesses Smith and Jacobs' breakeven analysis for

25       purposes of rate base."  And we haven't had much

FLORIDA PUBLIC SERVICE COMMISSION

38

1       discussion on that in terms of what would the mechanism

2       look like or what would the methodology look like in

3       using the breakeven analysis as part of setting rate

4       base.

5                 MR. BREMAN:  It's kind of hard to know

6       something when it's -- when the analysis is yet to be

7       presented to you.  OPC's testimony is that it should be

8       done when the project is completed.  So it's kind of

9       sight unseen you're being asked to agree to implement a

10       process, a formula, without knowing what it says.

11                 If I could, and I, and I know I did this

12       already, but the chart on page 49, or the Figure of 10.1

13       on page 49, and I might sound like I'm testifying

14       because you asked me a policy question, and I'll try to,

15       I'll try to address it from a policy basis.

16                 COMMISSIONER BRISÉ:  Sure.

17                 MR. BREMAN:  And I'm not a sworn witness, so.

18       One of the things that I didn't put in the

19       recommendation analysis, because I tried to stay within

20       the four corners of the transcript, is if you did

21       implement that as a regulatory theory, the utility would

22       incur -- would actually be encouraged to incur capital

23       expenditures that use up all of the fuel savings that

24       you see in this chart.  And that is another regulatory

25       concern.  If you're going to do something like this,

FLORIDA PUBLIC SERVICE COMMISSION

39

1       like set up a regulatory backstop, you need to do it at

2       inception, and that testimony is in the record.  And I

3       agree with the concept that whatever performance

4       conditions you put on a utility, you need to put it on

5       early in the project, not two years before it's

6       completed.

7                 COMMISSIONER BRISÉ:  So, therefore, from your

8       perspective, if we followed that path, it would have a

9       negative impact on the consumer ultimately?

10                 MR. BREMAN:  It's possible.  Because, like I

11       said, it might eat up the fuel savings.

12                 COMMISSIONER BRISÉ:  Okay.  Thank you.

13                 CHAIRMAN GRAHAM:  Commissioner Balbis.

14                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

15                 I wanted to follow up on a good point and

16       question that Commissioner Brisé asked, and that's

17       associated with the initial cost estimates.  And this is

18       something that I discussed with Staff during our

19       briefing, but in essence, the, the lower estimates at

20       the time of the need determination process, did they

21       skew the feasibility of the project in the need

22       determination process?

23                 MR. BREMAN:  No.

24                 COMMISSIONER BALBIS:  So, in other words, the

25       updated information that we now know is more accurate,

FLORIDA PUBLIC SERVICE COMMISSION

40

1       the project is still feasible and cost-effective;

2       correct?

3                 MR. BREMAN:  Yes.

4                 COMMISSIONER BALBIS:  Okay.  Thank you.

5                 CHAIRMAN GRAHAM:  Okay.  Anything else between

6       11 and 14?

7                 Commissioner Brown.

8                 COMMISSIONER BROWN:  A quick question on Issue

9       12.

10                 CHAIRMAN GRAHAM:  Sure.

11                 COMMISSIONER BROWN:  Can Staff please explain

12       the increase incurred in licensing costs in the amount

13       of 7.9 million for the year-end 2009, and the reason

14       behind it?

15                 MR. BREMAN:  The increase in licensing costs

16       as I saw it was an increase -- was responsive to a

17       projected increase in activity level.  So they'd be

18       responding to NRC data requests and such in trying to

19       achieve their license renewal approvals by the target

20       dates that they need in order to turn Turkey Point Units

21       3 and 4 back online and also complete the uprate for

22       St. Lucie 1 and 2.

23                 COMMISSIONER BROWN:  Which Staff deems is

24       reasonable given the time frame of the project?

25                 MR. BREMAN:  Yes, ma'am.  For projection

FLORIDA PUBLIC SERVICE COMMISSION

41

1       purposes that is very reasonable.

2                 COMMISSIONER BROWN:  Thank you.

3                 CHAIRMAN GRAHAM:  Can I get a motion?

4                 Commissioner Edgar.

5                 COMMISSIONER EDGAR:  Mr. Chairman, pursuant to

6       our discussion, I move the Staff recommendation on Items

7       11 and 14 and 12 and 13 as modified.

8                 COMMISSIONER BALBIS:  Second.

9                 CHAIRMAN GRAHAM:  It has been moved and

10       seconded Staff recommendations on Items 11, 12, 13, 14,

11       with the modifications on 12 and 13.

12                 Any further discussion?

13                 Seeing none, all in favor, say aye.

14                 (Affirmative response.)

15                 Any opposed?

16                 (No response.)

17                 By your action, you've approved Staff

18       recommendation on those items.

19                 Item 15.  Staff, let's just get started with

20       that one.

21                 MR. DOWDS:  Commissioners, Dave Dowds with

22       staff.

23                 Issue 15A pertains to whether or not FPL

24       willfully withheld information from the Commission

25       regarding the EPU project's estimated total project

FLORIDA PUBLIC SERVICE COMMISSION

42

1       completed costs and the EPU project's feasibility study

2       that the Commission required to make an informed

3       decision at the September 2009 NCRC hearings.  Staff

4       recommends that the Commission find that FPL did not

5       willfully withhold EPU total project cost information

6       that was necessary for the Commission to make an

7       informed decision at the September 2009 hearings.

8                 Staff also recommends that FPL continue to

9       provide to the Commission validated, reliable updates of

10       total project cost estimates as they are available.

11                 And we're ready to answer any questions you

12       may have.

13                 CHAIRMAN GRAHAM:  15B.

14                 MR. YOUNG:  Commissioners, Keino Young.  By

15       your decision on 15A, 15 -- by your decision on 15A will

16       dictate how 15B and 15C is to go.

17                 CHAIRMAN GRAHAM:  Let's just go ahead and,

18       let's just talk us through 15B.

19                 MR. YOUNG:  Pardon me, sir?

20                 CHAIRMAN GRAHAM:  What are the options on 15B?

21                 MR. YOUNG:  If your decision on 15A is to find

22       FPL willfully withheld information, Staff recommends

23       that it be given an opportunity to bring forth a

24       recommendation at the November Agenda Conference as to

25       the next steps, including, but not limited to, should a

FLORIDA PUBLIC SERVICE COMMISSION

43

1       show cause be -- show cause proceeding be initiated or

2       whether a separate proceeding should be opened to

3       consider whether the utility was prudent and what costs

4       should be associated with that decision.

5                 CHAIRMAN GRAHAM:  Commissioners, I just, I

6       paused at this one because I know there was a lot of

7       allegations that came out last year about this, and we

8       spent a lot of time talking about it this year.  So I

9       just wanted to make sure that we are specifically

10       talking about this one on the record so we had something

11       to go back to.

12                 Any comments, concerns on -- wow.

13                 Commissioner Brisé.

14                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

15                 There was a lot of discussion about this at

16       hearing, before hearing, in the press and so forth and

17       so on about this notion about willfully withholding

18       information.  And let's talk about what willfully

19       withholding information means, what information is

20       actually needed, and how Staff arrived at its

21       recommendation to say that, you know, no, Staff

22       recommends that the Commission find that FPL did not

23       willfully withhold information concerning the estimated

24       capital and so forth.  So if you can walk us through how

25       you got to that point and willful and all of that.

FLORIDA PUBLIC SERVICE COMMISSION

44

1                 MR. DOWDS:  Yes, Commissioner.

2                 In the Staff analysis being on page 94, I

3       opted to parse the issue as phrased into three

4       components, because it's rather difficult addressing a

5       compound issue.

6                 The first one is whether willfully failed to

7       provide EPU updated estimates by the time of the

8       hearings.  And the first component I looked at was

9       willful withholding.  What does that mean?  And the

10       record is not a model of clarity on that aspect, but

11       there is no argument from FPL that they were -- they

12       consciously made the decision not to update the

13       witness's testimony, and they had good reasons, which

14       are addressed in my second portion, which is whether or

15       not the witness was required to update its feasibility

16       study and its EPU cost estimate.

17                 FPL -- obviously OPC and Intervenors generally

18       argue that FPL was so obligated.  However, there were

19       good reasons offered by FPL as to why it chose not to do

20       so; namely, that they were still fighting back with the

21       EPC, Bechtel, throughout most of 2009 and into early

22       2010 trying to determine the increased scope of the

23       project, the cost estimates, the reasonableness of

24       Bechtel's proposed man-hour estimates, which increased

25       significantly in the first quarter of 2009.

FLORIDA PUBLIC SERVICE COMMISSION

45

1                 And they -- and senior management of FPL was

2       not ready to sign off on any of these estimates.  And to

3       the extent that the Executive Steering Committee must

4       sign off on such proposals before they are released

5       publicly, they, it was -- they were not ready for prime

6       time, in the vernacular.

7                 Third was whether there was any information

8       that the Commission didn't have in the September 2009

9       hearings that it needed to make informed decisions.  The

10       key -- there were two sets of decisions that were made

11       at the hearing.  First was the reasonableness of the

12       2008 costs that have already been incurred and the '09

13       and '10 projections.  They had all the information they

14       needed in the record, and the fact that the total

15       project cost estimates was not updated had no bearing

16       whatsoever on that, and OPC Witness Jacobs basically

17       agreed with that.

18                 Second is whether or not the project remained

19       feasible.  Internally FPL did a, quote, sensitivity

20       analysis, unquote, around the July-ish, the July 2009

21       time frame wherein they essentially did some additional

22       calculations where they substituted the tentative

23       increased capital costs into the feasibility

24       calculations, and they didn't even include the increased

25       capacity, which was then known.  The results of that

FLORIDA PUBLIC SERVICE COMMISSION

46

1       analysis indicated that the project remained feasible,

2       and the OPC witness agreed this is the case.

3       Consequently, there was nothing really of necessity that

4       the witness needed to update his testimony.

5                 As such, we can't find anything that, that

6       constitutes willful withholding, because what was

7       withheld was not reliable and was probably appropriate

8       that it not be provided so that the Commissioners did

9       not have to address potentially down the road erroneous

10       information.

11                 COMMISSIONER BRISÉ:  Thank you.  So let me

12       make sure I got this right in my head.  All right?  So

13       you have information that, that was available, but it

14       hadn't gone through the normal vetting process that the

15       company would normally use before it provided that

16       information.  And that information, the updated

17       information would not have had an impact on the outcome

18       of, of what was needed for our processes.

19                 So, so with that in mind, yes, they withheld

20       the information because it was not ready, but it wasn't

21       to the level where that information would sort of skew

22       significantly the information that was presently

23       available at the Commission.  Is that about accurate?

24                 MR. DOWDS:  That's correct.

25                 COMMISSIONER BRISÉ:  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

47

1                 CHAIRMAN GRAHAM:  Commissioner Balbis.

2                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

3                 And to follow up again with Commissioner Brisé

4       and his comments, and thank you, Staff, for the

5       additional clarification on the recommendation that you

6       provided us.

7                 And I agree with Staff.  I believe Florida

8       Power & Light did withhold information, but they

9       withheld it because it wasn't validated, it hadn't gone

10       through the process for approval.  And when I

11       specifically asked the FPL witness Olivera as to whether

12       the information that was provided to the Commission went

13       through a similar vetting process, he testified that it,

14       that it was.  And this Commission needs accurate,

15       validated information in order to make decisions.  These

16       are large projects that are, that are constantly

17       changing information as fluid, and we have to be in a

18       process to receive validated information so that we can

19       make a decision.

20                 So then I focused on what does the rule

21       require, the statute require?  And it requires that a

22       detailed analysis, you know, may not put quotes around

23       detailed, but a detailed analysis be provided.  And what

24       I feel is a detailed analysis, it includes validated,

25       accurate information.  So I believe FPL did withhold

FLORIDA PUBLIC SERVICE COMMISSION

48

1       information, but they were right to do so because it was

2       not vetted and they were not in violation of Rule

3       25-6.0423.  Thank you.

4                 CHAIRMAN GRAHAM:  Commissioner Brown.

5                 COMMISSIONER BROWN:  Thank you.

6                 Can we just take a step back and go through

7       the formal vetting process and can you explain,

8       elaborate, again within the confines of the record?

9                 MR. DOWDS:  Certainly.  If I can point you to

10       page 93 of the Staff recommendation.  There's a very

11       telling quote from the hearing that was during

12       cross-examination of FPL Witness Stall, where he

13       basically described in detail what vetting amounts to.

14       And to kind of short-circuit for the moment, the process

15       he describes, he indicated was the same process that

16       they would use prior to being allowed to release to

17       external entities, such as the SEC or the NRC, let alone

18       this Commission, any potentially sensitive business

19       information.

20                 COMMISSIONER BROWN:  Okay.  And then you

21       had --

22                 MR. DOWDS:  Which I -- I'm sorry.

23                 COMMISSIONER BROWN:  Go ahead.

24                 MR. DOWDS:  Which I found telling, because

25       CEOs have a tendency to be a little antsy about signing

FLORIDA PUBLIC SERVICE COMMISSION

49

1       off on filings with the SEC.  And if they're using the

2       same processes here for filings with the Commission, it

3       tends to increase my comfort level.

4                 COMMISSIONER BROWN:  That's good.  Thank you.

5       And didn't OPC Witness Jacobs testify at the hearing

6       that the info -- that even with the information -- even

7       with -- if they had proposed an errata with the updated

8       information, the project would be still deemed

9       economically feasible?

10                 MR. DOWDS:  That's correct.

11                 COMMISSIONER BROWN:  Okay.  I'm comfortable

12       with Staff recommendation as well.

13                 CHAIRMAN GRAHAM:  Okay.  Do I get a motion

14       for -- Commissioner Balbis.

15                 COMMISSIONER BALBIS:  Mr. Chairman, I move

16       Staff's recommendation on Issue 15A.

17                 CHAIRMAN GRAHAM:  It's been moved and seconded

18       Staff recommendation on Issue 15A.  No further

19       discussion?

20                 All in favor, say aye.

21                 (Affirmative response.)

22                 Any opposed?

23                 (No response.)

24                 By your action, you've approved Staff on 15A.

25                 MR. YOUNG:  Mr. Chairman, by your decision to

FLORIDA PUBLIC SERVICE COMMISSION

50

1       approve Staff recommendation on 15A, Staff would note

2       that Issues 15B and 15C are now moot and don't need a

3       vote.

4                 CHAIRMAN GRAHAM:  As per Mr. Young, we are

5       scratching 15B and C.

6                 All right.  I think it's about a good time to

7       take a five-minute break, and we'll be back here at 10

8       'til.  Thank you.

9                 (Recess taken.)

10                 All right.  We have one last issue dealing

11       with Florida Power & Light, which is Issue 19.  Any

12       questions or concerns on Issue 19?  Do I hear a motion?

13       Commissioner Balbis.

14                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

15       And I will move forward with a motion and kind of frame

16       it with during the hearing I asked, I believe it was

17       OPC's witness, if in their review of all the information

18       provided by Florida Power & Light, were there any costs

19       that they considered to be imprudent, and I want Staff

20       to confirm that the witness testified that, no, there

21       were no costs incurred that were imprudent.  Is that

22       correct?

23                 MR. BREMAN:  That's correct.

24                 COMMISSIONER BALBIS:  So, therefore, based on

25       the discussion we've had on the issues, especially

FLORIDA PUBLIC SERVICE COMMISSION

51

1       associated with the intent to construct a project and to

2       pursue the option and all the discussion we have had, I

3       move forward with Staff's recommendation on Issue 19 for

4       this docket.

5                 CHAIRMAN GRAHAM:  It's been moved and seconded

6       Staff recommendation on Issue 19.  Any further

7       discussion?  Seeing none, all in favor, say aye.

8                 (Affirmative response.)

9                 Any opposed?

10                 (No response.)

11                 By your action, you have approved Issue 19.

12                 Staff, I want to thank you for the Florida

13       Power & Light portion of this.  I know Commissioner

14       Brisé and I were new on the scene when this came up last

15       year, and it was pretty hectic and there was a lot of

16       unanswered questions and there was a lot of craziness,

17       in my opinion, going on, and you guys were able to get

18       the answers that we needed and put it before us in a

19       nice, concise manner that was very understandable.  And

20       I do appreciate everything you guys did and the way you

21       were able, the way you were able to put it together.

22                 And, Florida Power & Light, we appreciate your

23       patience and your time and going through this vetting

24       process so we all have a clear path moving forward.

25                 That being said, we're moving on to Progress.

FLORIDA PUBLIC SERVICE COMMISSION

52

1       Let's start with Issues 20 through 24.

2                 Commissioner Brown.

3                 COMMISSIONER BROWN:  Thanks.  I'll start with

4       the joint ownership discussion.  There was a lot of

5       discussion during the hearing regarding joint ownership.

6       What effect, if any, does the joint ownership have,

7       would a joint ownership scenario have on the

8       cost-effectiveness of the Levy project under the

9       scenarios outlined in the Staff recommendation?

10                 MR. GARL:  This is Steve Garl again,

11       Commissioner.

12                 The biggest difference -- two big differences.

13       The immediate rate impact would decline for the PEF

14       customers.  However, at the same time, the benefits that

15       would accrue would also decline, and that would run for

16       the longterm.  And on the, on the chart on page 106

17       probably demonstrates that differently, because Progress

18       Energy has looked at 100% ownership, 80% ownership, and

19       50% ownership.  And as you can see by the numbers there,

20       that as Progress Energy's percentage of ownership

21       declines, it would indeed turn towards less

22       cost-effectiveness and at the same time much less

23       savings to the customers.

24                 COMMISSIONER BROWN:  I'm happy you did point

25       that out, and I appreciate that.

FLORIDA PUBLIC SERVICE COMMISSION

53

1                 Does Staff believe that pursuing a joint

2       ownership though would be beneficial for -- to mitigate

3       the rate impact to the customers?

4                 MR. GARL:  Absolutely.  It would have that

5       effect.  But, again, it's -- one has to keep in mind the

6       balance of cost versus benefits.

7                 COMMISSIONER BROWN:  Mr. Breman?

8                 MR. BREMAN:  Sorry to chime in here.  When you

9       say costs, it's the timing of costs and the timing of

10       rate impacts.  So if a utility went to a technology that

11       didn't have the type of cost recovery mechanism that is

12       available through the NCRC, the cost impact would be

13       there.  It would just be later in time and it would be

14       larger.

15                 COMMISSIONER BROWN:  But right now in the

16       process of obtaining the COL, I believe it was on the

17       record and in the Staff recommendation that the company

18       is not in the best position in seeking or obtaining a

19       joint owner because of the lack of issuance of the COL.

20                 MR. BREMAN:  It's a buyer's market today.

21       Yes, ma'am.

22                 COMMISSIONER BROWN:  Yes.  That being said, we

23       require Progress to submit annual report -- annual

24       reports, correct, regarding this issue and the progress

25       of the joint ownership?

FLORIDA PUBLIC SERVICE COMMISSION

54

1                 MR. GARL:  That is correct, Commissioner.

2       Each year we look at the joint ownership situation; has

3       there been some activity going towards that?  Yes, we

4       do.

5                 COMMISSIONER BROWN:  Would it be beneficial

6       for the Commission to have a more engaged dialogue, say,

7       more frequent reports, maybe quarterly reports, with the

8       caveat that if there's a significant rate impact, that

9       it would not be beneficial obviously to the ratepayers?

10                 MR. GARL:  That's certainly something the

11       Commission could entertain as a requirement.  It's

12       probably arguable whether an annual report of that

13       nature or more frequent would provide additional

14       information that would be of value, since we have the

15       cost recovery proceeding only once a year.

16                 COMMISSIONER BROWN:  Uh-huh.  Is it, would it,

17       would it have a rate impact to require the company to

18       produce additional reports, and what would that be, off

19       the top of your head?

20                 MR. GARL:  I couldn't even hazard a guess what

21       a report of that nature might cost, but there would be

22       always some cost involved in putting out a report.

23                 COMMISSIONER BROWN:  I bet someone on Staff

24       has an idea.

25                 MR. LAUX:  I'm not sure if I have an idea or

FLORIDA PUBLIC SERVICE COMMISSION

55

1       not.  It would increase cost.  The question becomes is

2       the activities that, that Progress Energy would do,

3       would they change significant -- would there be enough

4       changes in those activities that would require updated

5       reporting activity?  And I don't believe that that --

6       you would be receiving information that would, you know,

7       have any impact.  Partially the Commission doesn't

8       necessarily have a direct role in requiring somebody to

9       sign up, to become a joint owner.

10                 COMMISSIONER BROWN:  Of course.

11                 MR. LAUX:  And at this point in time Progress

12       Energy has not shown that they are not taking activity,

13       so that they may need a little push or incentive to move

14       forward.  They are continuing to engage in those

15       activities.  Joint owners will probably show up at the

16       time that is right for a joint -- when that joint owner

17       makes a decision that they want to become a joint owner,

18       and until then it'll be the joint owner's decision.

19                 So an annual review of what those activities

20       are is probably a good balance between cost to the

21       utility and its ratepayers and information to the

22       Commission.

23                 COMMISSIONER BROWN:  Thank you.  And how --

24       can you refresh my memory, how this issue was addressed

25       in the need determination?

FLORIDA PUBLIC SERVICE COMMISSION

56

1                 MR. YOUNG:  Commissioner, Keino Young.

2                 During the need determination there was

3       discussion in terms of should the order require Progress

4       Energy to seek a joint owner before the need is granted.

5       The Commission, at Agenda Conference, discussed it at

6       length, and it was not memorialized, the Commission did

7       not vote to require Progress Energy to have a joint

8       owner in order to, to determine a need determination.

9       So at this point they are not required to have joint

10       ownership.

11                 COMMISSIONER BROWN:  And nor does the

12       Commission have the authority to require.

13                 MR. YOUNG:  Nor does the Commission have the

14       authority to require it.

15                 COMMISSIONER BROWN:  That's all.

16                 CHAIRMAN GRAHAM:  Question.  When a joint

17       owner comes around, what is our role?  Do we approve the

18       joint owner?  Do we just determine if the deal was

19       prudent?  What is, what is our role as a Commission?

20                 MR. LAUX:  As to the actual contract that the

21       company would sign with any particular type of

22       organization to become a joint owner, I don't believe

23       the Commission would have overall authority to approve

24       or deny that contract.  The Commission would be able to

25       make a decision as to whether or not entering into that

FLORIDA PUBLIC SERVICE COMMISSION

57

1       contract is in the ratepayers' best interest, and

2       therefore the costs that flow from that contract, you'd

3       be able to make a decision as to whether or not those

4       actions, the costs that flow from those actions were

5       prudently incurred or not.

6                 It would have a fairly large impact on the

7       utility.  And my guess is, given the size of how that

8       would change the dynamics, the company would probably

9       come, in all likelihood, like we see in a lot of

10       wholesale contracts that have large dollar amounts, even

11       though the Commission doesn't necessarily again have

12       approval as to whether or not to approve or deny the

13       contract, when it's a large contract like that, the

14       utility usually will bring it by the utility for its --

15       or, I mean, bring it by the Commission for its review.

16                 CHAIRMAN GRAHAM:  Okay.

17                 Commissioner Brisé.

18                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

19                 I'm going to go back to the regulatory

20       feasibility.  The Intervenors mentioned many or several

21       regulatory uncertainties.  Can we walk through some of

22       those potential uncertainties and, and why we, why Staff

23       feels that Progress has, as the recommendation notes,

24       the necessary things in place to, to move forward with

25       this project, with this project?

FLORIDA PUBLIC SERVICE COMMISSION

58

1                 MR. GARL:  Yes, Commissioner.  The folks at

2       Progress Energy did indeed consider some of these

3       uncertainties, as shown by their cost-effectiveness

4       analysis.  They've provided the updated cost of fuel,

5       the updated cost of emissions, CO2 in particular, and

6       used those figures in its cost-effectiveness analysis.

7                 One other item that was mentioned by

8       Intervenors was the impact of the incident -- incident

9       is minimizing and I apologize for that -- but in Japan

10       at Fukushima, and that is still under consideration by

11       the NRC.  We don't know yet, they're still working on

12       that, but what impacts that may have.  And all the

13       testimony at the hearing suggested that we don't know,

14       but we don't think it will be significant.

15                 COMMISSIONER BRISÉ:  Okay.  So with all of

16       that, what put Staff in a posture to feel that Progress

17       should move forward with this project?

18                 MR. GARL:  That's correct.  There was nothing

19       shown by the Intervenors that suggested from a

20       regulatory standpoint that the project was not feasible.

21                 COMMISSIONER BRISÉ:  Okay.  Thank you.

22                 CHAIRMAN GRAHAM:  Commissioner Balbis.

23                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

24                 And I have a question for Staff on the

25       economic feasibility portion of Issue 20, which starts

FLORIDA PUBLIC SERVICE COMMISSION

59

1       on page 103.  There's a statement in the recommendation

2       on Page 107 concerning the low fuel scenario.  And the

3       question I had for Staff during the briefing was what,

4       what fuel scenario are we in?  And the statement here

5       that the low fuel scenario in the 2011 analysis has

6       prices below $5 per million Btu over 30 years, which

7       seems like -- I won't make that statement.  But can you

8       confirm that that is the case, that that low fuel price

9       forecast is below $5 for 30 years; is that correct?

10                 MR. GARL:  Yes, Commissioner.  That is indeed

11       accurate.  It's actually in the fuel forecast for the

12       low scenario, it's under $4 for the next 30 years.

13                 COMMISSIONER BALBIS:  So then, just to confirm

14       that Staff and Progress's position is that we should be

15       more in the mid-fuel reference; is that correct?

16                 MR. GARL:  That's about the best guess.  The

17       whole purpose of providing a range of fuel costs in

18       their forecast is the hopes that somewhere between the

19       high and low of that range is where it will actually

20       fall.  Obviously nobody knows for sure what the future

21       price will be.  And so all I can do is hope that the

22       actual price is in that range that they've used, mid --

23       the midrange is probably as good a guess as any.

24                 COMMISSIONER BALBIS:  And going back to Table

25       20-1, one concern I do have is that the only case,

FLORIDA PUBLIC SERVICE COMMISSION

60

1       regardless of percentage of ownership, where the LNP

2       project is not more cost-effective than the nonnuclear

3       alternative is the no carbon dioxide legislation; is

4       that correct?

5                 MR. GARL:  That's correct.

6                 COMMISSIONER BALBIS:  So the question for you

7       is, is does that take into account there's no

8       legislation that exists today, and then obviously

9       throughout the life of the project there's no CO2

10       legislation, but has there been a sensitivity analysis

11       that looks at, well, there might not be today, but there

12       may be one in three years and five years and ten years,

13       et cetera?  Has that analysis been performed and entered

14       into the record?

15                 MR. GARL:  Well, the sources that they use for

16       obtaining the cost of these emissions shows that if they

17       do occur, in some cases it won't occur until 2014 or

18       later.  It varies by the estimates that they've provided

19       about when a cost of CO2 might be implemented, and, of

20       course, to be sure they have used a cost of no CO2 as

21       one of their sensitivities.

22                 COMMISSIONER BALBIS:  I'm not sure I

23       understood that answer.  If you could clarify.  You

24       indicated that the source of information that they use

25       indicates a staggering of the implementation.  And if

FLORIDA PUBLIC SERVICE COMMISSION

61

1       so, is that indicated in that table, as in the EPA or

2       not?  Or is that just there is or there isn't in that

3       different rate?

4                 MR. GARL:  Well, I refer you back to page 104,

5       and Figure 20-2 probably explains it a little more

6       clearly than I may have stated it.

7                 The EPA and the CRA estimates of the CO2 costs

8       don't begin until 2021.  So depending on those

9       forecasts, it may or may not start within the next

10       couple years, or until 2021, or never.  They've tried to

11       cover all those bases.

12                 MR. LAUX:  Commissioner, I think that's what,

13       the reason why the parties will come in or the utilities

14       come in with multiple -- or forecasts from multiple

15       sources that may have different views on what the future

16       will look like.  And the key there is if they -- that

17       reality is probably -- or what may happen is going to

18       sort of be surrounded by those different types of

19       forecasts.  Whether it goes right down the middle of the

20       forecast, it's towards one side of the forecast, or the

21       other side of the forecast, it's probably anyone's guess

22       and not, and really not any type of information

23       available to be able to guess at.

24                 But as long -- if, if the project continues to

25       be cost-effective at both extremes, then as long as

FLORIDA PUBLIC SERVICE COMMISSION

62

1       you're in the middle, the project will remain

2       cost-effective.

3                 COMMISSIONER BALBIS:  I agree.  I just wanted

4       to point out for the record that, that the, the

5       different carbon dioxide legislation options do not, do

6       not anticipate legislation existing now, because it

7       doesn't take a rocket scientist to tell you there's no

8       carbon dioxide legislation in place, but that we do have

9       a range of alternatives on the different implementation

10       of carbon dioxide legislation, which is, I think

11       prepares us for any option a little better than just

12       either there is or there isn't.

13                 And obviously on an annual basis we will

14       reassess the likelihood of that legislation and the

15       effect on the cost-effectiveness of the project.  Is

16       that correct?

17                 MR. LAUX:  That's correct.  Each year these --

18       and some of the companies which produce these

19       forecasts -- and they're in the business of making

20       forecasts, so they want to try and be as accurate as

21       they can be as compared to the majority of what people

22       out there may think what the future will look like and

23       things like that.  But each year they will have a

24       different -- they will make a different forecast, the

25       same way as forecasts of what fuel may look like

FLORIDA PUBLIC SERVICE COMMISSION

63

1       20 years from now and things like that.  So each year

2       those are being updated, and it will be reflected in

3       this chart, similar to what is on 20, Table 20-1 on page

4       106.

5                 COMMISSIONER BALBIS:  Thank you.

6                 And, Mr. Chairman, my questions, my previous

7       questions were on Issue 20.  You had mentioned Issue 20

8       through 24.

9                 CHAIRMAN GRAHAM:  25.

10                 COMMISSIONER BALBIS:  Through 25.  I do have a

11       question on Issue, or a comment on Issue 23, if it's

12       appropriate at this time, or do you want to go

13       through --

14                 CHAIRMAN GRAHAM:  It's appropriate right now.

15                 COMMISSIONER BALBIS:  I would, I would just

16       like to reiterate the same comments on Issue 23 as I had

17       for Florida Power & Light.  I agree that Progress Energy

18       is moving forward with an intent to pursue an option,

19       and, again, I think that is a good decision to make,

20       considering the annual feasibility analysis that we go

21       through.  So I believe that my comments for Florida

22       Power & Light are also appropriate for Progress Energy,

23       and that's all the comments I have on that issue.

24                 CHAIRMAN GRAHAM:  Okay.

25                 Commissioner Brisé.

FLORIDA PUBLIC SERVICE COMMISSION

64

1                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

2       On Issue 23, I want for the record to note that, you

3       know, my position is similar with respect to the Staff

4       recommendation on the siting, licensing, and

5       construction, and that whole question about intent.

6                 I do want to also put on the record that I've

7       read a lot of comments that have come into the docket,

8       and I am sensitive to, to the notion that there is some

9       angst, at least in the public, with respect to moving

10       forward with these projects.

11                 But as laid out by statute and by a policy

12       decision that was made several years ago, which sought

13       to -- from my understanding, because I was around at

14       that time -- was to bring nuclear investment into the

15       state, and with that in mind the statute was formulated

16       in this fashion to, to spur that.  So with that in mind,

17       the companies are following what the intent of that

18       statute was, and with that we are, as a Commission,

19       implementing the statute as is prescribed by the

20       Legislature.

21                 So with that, I am comfortable with Staff's

22       recommendation, because the company is doing what is

23       required by statute for it to move forward, and there is

24       nothing that they are doing that is outside of the

25       bounds or that shows that they are not moving in the

FLORIDA PUBLIC SERVICE COMMISSION

65

1       direction of completing a project or moving towards the

2       completion of a project.

3                 So I wanted to make sure that I put that

4       onto -- on the record as part of my thought process as

5       to how I arrive at this decision.

6                 CHAIRMAN GRAHAM:  Thank you, sir.

7                 Commissioner Brown.

8                 COMMISSIONER BROWN:  Thank you.  And I

9       appreciate Commissioner Brisé's comments.  Although I do

10       have a question, I do appreciate you making those

11       comments.

12                 On Issue 22, OPC alleges in the Staff

13       recommendation and in their brief, in its brief that the

14       EPC contract faces potential cancellation.  Can you

15       elaborate on that?

16                 MR. GARL:  Just about cancellation?

17                 COMMISSIONER BROWN:  Uh-huh.  And whether

18       there's supporting evidence to support that.

19                 MR. GARL:  Yes.  The activities that Progress

20       Energy has going on right now, much like Florida Power &

21       Light, primarily focuses on the Nuclear Regulatory

22       Commission and their pursuit of the combined operating

23       license.  That activity has not ceased and they continue

24       looking for that and hope to receive their license as

25       well.  That in itself shows the direction they are

FLORIDA PUBLIC SERVICE COMMISSION

66

1       going, and as of right now there's no reason to believe

2       that they plan to cancel that effort.

3                 COMMISSIONER BROWN:  Or the contract itself,

4       the EPC contract.

5                 MR. GARL:  Correct.

6                 MR. LAUX:  Commissioner, the contract is still

7       in full force.  The activities that were -- the

8       activities required under that contract have been

9       rescheduled because of the pushback in when they are

10       going to get their COLA license.

11                 I'm a little unclear as to what your, the

12       testimony, exactly what you're talking about, but I

13       think I can make -- I don't know if this is exactly what

14       it was getting at.  If Progress Energy does not get

15       their COLA, they will cancel their contract to build the

16       plant because they cannot build the plant without the

17       COLA.

18                 COMMISSIONER BROWN:  Right.  That's an obvious

19       answer, and I appreciate you putting that on the record.

20                 MR. LAUX:  Sometimes it's the best way.

21                 COMMISSIONER BROWN:  Thank you.

22                 CHAIRMAN GRAHAM:  Any other questions on 20

23       through 25?

24                 Commissioner Balbis.

25                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

67

1       And if there are no questions on those issues, I move we

2       accept Staff's recommendations on Issues 20 through 25.

3                 CHAIRMAN GRAHAM:  It's been moved and seconded

4       Staff recommendations on Issues 20 through 25.  Any

5       further discussion?  None?  All in favor, say aye.

6                 (Affirmative response.)

7                 Any opposed?

8                 (No response.)

9                 By your action, you have approved Staff

10       recommendation on Issues 20 through 25.

11                 Staff, take us through 27 and -- 27A and B.

12                 MR. LAUX:  If I may, Commissioner, can I

13       address the As together and the Bs together, because

14       they're basically the same?

15                 CHAIRMAN GRAHAM:  That sounds good to me.

16                 MR. LAUX:  Okay.  27A and 28A was a request by

17       some of the Intervenors that the Commission should

18       either not allow or find unreasonable certain costs that

19       Progress Energy suggests that they're going to incur

20       that were not related to the COLA.  And the Intervenors

21       were saying that until they receive the COLA, they

22       should not incur those costs.  Staff is recommending

23       that the continuation of those activities is reasonable

24       because those costs -- or those activities were on the

25       critical path.

FLORIDA PUBLIC SERVICE COMMISSION

68

1                 CHAIRMAN GRAHAM:  All right.  So that's 27A

2       and 28A.

3                 Commissioners, do we have any questions of

4       those two Staff recommendations?

5                 Commissioner Brown.

6                 COMMISSIONER BROWN:  Thank you.

7                 Staff, OPC is arguing to disallow non-COL

8       costs.  Yet if we limited the recommendation to that,

9       wouldn't that push the commercial operation date past

10       the 2021, 2022 --

11                 MR. LAUX:  That's the evidence that I found

12       compelling in the, that was presented by Progress Energy

13       in the hearing, was that certain of those activities

14       that Witness Jacobs said that the company could defer

15       until, activity on until after they got the COL and then

16       somehow expedite those activities are on the actual

17       critical path for that project for a commercial

18       operation date of 2021, 2022.  And there was no real

19       information that was presented at the hearing to say

20       that you could actually veer off of that critical path

21       and continue to have the project come in on 2021, 2022.

22                 COMMISSIONER BROWN:  And it would increase the

23       rates as well if it goes past that 2021, 2022 date?

24                 MR. LAUX:  In all likelihood, that's correct.

25                 COMMISSIONER BROWN:  Thank you.

FLORIDA PUBLIC SERVICE COMMISSION

69

1                 CHAIRMAN GRAHAM:  Commissioner Balbis.

2                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

3       And thank you, Commissioner Brown.  I was going down

4       that exact same track, but I could not resist the

5       opportunity to discuss the infamous late-filed exhibit

6       that showed the critical path for the project.  And,

7       again, looking at that, that exhibit and the testimony

8       that was provided, I agree.  I could not find and the

9       record didn't indicate where the nonperformance of any

10       activities that were listed in that schedule would not

11       push out the project and the ratepayers would not start

12       receiving the benefits of these new units.

13                 So, with that, although there are activities

14       that they are performing that are not part of the

15       receipt of the COL, they are critical in order to bring

16       these projects online by the anticipated in-service

17       dates.

18                 CHAIRMAN GRAHAM:  All right.  27B and 28B.

19                 MR. LAUX:  Those are the -- the B portions of

20       those are the costs that are being requested for 2011

21       and 2012 estimated and forecasted costs.  If the

22       Commission does not make adjustments in the A sections

23       of those, Staff is recommending that the numbers that

24       Progress Energy has provided are reasonable.

25                 CHAIRMAN GRAHAM:  Commission, any questions on

FLORIDA PUBLIC SERVICE COMMISSION

70

1       the numbers provided in 27B or 28B?  If not, I'll

2       entertain a motion to move Staff recommendations on 27A

3       and B and 28A and B.

4                 Commissioner Brisé.

5                 COMMISSIONER BRISÉ:  Mr. Chairman, I move

6       Staff on -- Staff recommendation on 27A and B and 28A

7       and B.

8                 CHAIRMAN GRAHAM:  It's been moved and seconded

9       Staff recommendations on Issues 27A and B and 28A and B.

10       Any further discussion?  Seeing none, all in favor, say

11       aye.

12                 (Affirmative response.)

13                 Any opposed?

14                 (No response.)

15                 By your action, you have approved Staff

16       recommendations on 27A and B and 28A and B.

17                 All right.  36.

18                 MR. LAUX:  Commission, Issue 36 is how much

19       should the Commission approve as the withdrawal from the

20       rate management plan for recognizing recovery in 2012.

21       You had two proposals that were present to you -- was

22       presented to you during hearing.  One was to limit that

23       amount to $60 million, and one was made by Progress

24       Energy, which was approximately -- removal of

25       approximately 115 million, plus associated carrying

FLORIDA PUBLIC SERVICE COMMISSION

71

1       costs.

2                 Staff is recommending that the Progress

3       proposal should be approved because it believes it's

4       more effective at managing both short- and long-term

5       rates.  But either proposal can be approved.  They're

6       consistent with the overall objective that the

7       Commission stated in approving the rate management plan

8       in 2009.

9                 CHAIRMAN GRAHAM:  Commissioner Brisé.

10                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

11                 If you can address the long-term rate impact

12       for both proposals on consumers.

13                 MR. LAUX:  From the information that was

14       presented at hearing, if the Commission chose to limit

15       the withdrawal from the rate management plan to

16       $60 million, in the short-term it would have an

17       immediate effect of -- compared to the proposal that

18       Progress Energy had made -- and in the 2012 factor the

19       residential rate would go down by $1.75 a month.  That's

20       on a 1,000 kilowatt basis for a residential customer.

21                 It would have -- it would add to -- since the

22       balance is not being brought down as much as under the

23       Progress proposal, there would be continuing carrying

24       costs on it for the next year or two or until the

25       balance goes away.  I believe Witness Foster made the

FLORIDA PUBLIC SERVICE COMMISSION

72

1       presentation that it would put an additional pressure on

2       rates for the next two years, and that would mean that

3       you would basically take the balance, the remaining

4       balance and spread recovery over two years of $1.93 per

5       month.  Again, based on a 1,000-kilowatt-hour

6       residential customer.

7                 COMMISSIONER BRISÉ:  So you primarily

8       described the impact for the reduction by 60 million.

9       And if there are other projects that would come online,

10       how would that impact those as well, in terms of the

11       rates?

12                 MR. LAUX:  I don't believe it would have

13       this -- the full impact of which we're talking about

14       would be the impact within the clause.  So there would,

15       it would not necessarily be an impact on the base, on

16       base rate.

17                 The only potential impact on base rates at

18       this point in time would be the recognition of the

19       Phase 2 completion of Crystal River 3, and I don't

20       believe that that will be completed within the next two

21       years.

22                 COMMISSIONER BRISÉ:  Okay.  Thank you.

23                 CHAIRMAN GRAHAM:  Commissioner Balbis.

24                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

25                 And this is more for a discussion with the

FLORIDA PUBLIC SERVICE COMMISSION

73

1       Commission, because this is an issue that I had quite a

2       few discussions with Staff and a lot of internal, as in

3       in-my-mind discussions on what to do with this issue.

4       And --

5                 CHAIRMAN GRAHAM:  How does that work?

6                 COMMISSIONER BALBIS:  It's very busy in there,

7       I will tell you.

8                 (Laughter.)

9                 But one of the things that I thought about is

10       as opposed to our previous discussion on allowing

11       recovery for activities that aren't for the COL, you

12       know, obviously Progress Energy not increasing the

13       recovery this year is not going to advance, nor the lack

14       of recovery just limited to $60 million is not going to

15       push the project out.  So we have, you know, a little

16       bit of leeway and more assurances as we have some

17       flexibility here.

18                 So then I focused on, okay, what -- would

19       there be a harm to either the ratepayers or to Progress

20       Energy if we maintained the $60 million per year

21       recovery of that amount?  And I want to point out that

22       the reason we have this flexibility is because of

23       Progress Energy's concern over rate impact, because by

24       statute they could have requested recovery of the full

25       amount in the first year and had a significant rate

FLORIDA PUBLIC SERVICE COMMISSION

74

1       impact on its customers.  So I want to, you know,

2       applaud Progress Energy for being concerned about the

3       rate impact, but -- and allowing us this flexibility.

4       So really, for the Commission, kind of going either way

5       on this, and really the only harm would be the carrying

6       cost of the $60 million and the additional carrying

7       costs throughout the amortization period.

8                 So I'm anxious to hear my fellow

9       Commissioners' thoughts on this.  I think we have

10       flexibility -- I'm on the fence either way -- but to

11       hear what your thoughts are on this issue.

12                 CHAIRMAN GRAHAM:  I can tell you my thoughts.

13       I think anything we can do to minimize the impact today

14       is a good thing.  I know, I know that the mission of

15       our, the mission of our Governor is to do whatever we

16       can to minimize the, the rates, the electric rates so

17       we're encouraging more and more businesses to come here.

18       And, you know, anything you can put off, you know, put

19       off 'til tomorrow is a good thing with the economy that

20       we have today.

21                 Commissioner Brown.

22                 COMMISSIONER BROWN:  Thank you, Mr. Chairman

23       and Commissioner Balbis.

24                 And I'm happy to hear this dialogue, because I

25       also struggled a little bit over this issue and weighed

FLORIDA PUBLIC SERVICE COMMISSION

75

1       both scenarios.  But I felt, I felt more in line with

2       OPC's Witness Jacobs when he offered testimony that

3       provided that we need to -- encouraged us to keep the

4       rates as low as possible, absolutely necessary, and I

5       was leaning towards that position, keeping it capped at

6       60 million.

7                 But that being said, can Mr. Laux, can you go

8       over real quick one more time with me, with us on what

9       the carrying costs would be if we -- and I hate to use

10       the word accelerated recovery -- but if we allowed the

11       full recovery of the deferred balance within a year?

12                 MR. LAUX:  I was with you until the last

13       moment when you said the full amount.  And is the

14       question wiping out the complete deferred amount or the

15       Progress proposal as compared to the OPC's proposal?

16                 COMMISSIONER BROWN:  The latter.  Sure.

17                 MR. LAUX:  Okay.  If the Commission approved a

18       reduction of the approximately 150 -- $115 million, the

19       associated carrying charge on that is 14.1 million.  Now

20       I got -- because I can't see -- that's OPC -- or the

21       Progress scenario.  I believe it's $14.1 million.

22                 COMMISSIONER BROWN:  So that additional

23       14.1 million will be assessed against the deferred --

24       will be added to the deferred balance?

25                 MR. LAUX:  Oh, I'm sorry.  If you, if you

FLORIDA PUBLIC SERVICE COMMISSION

76

1       chose to approve the project, the Progress proposal of

2       withdrawing approximately $115 million, then the

3       associated carrying costs for 2012, given that change in

4       the balance and everything, would be $15.1 million.  If

5       you limit the amount to $60 million, there will be

6       carrying charges that will not be covered by that

7       amount, and it will be flowed back into the balance.  So

8       next year that balance will be a little bit higher by

9       whatever the noncoverage of those carrying charges are.

10                 That's one way of saying it.  Or saying that

11       of the 60 -- the carrying charges of $15.1 million would

12       be about the same, so the actual amount that the total

13       balance would go down by 60 million minus 15.1, so

14       you're at 45, $49.9 million.  You won't see the full

15       effect of $60 million coming out of the balance.

16                 COMMISSIONER BROWN:  But overall, if we go

17       with the OPC position, the ratepayers will be

18       cumulatively paying more.

19                 MR. LAUX:  Yeah.  It's -- the analogy is

20       whether or not you pay your credit card bill off

21       completely in one month or only a portion of it.  It's

22       the exact same approach.

23                 COMMISSIONER BROWN:  I'd be curious to hear

24       from the rest of the Commission on this.

25                 CHAIRMAN GRAHAM:  Commissioner Brisé.

FLORIDA PUBLIC SERVICE COMMISSION

77

1                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

2                 And that's where I'm conflicted, in that, you

3       know, considering the economy and what people are going

4       through today, the reduction sounds very tempting.

5       However, you know, none of us know what the economy is

6       going to be like two, three, four years down the line.

7       And the question is whether the impact today would be

8       equivalent to the impact three or four years down the

9       line in a similar economy.

10                 So, therefore, if the impact is greater three

11       or four years down the line, have we then caused more

12       harm to the consumer by this decision today, or if we

13       all hope for the best, that the economy gets better, so

14       therefore the -- everything remaining the same with an

15       economy getting better, then the impact then would be

16       potentially minimal to the consumer if we were able to

17       provide the reduction and then, you know, handle the

18       carrying costs later and so forth.

19                 So that's my thought.  That's where, that's

20       where my sense of, of trepidation is at this moment.

21                 CHAIRMAN GRAHAM:  Commissioner Balbis.

22                 COMMISSIONER BALBIS:  Thank you.  Thank you,

23       Mr. Chairman.

24                 And just to clarify, I know Staff and the

25       parties understand and we understand, but we're not

FLORIDA PUBLIC SERVICE COMMISSION

78

1       talking about delaying any of these costs.  These --

2       Progress Energy anticipated a $60 million amortization

3       of these costs over a number of years.  So the decision

4       before us is do we maintain that 60 million or do we

5       take advantage of an overestimation on another issue to

6       advance the payoff of these costs?  So I just want to be

7       clear for the record that's what we're, we are deciding.

8                 And to follow up on Commissioner Brown's

9       question, I think you were close to answering the

10       question, but not, at least not -- I wanted a certain

11       question asked.  Even if you did a net present value of

12       the total amount, including the carrying costs, whether

13       or not we advance it for that one year or not, what is

14       the total dollar amount are we dealing with, as in the

15       reduction of carrying costs by advancing the payment?

16                 MR. LAUX:  Well, I wish I had another schedule

17       (phonetic) to see if I could get close, but I believe

18       the answer to your question is I don't have that type of

19       information here today to be able to answer the question

20       with any type of accuracy.  It's a, it's almost like a

21       little do loop type thing.  Depending on how much you

22       bring down -- we know what the balance was before.  I

23       can calculate the carrying charges on that.

24                 Depending on how much you bring down, you may

25       be covering the minimum -- let's take the credit card

FLORIDA PUBLIC SERVICE COMMISSION

79

1       analogy again.  If the $60 million is the minimum

2       balance of the interest rate, you're not changing the

3       principal at all.  You're not, you're not reducing the

4       principal at all.  Therefore, the carrying charges will

5       be exactly the same next year, because all you're doing

6       is paying for the carrying charges.

7                 So I know this isn't a very good answer for

8       what you're looking for, but I don't believe I can give

9       you an answer very accurately.

10                 COMMISSIONER BALBIS:  Well, maybe another way

11       of going about it.  To simplify it, a hypothetical

12       situation, what are the carrying costs of $60 million

13       for a period of one year?

14                 MR. LAUX:  It's going to be somewhere in the

15       neighborhood of about -- I'm doing this in my head

16       fairly quickly -- approximately $7 million, $7 to

17       $8 million.

18                 COMMISSIONER BALBIS:  And just as Chairman

19       Graham is not an attorney, I'm not an accountant, but I

20       think that could be one way we could kind of put our

21       hands around what, what's the additional cost to the

22       ratepayers by --

23                 CHAIRMAN GRAHAM:  Let's take a five-minute

24       break so they can get an accountant.

25                 MR. BREMAN:  Considering I'll probably being

FLORIDA PUBLIC SERVICE COMMISSION

80

1       the one calculating the number, can I have more than

2       five minutes?  Can I have about 15?

3                 CHAIRMAN GRAHAM:  We're getting real close to

4       lunch.  If we're going to break, we could just break for

5       lunch.  I'm hearing a whole lot of "huh-uh" up here.

6                 MR. BREMAN:  Okay.

7                 CHAIRMAN GRAHAM:  So you've got five minutes

8       and ten minutes, if you need it.

9                 (Recess taken.)

10                 I think it's time to get some answers for --

11       was it Mr. Balbis?  For Mr. Balbis.

12                 Mr. Balbis, you have the floor.

13                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

14       And I guess, as I recall, I was trying to get a handle

15       on what the cost differences were if we, we did not

16       advance the recovery.

17                 MR. LAUX:  And, Commissioner, if you can

18       believe it, with all this information that I have right

19       here, I really can't get exactly to the number that

20       you're asking for, but I'm making some simplified

21       assumptions and how I believe things may happen in 2013

22       and 2014.

23                 I believe, if I understand your, your

24       question, is if you did 60 million from here on out

25       until the balance goes away, what would be the delta or

FLORIDA PUBLIC SERVICE COMMISSION

81

1       the difference in the amount of actual carrying costs

2       throughout that period?

3                 I believe it's going to be somewhere in the

4       neighborhood of about $15 million.  But that's the

5       difference between doing the 115 this year and guessing

6       as to what they would do the next couple of years as

7       compared to 60, 60, and then zeroing it out in 2015.

8                 And that $15 million, I can't really do a

9       differential as to compounding because I don't have --

10       there's some holes there of numbers that I don't have

11       because those decisions haven't been made yet.

12                 COMMISSIONER BALBIS:  And, again, the rate

13       plan that was approved by the Commission was a

14       $60 million amortization over a certain period; is that

15       correct?

16                 MR. LAUX:  That, that is not 100% correct.

17       The proposal, the initial proposal that Progress Energy

18       brought to the Commission in 2009 was a straight

19       amortization of the balance of $60 million throughout

20       time.  The Commission accepted the concept of a rate

21       management plan but not, but did not approve any type of

22       an amortization schedule to go with that, so that there

23       would be the ability to have some flexibility so that

24       the company could flex, could maybe recover more than

25       60 million in a year when, when maybe expenses were

FLORIDA PUBLIC SERVICE COMMISSION

82

1       lower, or recover less than 60 million a year when

2       expenses were higher.

3                 That -- then in 2010 -- and there was like, I

4       think, a little bit of confusion in the order that went

5       out, but the Commission then made it very clear in 2010

6       that not only did they not approve any type of a

7       schedule, but that the company had to come back in and

8       reaffirm what their plan was every year.  So in a sense

9       it becomes a zero budget game each year.

10                 COMMISSIONER BALBIS:  Thank you.

11                 MR. LAUX:  If the Commission did approve the

12       $60 million, it would be exactly what you were saying.

13                 COMMISSIONER BALBIS:  And, again, I just want

14       to point out, we're not delaying the recovery more than

15       what was initially expected or initially proposed by

16       Progress Energy.  And I believe it was Commissioner

17       Brisé that made the analogy on, or maybe it was Staff,

18       on repayment of a credit card debt.  Staff did that.

19       And I think that's a good analogy.

20                 And I look at it as when times are good and

21       you have, you know, a couple extra dollars in your

22       pocket, you look at maybe paying off a little bit more

23       of your mortgage ahead of time or credit card payments,

24       you know, to get ahead.  I'm not sure that Progress's

25       customers are there at this time.  I agree with Chairman

FLORIDA PUBLIC SERVICE COMMISSION

83

1       Graham; anything we can do now to help control rates is

2       important.  I think Progress recognized that in 2009

3       when we approved their plan, and I'm glad we have that

4       flexibility.  I'm leaning towards sticking with the

5       $60 million amortization per year at this time.  That's

6       all the comments I have.

7                 CHAIRMAN GRAHAM:  As I, as I kind of mumbled

8       up here before we took the break, this is considered the

9       wimpy financing.  I will gladly pay you on Tuesday for a

10       hamburger today.

11                 Commissioner Brisé.

12                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

13                 And, you know, I could live with the

14       $60 million aspect of the rate management plan.  And as

15       I said before, I just want to make sure that it's clear,

16       the, the impact on ratepayers two years down the line or

17       a year down the line.  I think that that needs to be

18       made clear, so that when we are at this juncture a

19       couple of years down the line and we not only have to

20       consider the 60 million, but then also consider the

21       carrying costs that we've delayed, that that is clear

22       today so that when we make that decision, I mean, as we

23       make the decision and have to implement it two years

24       down the line, that that is also clear that that is

25       coming.  And that's where I want Staff to help out in

FLORIDA PUBLIC SERVICE COMMISSION

84

1       clearly defining that for me.

2                 MR. LAUX:  We do have information that was put

3       in the record that the difference between a collection

4       of a hundred and, approximately $115 million with the

5       associated carrying costs, as compared to limiting it to

6       $60 million in 2012, will have -- if you're going to

7       limit the amount of time that the balance will be

8       collected to zero, it will have an impact of a dollar --

9       an additional impact of $1.93 per month for those two

10       years.

11                 Now the Commission is not restrained by that

12       two years.  They could say, okay, we're going to stretch

13       it out to three years or four years or five years.  That

14       will affect the impact of that amount.  But that's the

15       information that we did have in the record through

16       discovery.

17                 CHAIRMAN GRAHAM:  Commissioner Brisé.

18                 COMMISSIONER BRISÉ:  Thank you.

19                 So you're saying that there will be an

20       additional, additional $1.93 if we kept it to the time

21       as, as prescribed by, by Staff.  I mean, of course, we

22       could lengthen that and therefore the amount would be

23       reduced.

24                 MR. LAUX:  All things being equal, and as

25       comparing the Progress proposal as compared to basically

FLORIDA PUBLIC SERVICE COMMISSION

85

1       the limiting of total recovery from the rate management

2       plan to $60 million.

3                 COMMISSIONER BRISÉ:  Okay.  Thank you very

4       much.

5                 MR. BREMAN:  That will be 60 every year until

6       it's totally gone.

7                 CHAIRMAN GRAHAM:  Commissioner Balbis.

8                 COMMISSIONER BALBIS:  I have one last question

9       for Staff.  Has Progress Energy, in its application or

10       in the evidence that's in the record, have they

11       indicated there would be any harm to them in maintaining

12       a $60 million per year amortization?

13                 MR. LAUX:  I believe the answer to that was

14       no.  Witness Foster was asked a number of times about

15       the question of whether or not there would be harm.  He

16       tried to, I believe -- his answer, I believe, was yes.

17       But I think it was much more higher on a theoretical

18       kind of answer, in that if somebody owes you some money

19       and you're not collecting it in the time frame that

20       you're collecting it, then you would have to replace

21       that money in a very, very general way by going out, and

22       given the same types of cash flows and everything, you

23       would have to -- and you weren't collecting that money

24       from one person, you would have to go out and get it

25       from the marketplace.  That's the theory.

FLORIDA PUBLIC SERVICE COMMISSION

86

1                 I don't believe this would have a major impact

2       on cost rates of collecting money or the ability to

3       collect funds for ongoing operations for Progress

4       Energy.  I can't disagree with the theory, but it's a

5       very, it's a very high level theory.

6                 COMMISSIONER BALBIS:  Thank you.

7                 CHAIRMAN GRAHAM:  Commissioner Brown.

8                 COMMISSIONER BROWN:  I just want to be clear,

9       Staff.  Are we talking about the -- if we cap -- if we

10       adopt OPC's position here at the 60 million cap, that's

11       just for the 115 million in the deferred balance, not

12       the total remaining deferred balance, which is 200?

13                 MR. LAUX:  The complete deferred balance is

14       higher than $115 million.  All you would be approving at

15       this point in time is the withdrawal of $60 million from

16       the rate management plan.  It's a little bit of a reason

17       why I'm having a little bit of trouble answering the

18       question, because you may be taking $60 million out of

19       the fund, i.e., I'm pulling $60 million of principal

20       out, but I'm not covering my carrying charges, which

21       will then get capitalized back into the fund the next

22       year.  It's kind of a circular argument.

23                 If it's 60 million and first it goes towards

24       paying carrying charges, and then the remainder is how

25       much I pull out of the deferred balance, it's going to

FLORIDA PUBLIC SERVICE COMMISSION

87

1       be less than $60 million because you pay the interest

2       first.  Just like on your credit card, I'm making a

3       payment of $100, and they say, well, first you're paying

4       off the interest, and then I'll put it towards how much

5       you owe.  It's the same thing.

6                 CHAIRMAN GRAHAM:  To me, this is the way I

7       look at it.  If we're at 10.5% unemployment and a guy

8       that doesn't have a job now would much rather not have

9       to pay that extra money now.  He may have a job

10       tomorrow, and that of course doesn't mean he's going to

11       have a job tomorrow.  And it's going to be a little bit

12       more money tomorrow because you didn't pay a little

13       today and a little tomorrow.  But what it comes down to

14       is how much -- how great is the pain today?

15                 Commissioner Brisé.

16                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

17                 So then, going back to the question that

18       Commissioner Brown asked, in order to cover the carrying

19       costs for this $60 million that would be pulled out of

20       principal, we would have to add the 15 million to it to

21       make it 75 million to sort of just make it clean.

22                 MR. LAUX:  That's sort of the difficulty.  The

23       $15.1 million is based on a pulling out of approximately

24       $115 million.  If you change that amount, obviously

25       you're changing the carrying costs.

FLORIDA PUBLIC SERVICE COMMISSION

88

1                 COMMISSIONER BRISÉ:  Then you have to go back.

2       Understood.

3                 MR. LAUX:  Commissioner Graham, I agree with

4       you totally in the sense -- that's why I said that

5       either one of the plans is consistent with past

6       Commission's orders on this.  So I can tell you what the

7       economic -- I actually didn't do that good a job, but I

8       can almost tell you what the economic effects are on

9       different levels and all that.  As to the policy effects

10       and the equity effects, that's y'all's job.

11                 MR. BREMAN:  Staff -- excuse me for

12       interrupting on Mark's issue -- but Staff recommends

13       that you don't get involved in that complicated

14       compounding of interest adjustment.

15                 What we did in our recommendation is simply

16       take the total amount and just net out the tension

17       between the 114 and 60, and the net resulting number is

18       on page 154.

19                 MR. LAUX:  That would get into the total

20       amount that you would approve in Issue 37.

21                 MR. BREMAN:  $85,951,036.  If you want to do

22       the 60 million a year this year and then take another

23       look at, at the state of the world next year and decide

24       on a different amount possibly next year, and just do it

25       step by step, which is basically what Staff is

FLORIDA PUBLIC SERVICE COMMISSION

89

1       recommending.

2                 It's just that we said you have two options;

3       you can approve either one.  And those are the two

4       numbers, the $114 million in the last -- the

5       $140 million in the last paragraph, if you think

6       ratepayers can take the wallop today.  If they can't

7       take the wallop today, then set the factor lower.

8                 CHAIRMAN GRAHAM:  Commissioner Balbis for a

9       motion.

10                 COMMISSIONER BALBIS:  Thank you, Mr. Chairman.

11                 Based upon, again, the fact that the

12       maintenance of the $60 million amortization throughout

13       the period as originally offered by Progress in 2009

14       would not delay the commercial in-service date of the

15       Levy nuclear projects, and the fact that Progress did

16       not identify any material harm throughout the hearing,

17       I'm comfortable with moving forward with OPC's position

18       on the, as associated with the $60 million recovery.

19                 But I do want to point out, I want to thank

20       Progress Energy, because obviously they know their

21       ratepayers as we do and they're concerned with any

22       potential rate impacts.  And so, again, they offered

23       this as an option to the Commission in 2009.  They

24       certainly could have requested and we would have had to

25       allow the full recovery at one time, which would have a

FLORIDA PUBLIC SERVICE COMMISSION

90

1       much higher rate impact.  So I want to thank Progress

2       Energy for bringing this option to us for consideration.

3                 And I want to continue to encourage Progress

4       and Florida Power & Light and the other utilities on

5       giving us that type of flexibility, considering the

6       economic conditions of the state.  So I want to thank

7       Progress for that, and I certainly don't want to

8       discourage that type of behavior.

9                 But with that, I want, I move that on Issue 37

10       we adopt OPC's position as associated with the

11       $60 million.

12                 CHAIRMAN GRAHAM:  36.

13                 MR. LAUX:  Issue 36.

14                 COMMISSIONER BALBIS:  I'm sorry.  36.  With

15       the $60 million for the rate management plan.

16                 COMMISSIONER EDGAR:  Second.

17                 CHAIRMAN GRAHAM:  It's been moved and seconded

18       to go with the OPC recommendation on Issue 36.  Any

19       further discussion or further clarification?

20                 Staff, is that clear?  No discussion.

21                 All in favor, say aye.

22                 (Affirmative response.)

23                 Any opposed?

24                 (No response.)

25                 By your action, you have approved OPC's

FLORIDA PUBLIC SERVICE COMMISSION

91

1       recommendation on Item 36.

2                 Item 37.

3                 MR. LAUX:  Commission, with your vote on

4       Issue 36, I would recommend that the total amount that

5       should be available for recovery for the nuclear cost

6       recovery in 2012 be changed from the 140,919,397 to

7       85,951,036.  That would reflect limiting the recovery to

8       $60 million in the rate management plan.

9                 CHAIRMAN GRAHAM:  Commissioner Edgar.

10                 COMMISSIONER EDGAR:  Mr. Chairman, I would go

11       ahead and move approval on Issue 37, with the further

12       direction that the Staff make the necessary adjustments

13       in light our decision on Issue 36.

14                 CHAIRMAN GRAHAM:  It has been moved and

15       seconded for Staff to make necessary corrections on

16       Issue 37, but basically Staff recommendation.  Further

17       discussion?

18                 Commissioner Brown.

19                 COMMISSIONER BROWN:  Mr. Chairman, I don't

20       know if this is an appropriate time to make some final

21       comments on -- no.  Okay.

22                 CHAIRMAN GRAHAM:  Any other discussion on the

23       motion?  Seeing none, all in favor, say aye.

24                 (Affirmative response.)

25                 Any opposed?

FLORIDA PUBLIC SERVICE COMMISSION

92

1                 (No response.)

2                 By your action, you have approved Issue 37 as

3       stated.

4                 Commissioner Brown.

5                 COMMISSIONER BROWN:  Thank you.  And I just

6       wanted to make some final comments from today's

7       posthearing discussion.

8                 Given the economy and the hardships that the

9       ratepayers do face today, I want to be clear that we

10       give these matters highest consideration and with great

11       diligence, and we don't merely rubber-stamp our Staff's

12       recommendations by any means.

13                 Commission Staff, our auditors, and this

14       Commission board has carefully scrutinized all of the

15       data and numbers that were presented to us, and there's

16       no evidence in the record that suggested that any of the

17       requested costs were imprudent, and the statute requires

18       the recovery of all prudently incurred costs.  That

19       being said, until the law changes, we must allow

20       recovery of these prudently incurred costs.

21                 And with that, I thank the Commission board,

22       the Commission Staff for their great time and

23       investment.  It's a year-long process.  And the

24       utilities, of course.  That's it.

25                 CHAIRMAN GRAHAM:  Commissioner Balbis.

FLORIDA PUBLIC SERVICE COMMISSION

93

1                 COMMISSIONER BALBIS:  Thank you, Mr. Chair.

2       And just a follow-up on Commissioner Brown and some

3       brief comments.

4                 Again, this is a culmination -- I believe the

5       utility's first filings were due on March 1st, and there

6       was a six-month period of interrogatories and

7       discoveries back and forth, leading up to the hearing, I

8       believe, in August, and there's a culmination of a lot

9       of work by Staff, a lot of work by the Intervenors, and

10       a lot of work by the utilities.  So I want to thank

11       Staff, Intervenors, and the utility on this matter.  I

12       know I am comfortable and hopefully the ratepayers and

13       the public is comfortable that this issue has been

14       thoroughly scrutinized by all parties.  I want to thank

15       everyone's involvement and Staff for their hard work.

16                 CHAIRMAN GRAHAM:  Commissioner Edgar.

17                 COMMISSIONER EDGAR:  Thank you, Mr. Chairman.

18                 I recall a few years back when the statute

19       that we are implementing with our decisions today was

20       first discussed by the Legislature, ultimately voted,

21       voted for approval by the House and Senate, and then

22       signed by the Governor into law.  And as part of that

23       statute as passed at that time, it directed the

24       Commission, I believe, to adopt an implementing rule

25       within six months, which was at the time a pretty tight

FLORIDA PUBLIC SERVICE COMMISSION

94

1       time frame for us to meet those deadlines coming out of

2       the session and going into the due process requirements

3       of rulemaking.

4                 I said numerous times at the time, and I have

5       since, and I'd like to take the opportunity to say

6       again, that the rule that we are implementing this

7       statute through I believe at the time was an excellent,

8       comprehensive, and consensus work product.  Our Staff

9       did a great deal of work under a short time frame at

10       that time, with the input of many, many, many

11       stakeholders, all of which was greatly appreciated and

12       also played a key role in formulating the rule that we

13       have.

14                 Also, with that, I'd point out that at the

15       time we were promulgating the rule it was for a

16       brand-new statute and a new process, and as

17       Commissioners and as our Staff and those who would be

18       participating in the process all tried to look forward

19       and think through what issues would come up and what was

20       the best way under the statute to adopt them.  And,

21       again, I think we did an excellent job of that.  But I

22       do know now that we have gone through as a Commission

23       the process of utilizing that rule for the past couple

24       of years.  Probably some things have been learned

25       through that process.  I know some of the time frames

FLORIDA PUBLIC SERVICE COMMISSION

95

1       directed by the statute and then more prescriptively put

2       into the rule can be somewhat problematic, and we've had

3       some instances where we've needed and have been able to

4       address that.

5                 With all of that said, I still believe that

6       the rule that we are implementing is a good -- it's

7       young, but it's a very, very solid and professional

8       mechanism to implement the statute as it was intended to

9       be.  But I do recognize that, now that we've had a few

10       years of using it, there may be a time in the future

11       that as a Commission we might want to take a look at it

12       and have the opportunity for some stakeholder input and

13       see if there are ways to improve those processes.

14                 Now that we are closing out our annual cycle

15       on this, that certainly doesn't need to be right now.

16       There are a lot of issues going on with rulemaking going

17       into another session, but I certainly encourage our

18       Staff to give that some thought and, as I know they

19       have, be thinking about if there are some ways that we

20       can make this work even better as a Commission from our

21       regulatory processes.  And I appreciate the

22       professionalism and thoroughness that has been applied

23       to this process this year by all involved.

24                 CHAIRMAN GRAHAM:  Commissioner Brisé.

25                 COMMISSIONER BRISÉ:  Thank you, Mr. Chairman.

FLORIDA PUBLIC SERVICE COMMISSION

96

1                 I had the, I guess I would call it honor,

2       privilege, or --

3                 CHAIRMAN GRAHAM:  Duty.

4                 COMMISSIONER BRISÉ:  -- duty to be the

5       Prehearing Officer on, on this particular docket.  And I

6       want to commend Staff for their hard work from the

7       beginning to the end in working with all the parties.  I

8       want to thank all the parties for their input throughout

9       the process so that we can get to or arrive at this

10       particular point.

11                 My vantage point is a little bit different

12       from, from the rest of the Commissioners in that I had a

13       little bit to do with some of the statute, at least had

14       a chance to vote on parts of it, and to say that the

15       statute was designed for a particular purpose.  And I

16       think by implementing it, we are forwarding that

17       particular purpose, and that was to make it, make our

18       state a state that's favorable towards nuclear

19       development.  And the statute contemplated that, and

20       therefore by rule that was established by the Commission

21       created a venue and a process for that to occur.

22                 I think, as Commissioner Brown stated, if

23       there are issues that individuals may want to take, that

24       there are venues for that to occur.  And this may not

25       necessarily be the best venue to address some of those

FLORIDA PUBLIC SERVICE COMMISSION

97

1       issues, other than to look at what can be made better

2       through the rulemaking process so that this process

3       continues to provide the best opportunity for

4       ratepayer -- ratepayers to be in the best possible

5       position with respect to what is due to them with

6       respect to service and, and rates.

7                 So with that, Mr. Chairman, that concludes my

8       statements with respect to this particular docket.

9                 CHAIRMAN GRAHAM:  Thank you, sir.

10                 I want to thank Commissioner Brisé for being

11       the Prehearing Officer on this.  Thank you very much for

12       that.  I want to thank Progress for helping us through

13       this process and getting us the information in as timely

14       a fashion as possible for Staff.  And, Progress, we have

15       another big one coming up with CR3, which I believe is

16       going to be in February or March.

17                 MR. YOUNG:  February.

18                 CHAIRMAN GRAHAM:  February.  It's going to be

19       in February.  So we're halfway done with the nuclear for

20       Progress.  But I do want to thank you for what we've

21       done so far.

22                 And, OPC, I want to thank you as well.  You

23       guys do a great job of pointing out a lot of things that

24       we need to look at and we need to discuss, and we want

25       to thank you for that.

FLORIDA PUBLIC SERVICE COMMISSION

98

1                 And I want to thank the Intervenors as well

2       for that, and for allowing us to pull off, to pull out

3       Crystal River 3 so we can deal with the things that are

4       more straightforward and then we can deal with that on

5       its own separate docket.  I think that makes everything

6       a lot cleaner for everybody.

7                 And, Staff, I want to thank you guys all.  I

8       think you guys have done a fantastic job this year for

9       going through the nuclear clause, and you made the

10       process look pretty easy, pretty straightforward.  We

11       want to thank you for all your time you've done.

12                 That all being said, the Staff has bought

13       lunch for people out front.  So if you're interested in

14       a hot dog, you're welcome to come around and come join

15       us.

16                 That all being said, we are adjourned.

17                 (Proceeding adjourned at 12:19 p.m.)

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION

99

1

2       STATE OF FLORIDA    )

:         CERTIFICATE OF REPORTER

3       COUNTY OF LEON      )

4

5                 I, LINDA BOLES, RPR, CRR, Official Commission

Reporter, do hereby certify that the foregoing

6       proceeding was heard at the time and place herein

stated.

7

IT IS FURTHER CERTIFIED that I

8       stenographically reported the said proceedings; that the

same has been transcribed under my direct supervision;

9       and that this transcript constitutes a true

transcription of my notes of said proceedings.

10

I FURTHER CERTIFY that I am not a relative,

11       employee, attorney or counsel of any of the parties, nor

am I a relative or employee of any of the parties'

12       attorneys or counsel connected with the action, nor am I

financially interested in the action.

13

DATED THIS _____ day of _____________________,

14       2011.

15

16                  ________________________________

LINDA BOLES, RPR, CRR

17                 FPSC Official Commission Reporter

(850) 413-6734

18

19

20

21

22

23

24

25

FLORIDA PUBLIC SERVICE COMMISSION